Annual Action Plan 2026

| ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Project | Location | Time Frame |  |  |  |  | Cost |  |  |  | Project Status |  | Implementing Institution/Department |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 |  | GoG | DACF | IGF | Other | New | Ongoing | Lead | Collaborating |  |
| Equip the various Area councils to increase revenue mobilization | Area Councils |  |  |  |  |  | 20,000.00 |  | 50,000.00 |  |  |  | FINANCE BUDGET | Area council staff |  |
| Provide incentives to revenue collectors | District wide |  |  |  |  |  | 5,000.00 |  |  |  |  |  | FINANCE | BUDGET |  |
| Strengthen SMEs capacities for enhanced operations (e.g. Soap making, baking, wielding, hairdressing, | District Wide |  |  |  |  |  | 12,500.00 |  | 25,000.00 |  |  |  | BAC/BRC | Private Sector/NGOs |  |
| Establishment of Modern Industrial Park at Shama, Assorko and abuesi | Shama, Assorko Abuesi |  |  |  |  |  |  | 300,000.00 |  |  |  |  | District Aassembly | Private sector |  |
| Refurbishment of 4No. 40-unit Market Sheds, 1No. Warehouse, 1No. Meat Shop, 1No. 16- Seater Toilet, 1No.Urinal, Lorry Terminal, Drainage works, Security Lighting and 2No. Toll Booth (Phase1) | Shama junction |  |  |  |  |  |  | 10,000,000.00 | 257,250 |  |  |  | District Aseembly | District Aseembly |  |
| Promote the formation of Village Savings and Loans Associations | District wide |  |  |  |  |  |  | 7,500.00 | 7,500.00 |  |  |  | BAC | NGOs |  |
| Collaborate with Financial Agencies to provide soft loans to Small and Medium Scale Businesses | District wide |  |  |  |  |  |  |  | 5,000.00 |  |  |  | BAC | NGOs, Agric |  |
| Assist Small and Medium enterprises to develop business proposals and link them to Financial Sources. | District wide |  |  |  |  |  |  | 51,500.00 | 5,000.00 | 5,000.00 |  |  | BAC | NGOs |  |
| Organize Local Economic Development (LED) Committee meetings. | District wide |  |  |  |  |  |  | 4,470,250 | 7,500.00 | 7,500.00 |  |  | BAC | NGOs |  |
| Organise District (RELC)research and extension linkages for actors in the agricultural commodity value chain for PWD, youth and women farmers | District wide |  |  |  |  |  |  | 1,000,000 | 3,000.00 |  |  |  | MOFA | BAC |  |
| Monitoring of demonstrations, field officers, PWD, youth and women farmers | District wide |  |  |  |  |  |  |  | 7,000.00 |  |  |  | MOFA | NYA, BAC |  |
| Capacity building for traditional (poultry, livestock, piggery) and non- traditional farmers (grasscutter, rabbit, snail, bee keeping) | District wide |  |  |  |  |  |  | 4,000.00 |  | 58,750.00 |  |  | MOFA | NGOs |  |
| Conduct home and farm visits to operational areas (Nkoko Nketenkete, PERD and FBO formation) / mobilise support and orientation for NKOKONKETENKETE | District wide |  |  |  |  |  |  |  | 35,000.00 |  |  |  | MOFA | Farmers |  |
| Training programme for selecteted farmers and field staff on climate smart agriculture | District wide |  |  |  |  |  |  |  | 4,500.00 |  |  |  | MOFA | NYA, BAC |  |
| Provision of agro processing equipment to farmers and Agric mechanization | District wide |  |  |  |  |  |  |  |  | 22,500.00 |  |  | Private sector | MOFA |  |
| Educate fisher folks on bad fishing practices and proper fish handling and management. | District wide |  |  |  |  |  | 15,000.00 | 3,000.00 | 7,500.00 |  |  |  | MOFA | BAC, NGOs |  |
| Sensitize fisher-folks on healthy fish handling, illegal fishing and post-harvest losses and management | District wide |  |  |  |  |  |  | 5,000.00 | 2,500.00 |  |  |  | DADU | BAC, NGOs |  |
| Update Database on Fishermen and fish vessels | District wide |  |  |  |  |  |  | 3,750.00 | 5,000.00 |  |  |  | DADU | BAC, NGOs |  |
| Annual cultural day celebration | District wide |  |  |  |  |  | 8,000.00 |  |  |  |  |  | CNC | DEV’T PLANNING |  |
| Cultural tourism promotion (promoting Shama’s cultural attraction and clean-up of tourist sites | District wide |  |  |  |  |  | 2,000.00 |  | 145,209.46 |  |  |  | CNC | DEV’T PLANNING |  |
| Youth cultural empowerment through cultural mentorship programmes skills development and historical site tour | District wide |  |  |  |  |  | 1,217,500 |  |  | 11,250.00 |  |  | CNC | DEV’T PLANNING |  |
|  |  | Sub-Total |  |  |  |  | 1,270,000.00 | 2,374,750.00 | 529,209.46 | 105,000.00 |  |  |  |  |  |
|  |  | Total: |  |  |  |  | 4,278,959.46 |  |  |  |  |  |  |  |  |
| SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project | Location | Time Frame |  |  |  |  | Cost |  |  |  | Project Status |  | Implementing Institution/Department |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 |  | GoG | DACF | IGF | Other | New | Ongoing | Lead | Collaborating |  |
| Continuation and Completion of 3No. 2- Storey 6-Unit Classroom Block | Komfueku, Essaman & Assorko |  |  |  |  |  |  | 100,000.00 |  | 5,416.4 |  |  | SDA | GES |  |
| Continuation and Completion of 2No. 2- Storey 6-Unit Classroom Block at Aboadze Islamic & Shama Junction | Aboadze Shama Junction |  |  |  |  |  | 200,000.00 |  |  |  |  |  | SDA | GETFUND |  |
| Continuation and Completion of 4No. 3- Unit Classroom Block with Ancillary Facilities | Kedzi-Cran, Anlo Beach,Old Daboase Junction, Abuesi and Ohiamadwen |  |  |  |  |  | 500,000.00 |  |  |  |  |  | SDA | GETFUND |  |
| Rehabilitation of 3No. 6-Unit Classroom Block | Shama methodist Anto Essumankrom |  |  |  |  |  |  |  | 500,000 |  |  |  | SDA | GETFUND |  |
| Construction of Model Basic School Complex | Shama Junction |  |  |  |  |  |  | 58,480.02 |  | 100,000 |  |  | SDA | GES |  |
| Construction of 3No. 2- Unit KG Block (L- shape) | Krobo bosomdo, and Antseambua, shama catholic |  |  |  |  |  |  |  |  | 100,000 |  |  | SDA | GES |  |
| Construction of 4No. Single Storey 3-Unit Primary Block (Double Verandah) | Aboso, Anlo Beach, supomu, Beposo |  |  |  |  |  |  |  | 5,000,000 |  |  |  | SDA | GES |  |
| Construction of 1No. Single Storey 6-Unit JHS Block at | Dwomo |  |  |  |  |  |  |  | 5,000,000 |  |  |  | SDA | GES |  |
| Completion of 3No. 3- Unit Classroom Block with Ancillary Facilities | Ohiamadwen, old Daboase Junction Anlo beach |  |  |  |  |  |  |  |  | 200,000 |  |  | SDA | GES |  |
| Completion of 1No. 4- Unit Semi-Detached Chamber and Hall Teacher's Quarters | Shama |  |  |  |  |  |  |  | 200,000 |  |  |  | SDA | GES |  |
| Provision of 4000 desk furniture (mono, dual, hexagonal) | District wide |  |  |  |  |  | 500,000.00 |  |  |  |  |  | SDA | GES |  |
| Provide Scholarship to needy but brilliant students across the district | District wide |  |  |  |  |  | 500,000.00 |  |  |  |  |  | SDA | Privat e Sector |  |
| Form gender clubs in schools and communities | District wide |  |  |  |  |  |  |  | 35,000.00 |  |  |  | GES | NGOs |  |
| Organize Community sensitization on Back to School / Re-Entry Policy. | District wide |  |  |  |  |  | 40,000.00 |  | 13,000 |  |  |  | GES | NGOs |  |
| Organize “My first day at school” ceremony in all KG and Primary one Schools | District wide |  |  |  |  |  | 30,000.00 |  | 25,000.00 |  |  |  | SDA | GES |  |
| Conduct regular monitoring and inspection of schools | District wide |  |  |  |  |  | 45,000.00 |  |  |  |  |  | SDA | GES |  |
| Organize Independence Day Celebration | District wide |  |  |  |  |  |  |  |  | 60,000.00 |  |  | SDA SDA | GES/private sector |  |
| Organization of District Mock for all final year pupils in JHS 3 | District wide |  |  |  |  |  | 200,000.00 |  |  |  |  |  | SDA | GES/private sector |  |
| Organize DEOC Meetings | District wide |  |  |  |  |  |  |  | 29,000.00 |  |  |  | SDA | GES |  |
| Organize Sports and Cultural Activities | District wide |  |  |  |  |  | 30,000.00 |  | 22,000.0 |  |  |  | GES | DSC/Private Sector |  |
| Construction of 4No. CHPS Compounds (Clinic & Quarters) | Asem Asa, Dwomo, poano, shama Kumasi |  |  |  |  |  |  | 400,000 |  |  |  |  | SDA | DHD |  |
| Construction of Maternity block | shama |  |  |  |  |  |  | 1,100,000.00 |  |  |  |  | SDA | DHD |  |
| Construction of nurses Quarters | shama |  |  |  |  |  |  | 3,000,000 |  |  |  |  | SDA | DHD |  |
| Continuation and Completion of 1No. CHPS Compound (Clinic & Quarters) | Abuesi |  |  |  |  |  |  | 100,000.00 |  |  |  |  | SDA | DHD/private sector |  |
| Construction of 100- bed capacity District Hospital | Shama |  |  |  |  |  | 2,000,000.00 |  |  |  |  |  | SDA | DHD/private sector |  |
| Renovate existing facilities (Fawomanye CHPS and quarters, Anapansu CHPS, Dunkwa CHPS) | Fawomanye Anapansu, supomu Dunkwa Dunkwa |  |  |  |  |  | 2,000,000 |  |  |  |  |  | SDA | DHD/private sector |  |
| Procure health equipment for various health facilities | District wide |  |  |  |  |  |  |  |  | 100,000.00 |  |  | SDA | DHD/private sector |  |
| Establish adolescent clubs in schools and communities | District wide |  |  |  |  |  |  |  | 7,500.00 |  |  |  | DHD | NGO |  |
| Organize District wide Health and HIV Screening | District wide |  |  |  |  |  | 6,250.00 |  |  |  |  |  | DAC/GHS | NGO |  |
| conduct monitoring and supervision to facilities | District wide |  |  |  |  |  | 5,000.00 | 4,500.00 |  |  |  |  | GHS | DHD |  |
| Operationalize the District Health committee and Community Health Management Committees | District wide |  |  |  |  |  | 7,500.00 | 11,250.00 |  |  |  |  | SDA | DHD |  |
| Org anise Health Review Meetings | District wide |  |  |  |  |  | 7,500.00 |  | 5,000.00 |  |  |  | DHD | SDA/GOG |  |
| Train health staff | District wide |  |  |  |  |  | 7,500.00 |  |  | 25,000.00 |  |  | DHD | Private sector |  |
| Distribute LLINs to vulnerable groups | District wide |  |  |  |  |  | 37,500.00 |  |  | 25,000.00 |  |  | DHD | NGO |  |
| Organize HIV sensitization in schools | District wide |  |  |  |  |  | 10,000.00 |  |  |  |  |  | DAC/GHS | NGO |  |
| Intensify comprehensive education on HIV/AIDS and STIs, including reduction of stigmatization | District wide |  |  |  |  |  | 8,750.00 | 3,750.00 |  |  |  |  | DAC/GHS | NGO |  |
| Expand and intensify HIV Counselling and Testing (HTC) programs in the district | District wide |  |  |  |  |  | 3,750.00 |  |  |  |  |  | DHD | NGOs |  |
| Celebration of World AIDS Day | District wide |  |  |  |  |  | 25,000.00 |  |  |  |  |  | DAC/GHS | NGO |  |
| Restructure and re-position the district Birth and Death Registry | District wide |  |  |  |  |  | 6,250.00 |  |  |  |  |  | Birth & Death | GHS |  |
| Organize education in schools, hospitals/health facilities and communities on birth and death registration | District wide |  |  |  |  |  | 10,000.00 | 5,000.00 |  |  |  |  | Birth & Death | GHS |  |
| Conduct annual mobile registration | District wide |  |  |  |  |  |  |  | 5,000.00 |  |  |  | Birth & Death | GHS |  |
| Supply 10 No. waste containers | District wide |  |  |  |  |  | 3,000.00 |  | 300,000.00 |  |  |  | EHU | WORKS |  |
| Construct 3 No. 8-seater institutional toilet | Anto, Konfueku and Anlo Baech |  |  |  |  |  |  | 777,250 | 300,000 |  |  |  | EHU | DONERS |  |
| Procurement of skip truck | shama |  |  |  |  |  |  | 500,000 |  |  |  |  | EHD | procurement |  |
| Procurement of 3No. tricycle | districtwide |  |  |  |  |  |  | 110,000 |  |  |  |  | EHD | procurement |  |
| Undertake provision and usage of 200 Household Toilets with Biodigester system in deprived communities | District wide |  |  |  |  |  | 250,000.00 | 100,000 | 100,000 |  |  |  | EHD | CODA/ Works |  |
| Construct 1 No. slaughter slab | Inchaban |  |  |  |  |  | 3,000.00 | 5,000,000 | 6,000.00 |  |  |  | EHU | WORKS |  |
| Acquire an engineered sanitary landfill | District wide |  |  |  |  |  | 400,000.00 |  | 3,000.00 | 3,000.00 |  |  | EHU | WORKS |  |
| Evacuate and Push 10 refuse heaps sites | District wide |  |  |  |  |  | 560,000.00 |  | 24,000.00 |  |  |  | EHU | WORKS |  |
| Purchase 15no. skip containers | District wide |  |  |  |  |  | 24,000.00 | 200,000.00 |  |  |  |  | EHU | WORKS DEPT. |  |
| Purchase and supply of cleaning tool – 50 n. wheelbarrows, 2 no. water storage tanks, 50 no shovels, 50 no. pick rods, 25 no spades, 100 no. wellington boots, 30 no. machetes and 20 no. rakes | District wide |  |  |  |  |  | 5,000,000.00 | 45,000.00 | 209,000.00 |  |  |  | EHU | WORKS DEPT, SDA |  |
| Supervise activities of waste management contractors in the district | District wide |  |  |  |  |  | 120,000.00 |  | 60,000.00 |  |  |  | EHU | WORKS DEPT, |  |
| Sensitize landlords on provision of household latrines. | District wide |  |  |  |  |  | 6,000.00 |  | 4,500.00 |  |  |  | EHU | WORKS |  |
| Carry out Fumigation and Sanitation improvement activities | District wide |  |  |  |  |  |  |  | 45,000.00 |  |  |  | EHU | ZOOMLION |  |
| Organize Community Clean-up activities across the district | District wide |  |  |  |  |  | 6,000.00 |  | 9,000.00 |  |  |  | EHU | N GOs/ NYA |  |
| Educating the public on proper waste management/CLTS | District wide |  |  |  |  |  | 6,000.00 |  |  |  |  |  | EHU | ISD/NCCE |  |
| Reconstitute the Community water and Sanitation Boards in the Various Communities | District wide |  |  |  |  |  | 3,000.00 |  | 3,000.00 |  |  |  | Planning Unit | EHU/NGOs |  |
| Train Community Water and Sanitation Board members | District wide |  |  |  |  |  | 3,000.00 |  | 3,000.00 |  |  |  | Planning Unit | EHU |  |
| Revamping of the DWST at the Assembly and WSMTs in the communities | District wide |  |  |  |  |  | 6,000.00 |  | 6,000.00 |  |  |  | SDA | EHU |  |
| Reactivate and strengthen the Community –Led Total Sanitation (CLTS) approach | District wide |  |  |  |  |  | 6,000.00 |  | 3,000.00 |  |  |  | SDA | EHU |  |
| Educate and encourage households to provide household toilets, covered well or boreholes for households and rainwater harvesting | District wide |  |  |  |  |  |  |  | 6,000.00 | 30,000.00 |  |  | SDA | EHU/NGOs |  |
| Develop a Local Policy and Minimum Standards Operation and Maintenance Policy and Guidelines for WASH activities in the district. | District wide |  |  |  |  |  | 6,000.00 |  |  |  |  |  | SDA | EHU |  |
| Create a platform for dialogue between water service providers, political leaders and communities(beneficiaries) | District wide |  |  |  |  |  | 6,000.00 |  |  |  |  |  | SDA | EHU |  |
| Develop result- community based strategies to address Open Defecation Free (ODF) issues in our communities | District wide |  |  |  |  |  | 3,000.00 |  | 9,000.00 |  |  |  | SDA | EHU |  |
| Public education on proper food handling & medical screening | District wide |  |  |  |  |  |  |  | 9,000.00 |  |  |  | EHU | ISD/NCCE |  |
| Educating the public on the dangers of stray animals | District wide |  |  |  |  |  |  |  | 6,000.00 |  |  |  | EHU | WORKS |  |
| Scale-up sensitization campaigns to promote proper handwashing and hygiene practices particularly among children | District wide |  |  |  |  |  | 6,000.00 |  | 6,000.00 |  |  |  | EHU/GES | NGOs |  |
| Organize sensitization program on child abuse, online safety teenage pregnancy | 5 selected communities |  |  |  |  |  |  |  | 2,500.00 | 10,000.00 |  |  | DSW/CD | UNICEF/NGOs |  |
| Capacity building Programme for stakeholders on addressing child labor issues | District wide |  |  |  |  |  |  |  | 5,000.00 | 15,000.00 |  |  | DSW/CD | UNICEF/NGOs |  |
| Intersectoral training on foster parenting | District wide |  |  |  |  |  | 3,750.00 |  |  | 12,500.00 |  |  | DSW/CD | UNICEF/NGOs |  |
| Sensitize community members on existing leap programmes and helping them to solve challenges | District wide |  |  |  |  |  | 5,000.00 |  | 2,500 | 3,500.00 |  |  | DSW/CD | SDA |  |
| Monitor and Support people with Disabilities (PWDs) with items/cash, school fees and medical bills | District wide |  |  |  |  |  | 12,500.00 | 400,000.00 | 5,000.00 |  |  |  | DSW/CD | LEAP |  |
| Case management; child custody, maintenance, defilement, child neglect etc. | District wide |  |  |  |  |  |  |  | 2,500.00 |  |  |  | DSW/CD | NGOs |  |
| Organize District Fund Management committee meetings | District wide |  |  |  |  |  |  |  | 5,000.00 |  |  |  | DSW/CD | NGOs |  |
| Organize social services sub- committee meetings | District wide |  |  |  |  |  |  |  | 20,000.00 |  |  |  | DSW/CD | NGOs |  |
| Organization and training of PWDs on savings, social issues and income generating activities. | District wide |  |  |  |  |  |  |  | 4000.00 |  |  |  | DSW/CD | NGOs |  |
| Procure logistics needed for social welfare Department | District wide |  |  |  |  |  | 7,500.00 |  | 5,000.00 | 12,500.00 |  |  | DSW/CD | procurement |  |
| Monitoring and inspection of day care schools and visitation to 200 homes | District wide |  |  |  |  |  |  |  | 3,750.00 |  |  |  | DSW/CD | NGOs/GES |  |
| Organize free breast cancer screening to celebrate breast care month | districtwide |  |  |  |  |  | 4,200.00 |  |  | 13,200.00 |  |  | Gender desk | UNICEF/NGOs |  |
| Organize sensitization on sexual assault and Gender Based Violence | District wide |  |  |  |  |  | 6,000.00 |  |  | 12,500.40 |  |  | Gender desk | UNICEF/NGOs |  |
| Sensitization on cervical cancer and HPV vaccination in 3 second cycle institutions | District wide |  |  |  |  |  | 6,250.00 |  |  | 10,500.00 |  |  | Gender desk | UNICEF/NGOs |  |
| Observe world male mental health day and sensitization on erectile dysfunction | District wide |  |  |  |  |  | 6,250.00 |  |  | 12,000.00 |  |  | Gender desk | UNICEF/NGOs |  |
|  |  | Sub-Total |  |  |  |  | 12,565,250 | 6,706,430.02 | 525,321 | 646,916.4 |  |  |  |  |  |
|  |  | Total |  |  |  |  | 20,443,917.4 |  |  |  |  |  |  |  |  |
| ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project | Location | Time Frame |  |  |  | Cost |  |  |  |  | Project Status |  | Implementing Institution/Department |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 |  | GoG | DACF | ICF | Other | New | Ongoing | Lead | Collaborating |  |
| Grading and maintenance of feeder roads (100km) | District wide |  |  |  |  |  |  | 100,000 |  |  |  |  | Works | DFR |  |
| Spot improvements and reshaping of town roads (80km) | District wide |  |  |  |  |  | 500,000 |  |  |  |  |  | Works | DFR |  |
| Rehabilitation and creation of access roads in farming communities (10km) | District wide |  |  |  |  |  | 100,000 |  |  |  |  |  | Works | DFR |  |
| Upgrade and reshaping of roads (25 km) across the district | District wide |  |  |  |  |  | 63,500,000 |  |  |  |  |  | DFR | Works |  |
| Strengthen the Assembly’s cooperation with Transport Unions (GPRTU & Others) | District wide |  |  |  |  |  |  | 6,000.00 |  |  |  |  | SDA | GPRTU |  |
| Promote and institutionalize knowledge, skills and attitudinal change programmes for transport sector personnel | District wide |  |  |  |  |  | 6,000.00 |  |  |  |  |  | SDA | GPRTU |  |
| Procure 2 pick ups for monitoring and revenues | Office Use |  |  |  |  |  |  |  | 1,400,000.00 |  |  |  | SDA | Transport Unit |  |
| Enforce road regulations | District wide |  |  |  |  |  |  |  | 13,000.00 |  |  |  | City Guards | Ghana police |  |
| Organize Road safety Campaigns | District wide |  |  |  |  |  |  |  | 15,000.00 |  |  |  | Road safety authority | Ghana Police |  |
| Facilitate for extension of electrification to rural communities | District wide |  |  |  |  |  | 10.000.00 |  |  |  |  |  | Admin | ECG/Works |  |
| Support the installation and maintenance of Streetlights | District wide |  |  |  |  |  | 50,000.00 |  |  |  |  |  | Works | Admin |  |
| Facilitate for provision of storm and U-drains | District wide |  |  |  |  |  | 40,000 |  |  |  |  |  | CODA | MP/Works |  |
| Facilitate for provision and rehabilitation of bridges | District wide |  |  |  |  |  | 40,000 |  |  |  |  |  | CODA /DFR | MP/ Works |  |
| Support Community Initiated Projects (CIP) | District wide |  |  |  |  |  | 100,000 |  |  |  |  |  | DA | CD /Works |  |
| Undertake desilting,dredging and opening of storm drains in flood prone communities | District wide |  |  |  |  |  | 200,000 |  |  |  |  |  | EHD | CODA/ Works/ |  |
| Facilitate the extention of Pipe borne water system to selected communities | District wide |  |  |  |  |  |  | 200,000.00 |  |  |  |  | CWSA | DA/ Works |  |
| Drilling and construction of 20no. Borehole water in selected communities | District wide |  |  |  |  |  |  |  | 100,000 |  |  |  | CODA | Works |  |
| Repair and maintenance of 20no. existing Borehole water in selected communities | District wide |  |  |  |  |  | 6,500 |  | 27,151.00 |  |  |  | Works | CWSA |  |
| Facilitate the improvement of telecommunication network in deprived communities | District wide |  |  |  |  |  | 40,000 |  |  |  |  |  | Admin | MP/Works |  |
| Maintain ICT Buildings and support the improvement of ICT infrastructure | District wide |  |  |  |  |  | 100,000 |  |  |  |  |  | CODA | MP/Works |  |
| Construction of Office Complex for the District Security Services with National Ambulance & Fire Stations at Aboadze | Aboadze |  |  |  |  |  | 200,000 |  |  | 48,000 |  |  | Private companies | SDA/ GNFS/GPS |  |
| Construction of Residential Accommodation for other decentralized departments | Shama |  |  |  |  |  |  |  | 100,000.00 |  |  |  | Admin | NAS / Works |  |
| Continuation and completion of District Assembly Block for Agric Department at Shama | Shama |  |  |  |  |  |  |  | 902,500 |  |  |  | Admin | Works |  |
| Construction of staff quarters | Shama |  |  |  |  |  |  | 100,000.00 |  |  |  |  | Works | Admin |  |
| Continuation and Completion of Area Council Office at Abuesi | Abuesi |  |  |  |  |  | 200,000 |  |  |  |  |  | Works | Admin |  |
| Construction of 5No. Area Council Office buildings for Shama, Shama Junction, Inchaban, Assorko, Supomu Dunkwa | Shama, Shama Junction, Inchaban, Assorko, Supomu Dunkwa |  |  |  |  |  |  |  | 50,000 |  |  |  | Works | Admin |  |
| Maintenance of District Assembly Office Buildings | shama |  |  |  |  |  |  | 400,000 |  |  |  |  | Works | Admin |  |
| Maintenance of District Assembly Official Residential Buildings | shama |  |  |  |  |  |  |  |  |  |  |  | Works | Admin |  |
| Provision and Maintenance of Revenue Collection Posts / Barriers | District wide |  |  |  |  |  | 10,000.00 |  |  |  |  |  | Finance | Works |  |
| Prepare and produce designs and work drawings for approved projects | District wide |  |  |  |  |  | 5,000.00 |  |  |  |  |  | Works | Admin |  |
| Prepare and produce Bill of Quantities/ Activity Schedule for approved projects | District wide |  |  |  |  |  | 5,000.00 |  |  |  |  |  | Works | Admin |  |
| Undertake management and supervision for approved works and housing, roads, water and sanitation projects | District wide |  |  |  |  |  | 5,000.00 |  |  |  |  |  | Works | Admin |  |
| Prepare and produce Operation and Maintenance Plan, maintain and update the Assets Register for the District | District wide |  |  |  |  |  | 5,000.00 |  |  |  |  |  | Works | Admin |  |
| Undertake daily inspection and control of developments and enforce the building regulations and code of practice | District wide |  |  |  |  |  | 5,000.00 |  |  |  |  |  | Works | Admin |  |
| Form Disaster Volunteer’s Groups (DVGs) across the district | District wide |  |  |  |  |  |  | 3,000.00 |  |  |  |  | NADMO | NGOs |  |
| Undertake tree planting exercise | District wide |  |  |  |  |  |  | 6,000.00 |  |  |  |  | NADMO | NGOs/forestry |  |
| Public education and Sensitization on climate change to minimize its impact and Initiate Green District campaign | District wide |  |  |  |  |  | 6,000.00 | 3,000.00 |  |  |  |  | NADMO | forestry |  |
| Organize Community Engagements on Disaster Risk Reduction Measures | District wide |  |  |  |  |  | 3,000.00 |  |  |  |  |  | NADMO | GNFS |  |
| Communal labour; desilting of drains, clean up exercise | District wide |  |  |  |  |  | 6,000.00 |  |  |  |  |  | NADMO | Traditional Leaders |  |
| Build the Capacity of NADMO Staff, DVGs and Organized Groups on Disaster Management | District wide |  |  |  |  |  |  | 4,500.00 |  |  |  |  | NADMO | GNFS/GES |  |
| Organise District Disaster Management Committee Meetings | District wide |  |  |  |  |  | 7,500.00 | 3,000.00 |  |  |  |  | NADMO | SDA |  |
| Observe International Day for Disaster Risk Reduction (IDDRR) | District wide |  |  |  |  |  | 12,000.00 |  |  |  |  |  | NADMO | NGOs |  |
| Provide Relief Support to Disaster Victims and reconstruction | District wide |  |  |  |  |  |  | 93,000 |  |  |  |  | NADMO | District Assembly |  |
| Risk and safety inspection at public spaces/Indusrial and fuel pump visitation | District wide |  |  |  |  |  | 5,000.00 | 5,000.00 |  |  |  |  | NADMO | SDA |  |
| Revision of Structure Plan | District wide |  |  |  |  |  |  | 37,500.00 | 37,500.00 |  |  |  | PPD | SDA |  |
| Prepare new local schemes and revision of existing Planning Schemes at Dwomo, Komfoeku, Supomu Dunkwa, Atwerboanda, Assorko, Essamang, Beposo, Abuesi/Aboadze | Selected communities |  |  |  |  |  |  | 5,000.00 | 175,000.00 |  |  |  | PPD | SDA |  |
| Organization of Land Use Conference at Shama | Shama |  |  |  |  |  |  |  | 15,000.00 |  |  |  | PPD | SDA |  |
| Sensitization of Chiefs & families on the need to sell lands in conformity with the planning schemes district wide | District wide |  |  |  |  |  |  |  | 50,000.00 |  |  |  | PPD | ISD, NCCE |  |
| Acquisition of land & facilitation of relocation of Inchaban market to new market site | Inchaban |  |  |  |  |  |  |  | 50,000.00 |  |  |  | PPD | Central Admi |  |
| Organization of monthly technical sub-committee meeting and Spatial Planning Committee meetings. | District wide |  |  |  |  |  |  |  | 50,000.00 |  |  |  | PPD | SDA |  |
| Extension of street naming and Property Addressing Exercise to these communities; Ituma, Inchaban, Dwomo, Assorko, Essamang, Yabiw, Supomu Dunkwaw, Beposo, Anto | Selected communities |  |  |  |  |  |  |  | 30,000.00 |  |  |  | PPD | Central Administration |  |
| Mapping, documentation and protection of Assembly lands. | district wide |  |  |  |  |  |  |  | 30,000.00 |  |  |  | PPD | SDA/lands |  |
| Organize Public education on permitting in the various communities. | district wide |  |  |  |  |  |  |  | 30,000.00 |  |  |  | PPD | ISD |  |
| Preparation of district Geospatial data. | district wide |  |  |  |  |  | 3,000,000 |  |  |  |  |  | PPD | SDA |  |
| Ensure the production of basemaps, orthophotos and topographical maps district wide | district wide |  |  |  |  |  |  | 5,000.00 |  |  |  |  | PPD | SDA. |  |
| Training on the preparation of local plans using GIS and other geospatial tools at shama | shama |  |  |  |  |  |  |  | 10,000.00 |  |  |  | PPD | LUSPA |  |
| Procurement of 3 Energy efficient laptop computers, two (1)A3 colour printer, 2 HP laser jet (P1102), 2 A3 colour scanners, 3 Desktop computers, 1 drone | Physical Planning Dept |  |  |  |  |  |  |  | 37,500.00 |  |  |  | Physical Planning Dept | Central Administration |  |
|  |  | Sub-Total |  |  |  |  | 3,742,500.00 | 1,080,000.00 | 1,126,651 | 48,000 |  |  |  |  |  |
|  |  | Total |  |  |  |  | 5,927,151.00 |  |  |  |  |  |  |  |  |
| GOVERNANCE AND INSTITUTIONAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Project | Location | Time Frame |  |  |  |  | Cost |  |  |  | Project Status |  | Implementing Institution/Department |  |  |
|  |  | Q1 | Q2 | Q3 | Q4 |  | GoG | DACF | ICF | Other | New | Ongoing | Lead | Collaborating |  |
| Intensify education on rights and responsibilities of electorates | District wide |  |  |  |  |  | 2,687.50 |  |  | 2,687.50 |  |  | NCCE | NGOs |  |
| Intensify public awareness on the need for equal gender at the Assembly for inclusive citizen participation in governance | District wide |  |  |  |  |  | 2,437.50 |  |  | 2,687.50 |  |  | NCCE | NGOs |  |
| Construct/rehabilitate Area council offices | Shama Junction |  |  |  |  |  |  |  | 300,000 | 40,000.00 |  |  | SDA | works |  |
| Provide logistics for the Area councils- - computers and accessories | District wide |  |  |  |  |  | 107,500.00 |  |  |  |  |  | SDA | NGOs |  |
| Reconstitution of the Area Councils | District wide |  |  |  |  |  |  |  | 1,562.00 |  |  |  | SDA | NGOs |  |
| Train Area Council members on Participatory Planning, Budgeting, M&E and other relevant araes | District wide |  |  |  |  |  |  |  | 200,000 |  |  |  | SDA | NGOs |  |
| Allocate District officers to manage the Area Councils | District wide |  |  |  |  |  |  |  | 1,250.00 |  |  |  | HR | SDA |  |
| Organize , Meet the Press on Assembly programs and Achievements. | District wide |  |  |  |  |  |  |  | 3,125.00 |  |  |  | ISD | Planning Unit |  |
| Organize DCEs Community Engagements | District wide |  |  |  |  |  | 11,875.00 |  | 11,875.00 | 6,342.87 |  |  | SDA | ISD |  |
| Organize stakeholders’ forum on planning process and Budgeting | District wide |  |  |  |  |  |  |  | 12,250.00 |  |  |  | SDA |  |  |
| Conduct Monthly Radio Sensitization on Assembly program Implementation andAchievements | District wide |  |  |  |  |  |  |  | 1,250.00 |  |  |  | Planning Unit | ISD |  |
| Organize quarterly DCEs engagement with the Public on Radio | District wide |  |  |  |  |  | 54,125 |  | 6,250.00 |  |  |  | DCE | Planning Unit |  |
| Organize quarterly DPCU Meetings. | District wide |  |  |  |  |  |  | 95,000.00 | 9,200.00 |  |  |  | Plan. Unit | SDA |  |
| Prepare Annual Action Plan | District wide |  |  |  |  |  |  | 100,000.00 |  |  |  |  | Plan. Unit | SDA |  |
| Prepare Annual Budgets | District wide |  |  |  |  |  |  | 100,000.00 |  |  |  |  | Budget Unit | SDA |  |
| Conduct Review of Annual Action Plans | District wide |  |  |  |  |  |  | 50,000.00 | 9,200.00 |  |  |  | Plan. Unit | SDA |  |
| Conduct Review of Annual Budgets | District wide |  |  |  |  |  |  | 50,000.00 | 9,200.00 |  |  |  | Budget Unit | SDA |  |
| Organize Town Hall Meetings | District wide |  |  |  |  |  | 12,250.00 | 200,000.00 |  | 9,750.00 |  |  | Plan. Unit | SDA |  |
| Project monitoring | District wide |  |  |  |  |  |  | 150,000.00 |  |  |  |  | Plan. Unit | SDA |  |
| Procurement of Vehicle for monitoring | shama |  |  |  |  |  |  |  | 800,000.00 |  |  |  | SDA | procurement |  |
| Mount Accountability billboards at the various Area Councils | District wide |  |  |  |  |  |  |  | 35,250.00 |  |  |  | Plan. Unit | NGOs/ |  |
| Conduct audit committee meeting | District wide |  |  |  |  |  |  | 85,000 |  |  |  |  | IAU | SDA |  |
| Encourage and Support Communities to undertake self-help projects | District wide |  |  |  |  |  |  |  | 51,250.00 |  |  |  | SDA | Private Sector |  |
| Construction of Staff Accommodation (DCD Bungalow) | Shama |  |  |  |  |  |  | 62,500.00 | 1,500,000 |  |  |  | SDA | Works Dept. |  |
| Strengthening Client Service Department at the Assembly | Shama |  |  |  |  |  |  |  | 10,250.00 |  |  |  | SDA | HR |  |
| Educate and sensitize citizens on their rights and responsibilities. | District wide |  |  |  |  |  |  |  | 1,250.00 |  |  |  | NCCE | ISD |  |
| Organize Capacity Training capacity building for CBO, community members and the Sub- structures to improve service delivery and data Collection of the District assembly | District wide |  |  |  |  |  | 1,250.00 |  | 1,250.00 |  |  |  | Planning Unit | NGOs |  |
| Procure and install VPN to connect to other offices outside of the Assembly | Area Council |  |  |  |  |  | 1,250.00 |  | 4,963.00 |  |  |  | MIS | SDA |  |
| Procure office equipment for offices | SDA |  |  |  |  |  | 6,250.00 | 2,625.00 | 300,000 |  |  |  | Procurement | SDA |  |
| Maintenance of furniture and fixtures | District wide |  |  |  |  |  |  | 184,875 |  |  |  |  | Works Dep’t | SDA |  |
| Ensure effective implementation of the National Anti- Corruption Action Plan (NACAP) | District wide |  |  |  |  |  | 1,250.00 |  | 100,000 |  |  |  | Focal Person | NCCE |  |
| Mounting of Suggestion box at the Assembly | SDA |  |  |  |  |  |  |  | 250.00 |  |  |  | Focal Person | NGO |  |
| Engage CSOs and other stakeholders in the District in the Fight against Corruption. | District wide |  |  |  |  |  |  |  | 6,250.00 |  |  |  | Focal Person | NCCE/NGOs |  |
| Organize Public education and awareness programs on the evils of corruption and the ethos of anti-corruption in the Society. | District wide |  |  |  |  |  |  |  | 1,250.00 |  |  |  | Focal Person | NCCE |  |
| Organize monthly Radio education and sensitization on Corruption related issues. | District wide |  |  |  |  |  |  |  | 3,750.00 |  |  |  | Focal Person | NCCE |  |
| Encourage the formation of community “watch- leads” | District wide |  |  |  |  |  |  |  | 6,250.00 |  |  |  | SDA | GPS |  |
| Provide office for city guards at Beposo Market | Beposo |  |  |  |  |  |  |  | 15,500.00 |  |  |  | SDA | GPS |  |
| Provide support to the District Police Service | Shama |  |  |  |  |  |  |  | 18,500.00 |  |  |  | SDA | GPS/NGOs |  |
| Strengthening the Shama Traditional Council to promote development | Shama |  |  |  |  |  |  |  | 5,000.00 |  |  |  | SDA | Private Sector |  |
| Enhance private sector participation in culture promotion | District wide |  |  |  |  |  | 3,125.00 |  |  |  |  |  | SDA | Private Sector |  |
| Position of the District as a preferred destination for business, education and tourism | District wide |  |  |  |  |  | 1,250.00 |  |  |  |  |  | SDA | Private Sector |  |
| Organise home coming summit for citizens in the diaspora | District wide |  |  |  |  |  | 3,125.00 |  |  |  |  |  | SDA | Private |  |
| Implement Open Governance Partnership (OGP) activities | District wide |  |  |  |  |  |  |  |  | 50,000.00 |  |  | Plan. Unit | OGP Secretariat |  |
|  |  | Sub- Total |  |  |  |  | 375,250.00 | 250,000.00 | 314,625.00 | 106,092.87 |  |  |  |  |  |
|  |  | Total |  |  |  |  | 1,045,967.87 |  |  |  |  |  |  |  |  |