SHAMA DISTRICT ASSEMBLY

+233 209 3236

P. O Box 37

Shamadistrict.gov.gh

2024 ANNUAL PROGRESS REPORT ON THE IMPLEMENTATION OF THE MEDIUM-TERM DEVELOPMENT PLAN 2022-2025

JANUARY - DECEMBER

# TABLE OF CONTENTS

TABLE OF CONTENTS	2

LIST OF ACRONYMS	4

EXECUTIVE SUMMARY	8

Implementation of the 2024 Annual Action Plan (AAP)	8

Challenges Encountered	9

Way Forward and Recommendations	9

Conclusion	10

CHAPTER ONE	11

GENERAL INTRODUCTION	11

1	INTRODUCTION	11

1.1	Purpose of M&E for the Year, 2024	11

1.2	Processes Involved in M&E	12

1.3	Summary of Achievements of the Implementation of the DMTDP (2022-2025)	14

1.4	Analysis of the proportion of the Annual Action Plan implemented.	14

1.5	Implication of Results on the District Development Goals and Objectives	16

1.6	Overall Proportion of the DMTDP (2022 -2025) Implemented	17

1.7	Implication of Results on District Development Goals and Objectives	18

1.7.1	Analysis of Graph and Implication of Results	20

1.8	Challenges Encountered in Implementing the DMTDP 2022-2025	21

CHAPTER TWO (2)	22

MONITORING AND EVALUATION ACTIVITIES REPORT	22

2	Introduction	22

2.1	Programme/Project Status for the year	22

2.1.1	Physical Projects	22

2.2	Repair And Maintenance of Existing Infrastructure	23

2.2.1	Programmes	23

2.3	Update on Funding Sources	24

2.3.1	Update on Revenue Sources	24

2.4	Analysis of Funding Sources Compared between 2022 to 2024	25

2.5	Update on Expenditure	26

2.6	Analysis of Capex Budget Allocation and Implementation for Active Projects	32

2.7	Update on Indicators & Targets	33

2.8	Implication of the Indicator Results on District Goals and Objectives	34

2.8.1	Economic Development	34

2.8.2	Social Dimension	35

2.8.3	Environment, Infrastructure and Human Settlements	36

2.8.3.1	Roads	36

2.8.3.2	Electricity Coverage	37

2.8.4	Governance, Corruption, and Public Accountability	37

2.8.5	Emergency Planning and Response (Including Covid-19 Recovery Plan)	37

2.8.6	Implementation, Coordination, Monitoring and Evaluation	38

2.9	Underlying Factors of Success or Failure in the Performance of the Indicators	38

2.9.1	Success Factors	39

2.9.2	Failure Factors	39

2.10	Update on Critical Development and Poverty Issues	40

2.10.1	School Feeding Programme (SFP)	42

2.10.2	Livelihood Empowerment Against Poverty (LEAP) programme	43

2.10.3	National Health Insurance Scheme	43

2.10.4	Planting for Food and Jobs Programme	43

2.10.5	Capitation Grant	44

2.10.6	Common Fund for Persons with Disability	44

2.10.7	Planting for Export and Rural Development (PERD)	44

2.11	Evaluations Conducted, their Findings and Recommendations	52

2.12	Participatory M&E Undertaken and Their Results	54

CHAPTER THREE	57

THE WAY FORWARD	57

3	Introduction	57

3.1	Key Issues Addressed and yet to be Addressed.	57

3.1.1	Key Issues Addressed	57

3.1.2 Issues yet to be addressed.	57

3.2	Recommendations	58

3.3	Conclusion	59

LIST OF TABLES

Table 1: Details of the Annual Action Plan Implemented under the Agenda for Jobs Policy Framework	15

Table 2: Proportion of The DMTDP Implemented	17

Table 3: Update on Revenue Sources	24

Table 4: Disbursement (Expenditure) between 2023 Compared with 2024	27

Table 5: Shama District Assembly CAPEX Analysis	29

Table 6: (ANNEX 6B) MMDAs Capex Budget Performance Analysis	29

Table 7: CAPEX budget allocation and implementation for ongoing projects	30

Table 8: Update on Critical Development and Poverty Issues	41

Table 9: Staff Strength for Shama District Assembly	45

Table 10: Staff Strengths of MMDAs (Trainings and Workshops)	48

Table 11: Staff Strengths of MMDAs (Logistics)	51

Table 12: Evaluations Conducted	53

Table 13: PM&E Conducted	55

LIST OF FIGURES

Figure 1: Status of Project implementation from 2021 to 2024	19

Figure 2: Funding Sources compared between 2022 and 2024.	25

Figure 3: Analysis of Disbursement (Expenditure) for 2021, 2022, 2023 and 2024	28

APPENDIX

Appendix 1: Projects Status - Updated Project Register As At December, 2024	60

Appendix 2: Repair and Maintenance of Existing Infrastructure	65

Appendix 3: Programme register	66

Appendix 4: Performance Indicators (Core And District Specific) At The District Level	125

# LIST OF ACRONYMS

AAPs			- 	Annual Action Plans

AMSEC 		- 	Agricultural Mechanization Service Centers

CDD			- 	Center for Democratic Development

CHPS 			- 	Community Health Planning Service

CSLP 			- 	Coastal Sustainable Landscape Project

CSO 			- 	Civil Society Organization

CSR 			- 	Corporate Social Responsibility

CWSA 		- 	Community Water and Sanitation Agency

DACF 			- 	District Assemblies Common Fund

DACF-RFG		-            District Assembly Common Fund – Responsive Factor Grant

DADU 		- 	District Agricultural Development Unit

DBA 			- 	District Budget Analyst

DCAT 			- 	District Centre of Agriculture, Commerce and

DCC 			- 	District Communication Committee

DDF 			-	District Development Facility

DISEC 		- 	District Security Committee

DMTDP 		-	District Medium Term Development Plan

DPCU 			- 	District Planning Coordinating Unit

DPO 			- 	District Planning Officer

EHD 			- 	Environmental Health Department

FBOs 			-	Faith Based Organizations

FGD 			-	Focus Group Discussion

FoN 			- 	Friends of the Nation

GES 			- 	Ghana Education Service

GHS 			- 	Ghana Health Service

GoG 			- 	Government of Ghana

GSGDA 		- 	Ghana Shared Development Growth Agenda

GSS 			-	Ghana Statistical Service

GTZ 			-	German Technical Corporation

HIV 			- 	Human Immune virus

HoDs 			- 	Heads of Departments

ICT 			- 	Information and Communication Technologies

IGF 			- 	Internally Generated Fund

IVRDP 		- 	Inland Valley Rice Development Project

LEAP 			- 	Livelihood Empowerment Against Poverty

LI 			- 	Legislative Instrument

M&E 			- 	Monitoring and Evaluation

MLGRD 		- 	Ministry of Local Government & Rural Development

MMDAs 		- 	Metropolitan, Municipal, District Assemblies

MoFA 			-	Ministry of Food and Agriculture

MOFAD 		- 	Ministry of Fisheries & Aqua-culture Development

MTDP 		- 	Medium Term Development Plan

NADMO 		-	National Disaster Management Organization

NBSSI 		- 	National Board for Small Scale Industries

NDPC 			- 	National Development Planning Commission

NGO 			- 	Non-Governmental Agency

NMTDPF 		-	National Medium Term Development Policy

OBK 			- 	ObinyimOkyina

PFJ 			- 	Planting for Food and Jobs

PHC 			- 	Population and Housing Census

PJI 			- 	Planting for Jobs and Investment

PLHIV 		– 	People Living with HIV

PM&E 		- 	Planning, Monitoring and Evaluation

PPP 			– 	Public – Private Partnership

PWDs 			- 	Persons with Disabilities

SAEMA 		- 	Shama Ahanta East Metropolitan Assembly

SDA 			- 	Shama District Assembly

SDGs 			- 	Sustainable Development Goals

STMA 		- 	Sekondi Takoradi Metropolitan Assembly

SW&CD 		- 	Social Welfare and Community Development

WRCC 		- 	Western Regional Coordinating Council

YEP 			– 	Youth Employment Programme

# EXECUTIVE SUMMARY

The Shama District Assembly, established in 2007, operates under the National Development Planning Commission Systems Act, 1994 (ACT 480), Regulation 8 Section 3 and Regulation 19 of the NDPC Legislative Instrument (L.I. 2232), and the Local Governance Act, 2016 (Act 936). These legal provisions mandate the Assembly to plan, implement, monitor, and evaluate development policies, programs, and projects within the district.

Through the District Planning Coordinating Unit (DPCU), the Assembly conducted Monitoring and Evaluation (M&E) activities in collaboration with beneficiary/host departments, NGOs, traditional authorities, beneficiary communities, the Internal Audit Unit, Social Accountability Committee members, opinion leaders, Assembly members, and execution agencies such as contractors. These efforts facilitated tracking project progress, identifying challenges, and extracting lessons to improve future development initiatives.

### Implementation of the 2024 Annual Action Plan (AAP)

The 2024 Annual Action Plan (AAP) outlined 320 planned projects and programs, with an estimated budget of GH¢16,590,000.00. By the end of the year, the district achieved a 94.68% implementation rate, successfully executing 303 activities. This represents an improvement from the 92.98% completion rate in 2023. Additionally, 73.03% of the Medium-Term Development Plan (MTDP) 2022–2025 had been implemented, at the end of 2024.

The district excelled in all six development dimensions, particularly in:

- Economic Development: 51 out of 55 planned activities were completed, contributing to job creation and business growth through the support of SMEs, financial linkages, and local trade exhibitions.

- Social Development: 127 out of 133 activities were executed, improving education, health services, gender equality, and social protection programs.

- Infrastructure and Human Settlements: 47 out of 50 activities were completed, including road rehabilitation, drainage systems, and climate action initiatives.

- Governance, Corruption, and Public Accountability: 58 out of 60 planned initiatives were executed, improving stakeholder engagement, transparency, and accountability.

- Emergency Planning and Response: 8 out of 10 activities were carried out, reducing disaster impacts and improving community resilience.

By the end of 2024, GH¢18,664,986.68 was mobilized, exceeding the revenue target by 12.5%. This was due to increased IGF collection efforts, support from development partners, and improved property rate collection after regaining responsibility from the Ghana Revenue Authority (GRA). Projected expenditure for 2024 was GH¢9,943,500.00, but actual spending totaled GH¢16,507,756.07 reflecting higher capital investment in infrastructure projects, health services, education, and governance programs.

Key Achievements in 2024

- Education: Net enrollment reached 69.4%, and JHS pass rates improved from 55% in 2023 to 64.6% in 2024 due to increased logistical support and monitoring in schools.

- Health: The district recorded zero maternal mortality and a reduction in malaria-related fatalities, although Outpatient Department (OPD) attendance was low due to reliance on pharmacies and herbal remedies.

- Road Infrastructure: 8.4km of feeder roads were reshaped to improve accessibility, particularly Komfueku to Shama Junction and Yabiw to Yabiw Junction. Much of this intervention came through the District Road Improvement Programme

- Electricity Coverage: Achieved 100% electrification for all communities connected to the national grid.

- Local Economy and Agriculture: Yield studies were conducted on rice, maize, cassava, and plantain, and farmers were trained in modern farming techniques to increase production.

### Challenges Encountered

- Delayed release of DACF funds, affecting project execution timelines.

- Inadequate logistics and vehicles for revenue mobilization and project monitoring.

- Limited participation in gender and social protection programs, particularly among women.

- Poor road conditions, especially in farming communities, lead to higher transportation costs for agricultural produce.

### Way Forward and Recommendations

- Strengthening revenue mobilization by increasing training for revenue collectors and introducing incentive schemes.

- Enhance monitoring and evaluation to improve efficiency and accountability in project execution.

- Increase investments in road infrastructure to boost economic activities, particularly in agriculture and trade.

- Expand community engagement programs to encourage active participation in governance and local development.

### Conclusion

Despite economic challenges, the Shama District Assembly demonstrated resilience and efficiency in achieving significant milestones in infrastructure, economic growth, social development, and governance. Moving forward, the Assembly will prioritize sustainable resource mobilization, strengthen stakeholder collaboration, and enhance capacity-building initiatives to sustain progress and improve service delivery.

This report follows the 25 Core Indicators recommended by the NDPC and district-specific performance metrics under the 2022–2025 DMTDP, providing a detailed analysis of achievements, challenges, and recommendations to guide informed decision-making.

The report is structured into three chapters:

- Chapter One presents the general introduction.

- Chapter Two details the Monitoring and Evaluation (M&E) activities conducted in 2024.

- Chapter Three outlines recommendations and the way forward.

Performance analysis is visually represented through charts and graphs for easy interpretation and reference.

## CHAPTER ONE

## GENERAL INTRODUCTION

## INTRODUCTION

The Shama District Assembly was carved out of the former Shama Ahanta East Metropolitan Assembly (SAEMA) and established in December 2007 by Legislative Instrument (LI 1882) with Shama town as its administrative Capital. Officially, it was inaugurated in March 2008. The Assembly is required by Section 2 sub-section (1) f and g of the National Development Planning Commission Systems Act, 1994 (ACT 480); Regulation 8 section 3 and Regulation 19 of the NDPC Legislative Instrument (L.I. 2232) and section 12 (3a, b, e; 4e), 46 (1b) and 83 (g & h) of the Local Governance Act, 2016 (Act,936) to plan, implement and monitor and evaluate the development of policies, programmes and projects being executed in the district.

The provisions mandate the Assembly to regularly inform Central, Regional, and Local Level Authorities, along with all concerned stakeholders, about the advancements in policies, programs, and projects within the district. To fulfill this responsibility, the Assembly compiles and submits reports detailing the progress and impact of these initiatives on a quarterly and annual basis to the National Development Planning Commission (NDPC), facilitated through the Regional Coordinating Council (RCC). Simultaneously, the contents of the report are disseminated to other pertinent stakeholders within the district.

This Annual Progress Report comprehensively outlines the activities carried out by the Assembly from January to December 2024. These activities have been duly reported by the various departments of the Assembly and are presented in three sections with headings, subheadings, and concluded with key findings, recommendations, and conclusions.

## Purpose of M&E for the Year, 2024

Through the District Planning Coordinating Unit, the Shama District Assembly carried out M&E for the period under discussion in collaboration with beneficiary/host departments, NGOs, traditional authorities, beneficiary communities, the Internal Audit Unit, members of the Social Accountability Committee, and execution agencies such as contractors.

The main reasons for the M&E exercise are enumerated below:

- To ascertain the achievements being made (progress) regarding meeting the Development Goals, Objectives and Targets as outlined in the District Medium Term Development Plan (DMTDP 2022-2025).

- To track, assess and compare actual performance of programmes and projects against our set targets effectively and efficiently.

- To generate reliable and accurate information/ data to help make sound policies and improved decisions for the realization of the district goals and objectives.

- To review actions on implementation of plans and budgets and assess the impact of the various interventions as stated in the DMTDP (2022-2025).

- To establish the level or extent of citizens’ satisfaction with services delivery in the district.

- To provide opportunities for stakeholders to familiarize themselves with the various projects and programs being implemented in the district and ask questions.

- To provide feedback to the Stakeholders in the District.

- To increase stakeholders’ commitment in the participation of programme implementation to achieve holistic success of programmes.

- To build and strengthen stakeholders’ relationship for enhanced program implementation.

- To provide information for better transparency and accountability.

The outcomes and findings of the M&E exercise generated through reports are disseminated to various stakeholders and validated with emphasis on the achievements, challenges, and recommendations.

## Processes Involved in M&E

This annual progress report compiles information on major interventions carried out by the district's departments, agencies, and the private sector. Below are the primary procedures followed in the creation of this report and project monitoring:

- Project Site Inspections and Meetings: To gather reliable information for the APR preparation, a team from the Core DPCU conducted site meetings and inspections at all project locations. These inspections, along with the harmonized reports from previous meetings, were incorporated into this APR.

- Monitoring and Evaluation (M&E) Exercises: The DPCU conducts quarterly monitoring visits to track and assess the progress of ongoing projects and evaluate the impact of completed ones. Before these M&E activities, the DPCU Secretary (DPO) arranges a meeting to explain the purpose of the exercise. Team members are then divided into pairs, with each pair assigned specific projects to evaluate.

- Use of Checklists: Each team follows the M&E guidelines and checklist provided by the DPCU, ensuring consistency in report presentations and easy harmonization.

- Compilation of M&E Reports and Presentations: Each team, led by a leader and secretary, prepares comprehensive reports which are presented to the DPCU during meetings. These reports are harmonized and incorporated into the APR. The M&E exercises are participatory, involving DPCU members, Development Planning and Works Sub-Committees, Assembly members from host communities, project beneficiaries, lead departments, user agencies, and local chiefs.

- DPCU Meetings: The DPCU organizes meetings where department heads present their activities. Copies of these presentations are submitted to the DPCU Secretary for harmonization. The format for the APR was discussed in an earlier meeting, with feedback from the National Development Planning Commission shared with all members to ensure consistency.

- Official Requests: The DPCU Secretariat formally requests each department to submit details of their activities, including all programs, projects, and updates on national policies or interventions. These submissions are captured in annual reports and shared with the DPCU Secretary. The content of these reports is reviewed, harmonized, and incorporated into the APR.

- Data Collection: The DPCU collects data from both primary and secondary sources to analyze and assess the impact of programs and projects on the recipient communities. Secondary data includes reports from departments, NGOs, development partners, and MDAs, as well as minutes from management meetings and subcommittees. Primary data is gathered through structured interviews and open-ended discussions with officers overseeing key interventions like NHIS, 1D1F, DCAT, and others.

- Data Validation Exercise: A data validation session took place on Wednesday, January 23rd, 2024, at the Riverside Conference Hall, where the report was presented for scrutiny and validation. The report was reviewed and endorsed by various stakeholders, including department heads, Assembly members, chiefs, community leaders, and association representatives. The validation focused on the progress of projects, revenue generation, critical poverty reduction programs, core district indicators, and evaluation results. Stakeholders were given the opportunity to ask questions for clarification.

- Report Review by the DCD and DCE: After the DPCU Secretariat completed the report, copies were reviewed by the DCE and DCD to ensure the content accurately reflected the situation on the ground. Once finalized, the report was submitted to the WRCC and the NDPC.

#### Sample Photos of Monitoring Activities for the period

## Summary of Achievements of the Implementation of the DMTDP (2022-2025)

This section presents the analysis of the proportion of the Annual Action Plan and the DMTDP (2022-2025) implemented at the end of 2024. It discussed the key results achieved and the implication on the attainment of the district goals and objectives. Below are the details.

## Analysis of the proportion of the Annual Action Plan implemented.

The successful implementation of 303 out of 320 programmes and activities outlined in the Shama District Assembly's 2024 Action Plan represents a significant achievement, reflecting a 94.68% success rate compared to 92.98% in 2023. This improvement highlights notable progress in local development and demonstrates a strong commitment to efficiency in executing planned initiatives. Despite prevailing economic challenges, including inflation and its impact on the standard of living, the Assembly’s success can be attributed to effective community engagement, stakeholder collaboration, and transparency in reporting the status of initiatives. Additionally, proactive measures in addressing community needs have contributed to fostering a sense of ownership and participation, ultimately promoting sustainable growth across the district.

Table 1: Details of the Annual Action Plan Implemented under the Agenda for Jobs Policy Framework

| S/N | DEVELOPMENT DIMENSION | 2022 |  | 2023 |  | 2024 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | PLAN | EXECUTED | PLAN | EXECUTED | PLAN | EXECUTED |
| 1 | Economic Development | 51 | 46 | 52 | 49 | 55 | 51 |
| 2 | Social Development | 117 | 111 | 129 | 123 | 133 | 127 |
| 3 | Environment, Infrastructure and Human Settlement | 44 | 42 | 41 | 34 | 50 | 47 |
| 4 | Governance, Corruption and Public Accountability | 50 | 45 | 43 | 39 | 60 | 58 |
| 5 | Emergency Planning and Response (Including Covid-19 Recovery Plan) | 10 | 9 | 8 | 8 | 10 | 8 |
| 6 | Implementation, Coordination, Monitoring and Evaluation | 12 | 11 | 12 | 12 | 12 | 12 |
| TOTAL |  | 284 | 264 | 285 | 265 | 320 | 303 |

## Implication of Results on the District Development Goals and Objectives

With reference to the table above, the district excelled across all six development dimensions by allocating resources and implementing a range of interventions for overall progress. Specifically, in Economic Development, 51 out of 55 activities were carried out, and in Social Development, 127 out of 133 activities were implemented according to the table. In the categories of Environment, Infrastructure, and Human Settlement, 47 out of 50 activities were successfully implemented. Concerning Governance, Corruption, and Public Accountability, 58 out of 60 activities were effectively executed. Emergency Planning and Response witnessed the completion of all 8 activities, and Implementation, Coordination, Monitoring, and Evaluation saw the successful implementation of all 12 activities. In total, 303 out of 320 activities were implemented, leaving 17 activities pending.

The Assembly placed significant emphasis on Social Development, demonstrating greater commitment to this sector than to others. This strategic focus played a crucial role in strengthening the healthcare management system, improving sanitation standards, and advancing gender equality initiatives throughout the district.

Similarly, Economic Development was prioritized, with targeted efforts to support small and medium-sized enterprises, leading to notable improvements in the business environment. The establishment of the District Local Economic Development Platform served as a catalyst for business promotion and networking. Additionally, public sensitization campaigns, conducted via radio broadcasts and community forums, highlighted the importance of tax compliance. These initiatives contributed to the Assembly's 2024 objective of fostering a strong and resilient economy.

Also, in the year under review, the Assembly placed greater emphasis on Environment, Infrastructure, and Human Settlement development compared to the previous year, 2023. This strategic focus resulted in significant improvements in spatial planning, as evidenced by a rise in the number of developers seeking approval for development permits. Additionally, governance, corruption control, and public accountability saw substantial advancements, promoting increased transparency, inclusivity, and accountability within the district.

## Overall Proportion of the DMTDP (2022 -2025) Implemented

This section examines the overall progress of the District Medium Term Development Plan (DMTDP) from its inception in 2022 through its third year of implementation (2022–2025). Given the importance of assessing implementation trends, the Assembly has undertaken this review to identify challenges, lessons learned, and areas for improvement in the remaining two years of the plan.

As the year under review marks the third year of the DMTDP (2022–2025), the Assembly conducted an evaluation of the implementation of planned activities. The assessment revealed that, as of December 2024, the Assembly successfully implemented 73.03% of the activities outlined in the plan, a significant improvement from the 49.36% recorded in 2023. This notable achievement is largely attributed to increased revenue from various sources, which provided the financial capacity to undertake more projects in 2024.

A summary of the overall implementation progress of the DMTDP (2022–2025) is presented in Table 2 below.

Table 2: Proportion of The DMTDP Implemented

| INDICATORS | 2021 | 2022 |  | 2023 |  | 2024 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | BASELINE | TARGET | ACTUAL | TARGET | ACTUAL | TARGET | ACTUAL |
| Proportion of the annual action plans implemented by the end of the year | 89.2% | 100% | 92.96% | 100% | 92.98% | 100% | 94.68% |
| - Percentage completed | 85.7% | 100% | 62.1% | 100% | 69.82% | 100% | 78.87% |
| - Percentage of ongoing interventions | 13.1% | 0 | 26.9% | 0 | 20.35% | 0 | 16.83% |
| - Percentage of interventions abandoned | 0.0% | 0 | 3% | 0 | 2.81% | 0 | 0% |
| - Percentage of interventions yet to start | 1.2% | 0 | 8% | 0 | 7.02 | 0 | 4.3% |
| Proportion of overall MTDP Implemented by the end of the year. | 90.02% | 25% | 24.20% | 50% | 49.36% | 75% | 73.03% |

Source DPCU, 2024

## Implication of Results on District Development Goals and Objectives

As illustrated in Tables 1 and 2, the Assembly undertook various projects and activities in 2024 to achieve its development goals and objectives. Out of the 320 activities planned for the year, 303 were successfully executed. Among these, 239 projects (78.87%) were fully completed, 51 (16.83%) were still in progress, and 13 (4.3%) had yet to commence. All development parameters outlined in the Annual Action Plan (AAP) and the District Medium Term Development Plan (DMTDP) positively contributed to the implementation of these projects.

To uphold accountability, transparency, and value for money, the Assembly adopted a participatory approach in both project execution and monitoring. As a result of the successful implementation of these initiatives in 2024, several key achievements were recorded, including the following:

- The disbursement of the District Assemblies Common Fund (DACF) to Persons with Disabilities (PWDs) have significantly contributed to poverty reduction among PWDs, the poor, and other vulnerable groups in the district, thereby promoting their economic empowerment.

- Strengthened collaboration with Development Partners and Non-Governmental Organizations (NGOs), particularly GIZ and Friends of the Nation, to support the district in the effective implementation of various development activities.

- Improved execution of projects, resulting in enhanced service delivery in key sectors such as education, healthcare, and water supply.

- Increased citizen participation in the Assembly’s activities. Despite economic challenges affecting operations, the Assembly successfully organized two (2) Town Hall Meetings to communicate achievements, discuss challenges, and share best practices with stakeholders.

- Enhanced efficiency within the Agriculture Department has led to increased food production, particularly in maize, cassava, and rice cultivation, as well as improved livestock farming, including goat, pig, and poultry production.

- Expanded support for Persons with Disabilities (PWDs) through the provision of materials and financial assistance, enabling them to engage in productive economic activities, access education, and cover medical expenses.

- Improved access to potable water and a reduction in waterborne diseases, resulting from the provision of boreholes across rural communities in the district.

- Increased access to potable water in urban areas, as expanded Ghana Water Supply facilities have improved water availability for residents.

- Strengthened support for vulnerable groups, with PWDs who received financial assistance successfully investing in businesses, generating profits, and improving their livelihoods to support their families.

Figure 1: Status of Project implementation from 2021 to 2024

Source DPCU, 2024

## Analysis of Graph and Implication of Results

The data above clearly indicates that the Assembly's performance in 2024 was notably more effective in executing initiatives and plans compared to previous years. The positive outcomes can be attributed to several key factors: enhanced supervision, monitoring, and evaluation by the DPCU, greater citizen involvement through radio programs focused on taxation, stronger support from both the public and stakeholders, improved donor relationships, and continuous oversight by auditors, ensuring that funds for ongoing projects were disbursed on schedule. In response to the challenge of insufficient resources, the Assembly also opted to award projects to contractors who could pre-finance and complete them within the set timeframes.

However, despite these achievements, the Assembly fell short of fully implementing the plans. The following limitations were identified as the primary reasons for this gap:

- A lack of leadership commitment to allocating resources effectively for the execution of the plan (AAP/DMTDP).

- Budgeting practices often deviated from established procedures, with many new activities being submitted for inclusion by departments. This resulted in the preparation of the budget based on new submissions, which did not align with the original plan (AAP).

- Limited commitment from the community towards the programs, coupled with low participation from women in gender and social protection programs.

- The adverse economic conditions, which significantly hindered the smooth execution of projects. Efforts to mobilize revenue were hampered by the President's preventative measures, and many institutions took advantage of the situation to delay payments or request discounts on fees.

- Finally, the delayed release of funds further impacted on the implementation of the program.

This analysis highlights the contrasting factors that contributed to both the successes and the challenges faced by the Assembly in 2024.

## Challenges Encountered in Implementing the DMTDP 2022-2025

The implementation of the 2024 Annual Action Plan and the M&E were not devoid of challenges. The Assembly was faced with the challenge of inadequate funding for the implementation of activities in the Plan. Funds earmarked for the period were not realized in full due to the delay in releases and deductions at source on the implementation of the Central Government transfers, among others. This hindered the ability of the Assembly to implement all planned projects.

- The pollution of the Pra river by illegal miners affected fish productivity. Fishers go as far as cote d’ivoire before getting a good catch. Though galamsey is not practiced in Shama, the polluted Pra joins the see at shama, Anlo beach to be precise.

- Poor road network and condition also hindered the smooth implementation of the Plan in some communities and most often hindered monitoring activities.

- Logistical challenges faced by some Departments of the Assembly also made it difficult for them to reach some communities.

- Collecting updates on the indicator levels from some of the departments and agencies such as the Domestic Violence and Victims Support Unit (DOVVSU) delayed the process because of non-response and reluctance to release data.

- Also, in most cases the formats and the units of measurement used by the departments for submission of the same information are different. To address this, new estimations had to be made so that the right figures could be submitted.

- More so is the indiscriminate selling of large areas of farmlands to multi-nationals and para-rubber farmers leading to destruction of existing cocoa and other food crop farms. This situation if not halted is potentially potent for food insecurity in the future.

- Inadequate funds to organize M&E meetings were also a challenge.

## CHAPTER TWO (2)

## MONITORING AND EVALUATION ACTIVITIES REPORT

## Introduction

This section of the report provides a comprehensive review of the performance of the 2024 Annual Action Plan as outlined in the Medium-Term National Development Policy Framework (Agenda for Jobs: Creating Prosperity and Equal Opportunity for All 2022-2025). It also includes an analysis of the operations of decentralized departments and agencies that are aligned with the Shama District Medium-Term Development Plan (2022–2025) during the specified year.

Key components of this section include: the status of programs and projects for the year, updates on funding sources and disbursements, progress on indicators and targets, critical development and poverty issues, evaluations conducted with their findings and recommendations, participatory monitoring and evaluations (PM&E) carried out with their results, and a conclusion with a look toward the future.

## Programme/Project Status for the year

## Physical Projects

Several physical projects were executed during the year under review. Detailed information about these projects, including their descriptions, contract sums, and implementation status, is provided in the project register/matrix in Appendix 1, along with details on the repair and maintenance of existing infrastructure in Appendix 2.

The 2024 project registry lists 17 physical projects. To monitor their progress, the DPCU, along with all parties involved, conducted monitoring and assessment activities every three months. Funding for these projects came from various sources, including the DACF, MPCF, DACF-RFG, and GET Fund. By year-end, the projects were at different stages of completion. Some had their timelines extended due to delays in external funding disbursements. While some projects were completed, there were still outstanding retention amounts to be paid to the contractors. However, all ongoing and unfinished projects have been carried over into 2025 to ensure their full completion, supporting the district’s efforts to achieve its goals and objectives. The completion of these projects from diverse funding sources will significantly improve the quality of life for citizens in the district.

## Repair And Maintenance of Existing Infrastructure

In Shama District, repair and maintenance of existing infrastructure are essential to ensuring the longevity, functionality, and safety of critical resources. Maintenance activities encompass a variety of tasks, such as addressing wear and tears, repairing structural damage, and conducting regular inspections to prevent potential hazards. By prioritizing maintenance, the Shama District Assembly can extend the lifespan of infrastructure, minimizing the need for costly replacements or major repairs in the future. As shown in the table (Appendix 2), the Assembly has effectively maintained its infrastructure, which has positively impacted the overall quality of life for residents by ensuring the reliability of services such as transportation, utilities, and public facilities. This commitment to regular maintenance has also supported economic stability by preserving property values, attracting investment, improving infrastructure, and minimizing disruptions to business activities, all of which align with the district's goals and vision. Additionally, maintaining infrastructure boosts community resilience to natural disasters and other emergencies. Therefore, investing in repair and maintenance is crucial for promoting sustainable development, driving economic growth, and protecting the well-being of Shama District residents.

## Programmes

A total of 286 activities were recorded in the programmes register for the reporting year. These programmes span all six development dimensions outlined in the National Medium-Term Development Policy Framework: AGENDA FOR JOBS: CREATING PROSPERITY AND EQUAL OPPORTUNITY FOR ALL, 2022-2025. Detailed information, including the total number of beneficiaries, is provided in a matrix in Appendix 3.

Challenges encountered during programme implementation included the low level of public engagement and delays in the allocation of funds for programme execution. Despite these challenges, the successful implementation of most activities in the Annual Action Plan played a significant role in achieving the Assembly's broader development goals and objectives. These activities have had a positive impact on various indicators, particularly in education, health, water and sanitation, and roads. Overall, there has been an improvement in the quality of life, with a reduction in poverty levels, the development of substantial capital, and the creation of a limited number of job opportunities through business training programmes.

## Update on Funding Sources

This section presents an analysis of the sources of funds for the Assembly, total amount received and how these funds were utilized (expenditure) within the period under review. The information is presented in tabular and graphical format to enhance readers’ understanding.

## Update on Revenue Sources

The Assembly's traditional revenue sources include the District Assembly Common Fund (DACF), Government of Ghana (GoG), District Performance Assessment Tool (DPAT/DACF-RFG), Member of Parliament Common Fund (MPCF), School Feeding Grant (SFG), Donor Support (DS), and Internal Generated Funds (IGF). Among these, the District Assembly Common Fund (DACF) remains the primary funding source for developmental projects and programs in the district. Other notable funding sources include DACF-RFG, MPCF, Donor Support, and IGF. During the year under review, there were delays and irregularities in the release of funds from the Government of Ghana, particularly the DACF. Table 3 below outlines the various sources of funds received from January to December 2024, with comparisons to previous years.

Table 3: Update on Revenue Sources

| Revenue Sources | Estimates |  |  |  | Performance |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2021 | 2022 | 2023 | 2024 | 2021 | 2022 | 2023 | 2024 |
| DACF | 3,961,475.00 | 3,919,126.10 | 1,800,000.00 | 2,000,000.00 | 901,296.82 | 1,680,385.51 | 1,203,911.36 | 1,818,824.09 |
| DACF- RFG | 1,180,906.00 | 1,204,832.56 | 1,744,566.24 | 1,800,000.00 | 1,115,329.00 | 1,174,498.30 | 0.00 | 1,452,792.00 |
| MP’s CF | 594,221.00 | 320,000.00 | 696,390.00 | 700,000.00 | 432,321.66 | 460,777.15 | 446,101.35 | 649,214.41 |
| IGF | 2,000,000.00 | 2,100,000.00 | 3,680,000.00 | 4,000,000.00 | 1,813,231.85 | 2,105,590.37 | 3,538,327.53 | 6,085,362.84 |
| MSHAP/HIV | 83,600.00 |  |  |  |  | 12,526.38 |  | 3,121.50 |
| PWDs CF |  | 250,000.00 | 200,000.00 | 210,000,00 |  |  | 106,443.63 | 261,264.64 |
| UNICEF |  | 30,000.00 | 30,000.00 | 30,000.00 |  | 30,000.00 | 30,000.00 | 30,000.00 |
| LEAP |  |  |  |  |  |  |  | 0.00 |
| GOG SALARIES | 4,369,075.08 | 3,101,669.80 | 5,121,894.29 | 8,000,000.00 | 3,710,591.90 | 5,147,122.64 | 7,754,649.74 | 8,364,407.20 |
| GOG GOODS & SERVICES | 71,913.00 | 109,017.00 | 56,000.00 | 60,000.00 | 50,643.78 | 51,296.98 | 55,142.03 |  |
| TOTAL | 12,261,190.08 | 11,034,645.46 | 13,323,494.31 | 16,590,000.00 | 8,023,415.01 | 10,662,197.33 | 13,134,575.64 | 18,664,986.68 |

Source: Finance Dept., 2024

Figure 2: Funding Sources compared between 2022 and 2024.

## Analysis of Funding Sources Compared between 2022 to 2024

Table 3 and Figure 2 display the funding levels from various sources, showing that the Assembly received more funds in 2024 compared to previous years, particularly from IGF, the MP’s CF, and DACF. As a result, the total funding for 2024 exceeded that of 2023, contributing to the Assembly's success rate of 94.68%, an increase of 1.76% from 92.98% in 2023. Furthermore, in 2024, the Assembly raised nearly double the amount of IGF compared to 2023. This increase was due to MMDAs regaining the responsibility for collecting property rates after the Ghana Revenue Authority took over this task in 2023. This allowed for the implementation of more program-based activities than physical projects, which significantly supported the achievement of the district's goals, particularly in enhancing access to socio-economic services and maintaining peace and security.

However, the Assembly's performance in the LEAP area could have been improved had the expected funds been released on time. To overcome these challenges in 2025 and enhance revenue collection, several strategic interventions have been introduced. These include the creation of the IGF Working Group and Task Force, the deployment of National Service personnel for revenue collection, the bonding of Area Councils, and capacity-building initiatives for market queens to assist in revenue collection for the Assembly. Additionally, management has implemented a reward system and introduced a revenue league table that tracks revenue collection from different Area Councils. This initiative is designed to motivate collectors and prevent the misappropriation of funds.

## Update on Expenditure

According to the collected records, the Assembly allocated its financial resources into three main categories: Compensation, Goods and Services, and CAPEX. The data indicates that, during the period from 2022 to 2025, the Assembly allocated more resources to Compensation in 2024 than in 2023. This shift is due to an increase in activities such as monitoring and evaluation, DISEC meetings, and other statutory committee meetings.

The total annual expenditure for 2024 was 25.13% higher than that of 2023. This increase can be attributed to several factors, including the completion of three capital projects, the procurement and distribution of 320 hexagonal tables and 1,920 chairs to schools across the district, emergency responses, support for the health sector, and backing government flagship programs such as Free SHS, Planting for Food and Jobs, and Planting for Export and Rural Development. A detailed breakdown of the Assembly's expenditure from 2022 to 2024 is provided in Table. This financial investment was instrumental in advancing the district’s goals and objectives. It created a favorable environment for business growth, improved access to essential social services, reduced crime rates and other social challenges, promoted the Local Assembly utilizing its revenue during the year under review. Expenditures were categorized into three main components: Compensation, Goods and Services, and CAPEX(Investment/Assets), along with other additional expenses not explicitly covered in this template.

Table 4: Disbursement (Expenditure) between 2023 Compared with 2024

| Budget Items | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure |
| Compensation | 3,990,123.08 | 3,961,795.20 | 3,961,795.20 | 4,320,352.06 | 5,254,750.61 | 5,254,750.61 | 4,471,388.32 | 8,244,306.38 | 8,244,306.38 | 4,500,000.00 | 9,028,607.76 | 9,028,607.76 |
| Goods and Services | 4,353,147.97 | 3,079,311.22 | 3,079,311.22 | 4,161,499.65 | 4,059,380.15 | 4,059,380.15 | 4,636,473.18 | 4,523,507.27 | 4,523,507.27 | 4,898,000.00 | 5,518,478.12 | 5,518,478.12 |
| CAPEX | 3,917,919.03 | 367,873.61 | 367,873.61 | 2,552,793.75 | 1,354,927.64 | 1,354,927.64 | 4,164,989.03 | 424,897.18 | 424,897.18 | 545,500.00 | 1,960,670.19 | 1,960,670.19 |
| Total | 12,261,190.08 | 7,408,980.03 | 7,408,980.03 | 13,134,645.46 | 10,669,058.40 | 10,669,058.40 | 13,272,850.53 | 13,192,710.83 | 13,192,710.83 | 9,943,500.00 | 16,507,756.07 | 16,507,756.07 |

Source: Finance Dept., 2024

As shown in the table, expenditure in 2024 exceeded that of 2023 due to the Assembly's involvement in various high-cost initiatives. Key among these were investment projects, routine monitoring and evaluation activities, and expenses related to DACF-RFG projects.

This financial commitment played a crucial role in achieving the district's goals and objectives. It created a favorable environment for business expansion, improved access to essential social services, reduced crime and other social challenges, promoted Local Economic Development, and enhanced the district's international reputation. These expenditure trends are further illustrated in Figure 3 below.

Figure 3: Analysis of Disbursement (Expenditure) for 2021, 2022, 2023 and 2024

Source: Finance Dept 2024

Table 5: Shama District Assembly CAPEX Analysis

| Proposal |  | Release Expenditure |  | Variations |  |  | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unconstrained Capex- plan (A) | Constrained Capex-budget (B) | (C) | (D) | (A-B) | (B-C) | C-D |  |
| 6,700,000.00 | 5,099,670.00 | 1,960,670.19 | 1,960,670.19 | 1,600,330.00 | 3,166,643.76 | 0 | - The Assembly should comply with the payment plan made. |

Source: DPCU

Table 6: (ANNEX 6B) MMDAs Capex Budget Performance Analysis

| Estimate |  | Release | Expenditure | Variance |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Unconstrained (A) | Constrained (B) | C | (D) | (A-B) | (B-C) | C-D |
| 4,500,000.00 | 3,473,670.00 | 1,359,026.24 | 1,359,026.24 | 1,026,330.00 | 2,114,643.76 | 0 |
| 2,200,000.00 | 1,626,000.00 | 601,643.95 | 601,643.95 | 574,000.00 | 1,052,000.00 | 0 |
| 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 6,700,000.00 | 5,099,670.00 | 1,960,670.19 | 1,960,670.19 | 1,600,330.00 | 3,166,643.76 | 0 |

The table presents information related to proposed plans and budget for the year 2024, release, expenditure, variations, and recommendations, possibly in the context of a financial or budgetary analysis. The Unconstrained Capex plan depicts the total number of capital projects in the 2024 AAP that has been planned for while constrained is the actual projects budgeted. In the year under review, GH₵ 5,099,670.00 was budgeted while only GH₵ 1,960,670.19 was released for the execution of those projects. At the end of the year, it can be observed that the actual expenditure used in carrying out the projects is the actual released.

Table 7: CAPEX budget allocation and implementation for ongoing projects

| Multi-Year CAPEX throw forward |  |  | MTBF Envelope |  | Performance |  | Details on Capital Projects, 2024 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Annual Estimate | Annual Estimate | Annual ceilings |  | Approved/Released | Expenditure | Project |  |  |  |  |  |  |  |  |  |  |  |
| Total Medium-Term Plan Estimate ( plan) |  |  |  |  |  |  | Code | Name | Age | Original Estimate cost | Revised cost | Expenditure to date | Outstanding balance | Completion status |  | Time overruns | Cost overruns | Land acquisition and resettlement |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  | % | Picture |  |  |  |
| 2022-2025 | 2025 | 2024 | 2025 | 2024 | 2024 | 2024 |  |  |  |  |  |  |  |  |  |  |  |  |
| 18,183,382 | 5,500,000.00 | 6,000,000.00 | 4,094,028.00 | 5,099,670.00 | 1,960,670.19 | 1,960,670.19 |  | Construction of 1No. 3 Unit Classroom Block with ancillary facilities at Essaman | 12months | 281,904.02 | NA | 155,048.48 | 126,855.54 | 60% |  | 60 months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Construction of 1No. 3 Unit Classroom Block with ancillary facilities Phase 1 at Komfueku | 12months | 282,667.55 | NA | 94,915.54 | 187,752.01 | 85% |  | 60 months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Const. of 3-unit classroom Block with ancillary facilities at Ituma (Revised) | 6months | 195,545.37 | NA | 113,214.20 | 82,331.17 | 85% |  | 108months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Construction of Area Council Office at Abuesi | 6months | 76,070.25 | NA | 32,131.73 | 43,938.52 | 43% |  | 108months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Construction of 6-Unit Classroom Block with Office Atta Na Atta (Revised) | 6months | 222,320.64 | NA | 131,408.32 | 90,912.32 | 85% |  | 98months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Continuation and completion of Community Centre Abuesi (DACF MP) | 9months | 507,775.73 | NA | 233,482.45 | 274,293.28 | 55% |  | 103months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Construction of 1 No. 3-Unit Classroom block with Ancillary Facilities Phase1 Assorko | 12months | 277,860.83 | NA | 96,163.21 | 181,697.62 | 45.8% |  | 53months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Construction of CHPS Compound Abuesi (DACF MPHF) | 12months | 479,034.36 | NA | 275,915.35 | 203,119.01 | 60% |  | 36months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Construct 1 No. 4units Semi-Detached Chamber and Hall Teachers Quarters | 6months | 449,500.00 | NA | 268,236.43 | 181,263.57 | 65% |  | 33months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Construction of 3 Units Classroom Block at Assorko | 6months | 303,500.00 | NA | 257,975.00 | 45,525.00 | 75% |  | 33months | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Renovation of 5no. market sheds and graveling at beposo | 6 months | 380,020.45 | NA | 106,420.45 | 273,600.00 | 100% |  | 0 | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Completion of football park | 6 Months | 150,931.55 | NA | 22,681.55 | 128,250.00 | 100% |  | 0 | NA | NO PENDING ISSUE |
|  |  |  |  |  |  |  |  | Construction of community market shed with store and urinal | 6 months | 459,442.00 | NA | 70,142.00 | 389,300.00 | 100% |  | 0 | NA | NO PENDING ISSUE |

NA-Not Applicable

## Analysis of Capex Budget Allocation and Implementation for Active Projects

Ongoing infrastructure projects in the Shama district have faced considerable delays due to multiple challenges. Administrative bottlenecks have been a primary obstacle, while setbacks such as reductions and delays in DACF disbursements, regulatory compliance issues, and funding uncertainties have further hindered progress. Additionally, logistical difficulties and manpower shortages have worsened the situation, causing stagnation in critical infrastructure development. Some of the active projects rolled over from the previous years were awarded by GETFUND secretariat and it has been abandoned. In the year under review, the Assembly undertook 3 major Capital projects and all were completed even though the Assembly has some outstanding payments to be made to the contractors.

Despite these challenges, the Assembly has made significant contributions to the district’s development. Several active projects are progressing steadily with the available resources, reinforcing the Assembly’s commitment to building a resilient economy, one of its key strategic objectives.

## Update on Indicators & Targets

Certain key indicators are essential for monitoring the progress of project and program implementation. These indicators serve as benchmarks to evaluate whether initiatives are advancing as expected.

In collaboration with MMDAs, RPCUs, DPCUs, CSOs, and DPs, the NDPC has established district-level key indicators and targets to be tracked across all MMDAs nationwide. These indicators are categorized under the development dimensions of the National Medium-Term Development Policy Framework. Detailed information on indicator levels, baselines, targets, and actual performance for the review period is provided in Appendix 3 of this report.

Additionally, the District developed specific indicators as measurement units to help the Assembly’s management assess progress toward achieving its goals and objectives outlined in the DMTDP 2022–2025. These indicators were accompanied by targets, enabling management to quantify performance levels for each period.

## Implication of the Indicator Results on District Goals and Objectives

This section highlights the performance of district core indicators and specific indicators and target set under the Agenda for Jobs. The indicators and their corresponding target have been categorized under the development dimensions and their assessment focuses on the goals of the Assembly.

## Economic Development

Based on the data gathered, the economic development sector achieved significant results through various strategic initiatives. The promotion of secure transactions on mobile money enhanced financial inclusion and trust in digital financial services. The organization of Local Economic Development (LED) Committee meetings facilitated stakeholder engagement and policy coordination, fostering a conducive environment for economic growth.

Collaboration with financial agencies to provide soft loans to Small and Medium Scale Businesses improved capital flow, supporting entrepreneurship and business sustainability. The establishment of a District Local Economic Development (LED) Platform created a centralized system for economic planning and stakeholder engagement. Supporting businesses in forming vibrant groups, cooperatives, and local partnerships facilitated knowledge sharing, resource pooling, and collective business growth.

Additionally, assisting SMEs in developing business proposals and linking them to financial sources enhanced funding, boosting business expansion and job creation.

In the agricultural sector, conducting yield studies on selected crops such as rice, maize, cassava, and plantain enabled data-driven decision-making for improved agricultural productivity. Demonstration and field days on improved technologies enhanced farmers’ adoption of modern farming techniques, increasing yields. Regular farm and home visits facilitated the effective implementation of programs such as PJF, RFJ, and PERD, ensuring continuous agricultural development.

These collective efforts significantly contributed to the economic development sector’s strong performance, fostering job creation, business growth, and sustainable economic progress.

## Social Dimension

Activities implemented under Social Development Dimension focused on improving Education and Training, Health and Health Services, Population Management, Water and Sanitation, Child, and Family Welfare, The Aged, Disability and Development, Employment and decent work, Gender Equality, and Sports and Recreation. A total of 126 activities were implemented under this dimension.

As part of the Assembly’s quest to promote equal opportunities, especially for the Vulnerable in society, the Assembly enrolled 42 people with Disabilities (PWDs) in the Disability register. Out of the forty two, 27 females and 15 males making the total register 859.The PWD register was accordingly updated to capture the new applicants. During the year under review, the Social Welfare Department  in collaboration with  the National Commission for Civic Education, Legal Aid, Education, Health directorate, Hen Mpoano (an NPO), Information Service, Statistics, Human Rights and Administrative Justices, Traditional Authorities, and Rural Aid Alliance foundation (RAAF) were able to organised Twenty-six  community durbars/meetings  in the selected communities,  three (3) radio programmes to sensitize public  on child protection issues, gender based violence, women empowerment in decision making, Core mandates of the departments, good parenting , Human Rights and Civic Responsibilities, World International Women’s Celebrations. Peace Campaign Gender Inclusive

The performance indicators showcase the district’s progress in the education sector, with net enrollment rates reaching 69.4% overall and 86.19% at the Kindergarten and Primary levels. Additionally, improvements in gender parity and completion rates reflect the positive impact of strategic interventions implemented by the assembly to enhance educational outcomes, aligning with the goals of SDG 4.

At the Junior High School (JHS) level, the pass rate increased significantly from 55% in the 2022/2023 academic year to 64.6% in 2023/2024. This achievement is attributed to logistical support that enabled frequent and intermittent monitoring visits to schools across the district. Moving forward, the District Education Directorate remains committed to strengthening monitoring efforts to sustain and further improve performance.

In the health sector, despite various challenges, the district achieved remarkable success in disease control, maintaining a zero maternal mortality rate and preventing malaria-related fatalities. However, health facilities recorded low Outpatient Department (OPD) attendance, possibly due to residents opting for pharmacies and traditional herbal remedies for their healthcare needs.

## Environment, Infrastructure and Human Settlements

This Development Dimension focused on establishing a safe, healthy, and conducive environment to support socioeconomic activities. During the year under review, various initiatives, including health education programs, industrial inspections, and environmental health interventions, were implemented to safeguard public health, protect property, and promote effective sanitation practices.

Aligned with the district's goal of promoting spatially integrated and orderly human settlements, this dimension addressed key areas such as housing, protected areas, transportation infrastructure, drainage, and flood management. Additionally, the Assembly undertook climate change-related initiatives to support the achievement of SDGs 11, 13, and 15. These efforts included reclaiming degraded lands, raising public awareness on agroforestry, and tree planting activities.

The implementation of these initiatives under this development dimension contributed to notable improvements in key performance indicators.

## Roads

The state of road infrastructure in the district remains a major concern. The district has a total road network of 242.9km, consisting of approximately 113km of feeder roads and 42.5km of urban roads, while the remaining roads are rural and in poor condition.

During the year under review, in alignment with the national agenda to improve the efficiency and effectiveness of road transport infrastructure and services, the Assembly undertook several feeder road reshaping activities as part of the DRIP initiative. Through this initiative, the DRIP team successfully reshaped 8.4km of roads, including the Komfueku to Shama Junction stretch and the Yabiw to Yabiw Junction route.

The persistent challenges in the road sector have had far-reaching effects on other sectors, hindering the Assembly’s ability to fully and effectively achieve its developmental objectives.

## Electricity Coverage

The district has achieved full electricity coverage in all communities, both rural and urban, connected to the national grid. This aligns with the national agenda to enhance the efficiency of the transmission and distribution system, significantly improving the well-being of residents. Additionally, this initiative contributes to the attainment of SDG 7, specifically Target 7.1.

## Governance, Corruption, and Public Accountability

#### The district's objective under this development dimension is to ensure transparent and accountable governance. This involves promoting active citizen participation in governance and decision-making processes while strengthening the capacity of both district and sub-district administrations to operate efficiently and effectively.

#### In 2024, the District Assembly implemented 58 activities and projects in alignment with good governance principles, many of which support the objectives of SDG 16. These principles include openness, transparency, responsiveness, and sustainability. To enhance government accountability and public engagement, the Assembly organized town hall meetings, open governance partnership meetings, and stakeholder engagements.

#### These initiatives fostered greater transparency, strengthened institutional efficiency, and contributed to improvements in key governance performance indicators within the district.

## Emergency Planning and Response (Including Covid-19 Recovery Plan)

The primary objective of the Emergency Planning and Response Dimension, including the COVID-19 recovery plan, is to promote proactive planning and implementation for disaster and disease prevention while enhancing the district’s adaptive capacity to withstand national and global threats.

Indicators within this development dimension assess the Assembly's preparedness for emergencies, including disasters and COVID-19 cases. As a coastal and agricultural district, the Assembly recorded fewer disaster-related impacts in the review year compared to 2023. Specifically, two communities were affected by domestic fires, two building collapses were recorded, and no communities experienced flooding or rainstorms.

Through continuous education and sensitization efforts, the District Assembly successfully reduced fatalities and the number of individuals impacted by disasters. This led to a significant decline in direct economic losses, with a strong focus on protecting vulnerable populations and safeguarding the well-being of the poor.

## Implementation, Coordination, Monitoring and Evaluation

Effective governance and sustainable development rely on efficient planning, execution, and coordination at all levels. This development dimension focuses on strengthening monitoring and evaluation systems, improving statistical data production and utilization, enhancing resource mobilization, optimizing resource management, and promoting knowledge-sharing and learning processes. By advancing these areas, the district aims to foster greater efficiency, accountability, and impact in its developmental efforts.

A key indicator of progress in this dimension is the successful implementation of the 2024 Annual Action Plan, which achieved a 94.68% completion rate, an improvement from 92.98% in 2023. This increase reflects the Assembly’s commitment to enhancing revenue generation and deepening stakeholder collaboration, ensuring that planned initiatives are effectively carried out.

The district’s improved performance can be attributed to robust monitoring and evaluation mechanisms that provided timely feedback for better decision-making. Additionally, aligning with SDG 17, which emphasizes partnerships for sustainable development, the District Assembly worked closely with organizations such as Friends of the Nation, CDD, and other key stakeholders. These collaborations facilitated the successful execution of planned activities, ensuring that development efforts were inclusive and impactful.

By continuing to strengthen its planning, monitoring, and stakeholder engagement strategies, the district is well-positioned to achieve greater efficiency, transparency, and long-term sustainability in its development agenda.

## Underlying Factors of Success or Failure in the Performance of the Indicators

From the data gathered from the various departments, we observed that, the successes and failures encountered were due to certain factors. These have been categorized as success factors and Failure factors.

## Success Factors

- Enhanced project/programme supervision

- Regular site inspections

- Improved revenue mobilization

- Enhanced cooperation of stakeholders

- The use of the Participatory Monitoring and Evaluation Strategy which offered an opportunity to the citizens/beneficiaries to participate in the programmes/project implementation processes.

- Engagement of Assembly members in revenue collection

## Failure Factors

- Inability to meet revenue target due to the following reasons.

- Inadequate Permanent Revenue Staff,

- High Attrition Rate of Trained Revenue Collectors,

- Inadequate Logistics (Lack of Dedicated Vehicle for Revenue Mobilization),

- Effect of post covid-19 era as many organizations called for rebates or fees waivers.

- Late or non-release of funds from Central Government, especially DACF) leading to inability to implement projects budgeted against the DACF.

- Inadequate funds for data collection and untimely submission of reports from some decentralized departments.

- Inadequate logistics (computers, laptops, vehicle) for departments and units.

- Inadequate and untimely release of funds for implantation activities.

## Update on Critical Development and Poverty Issues

This section discusses programs and intervention to protect the vulnerable and the marginalized in the society who are most often considered the poor as well. These interventions are necessary to cushion the target group from socio-economic shocks. The District Planning Unit, together with the Department of Social Welfare and Community Development administer the social interventions in the district. The major social protection interventions in the district are Livelihood Empowerment against Poverty (LEAP), interventions for the disabled, school feeding programs, Capitation Grant, NHIS, 1D1F, Free SHS and Agricultural programmes.

Table 8: Update on Critical Development and Poverty Issues

| Critical Development and Poverty Issues | Allocation GH¢ | Actual receipt GH¢ | No of beneficiaries |  |
| --- | --- | --- | --- | --- |
|  |  |  | Targets | Actuals |
| Ghana School Feeding Programme | 25,582.20 | 25,582.20 | Male:8,230 Female:12,421 | Male: 7,520 Female: 10,753 |
| Capitation Grants | 254,170 | 198,454 | Male:11,000 Female:13,000 | Male: 11,069 Female: 14,381 |
| National Health Insurance Scheme | 1,931,904 | 310,098 | Male: 30,000 Female:90,496 | Male:40,699 Female:158,708 |
| Livelihood Empowerment Against Poverty (LEAP) programme | 500,000 | 465,840 | 1306 | Male:197 Female:1109 |
| National Youth Employment Program | N/A | N/A | Male Female | Male Female |
| One District-One Factory Programme | N/A | N/A | Male Female | Male Female |
| One Village-One Dam Programme | N/A | N/A | Male Female | Male Female |
| Planting for Food and Jobs Programme | 8,000.00 | 7,300.00 | Male:1000 Female:800 | Male:950 Female: 181 |
| Free SHS Programme | 1,848,946.22 | 332,660.25 | Male:1490 Female:2050 | Male:1490 Female:2050 |
| Planting for Export and Rural Development | 548,900.00 | 909,000.00 | Male: 170 Female: 100 | Male: 175 Female: 68 |
| Common fund for persons with disability | 149,008.02 | 261,264.64 | 100 | Total =76 Male = 32 Female =44 |

N/A1 - Not Applicable				N/A – Not Available     NRD- No reliable data

According to the data presented in Table 6, the Assembly executed seven interventions aimed at tackling critical development and poverty issues identified in the district during the reviewed year. For all these interventions, the Assembly saw some level of success.

The free SHS policy is ongoing with the numbers increasing every year.

## School Feeding Programme (SFP)

The School Feeding Programme was initiated to offer each student a nutritious meal during school days, aiming to boost enrollment and keep students in basic education. The initiative was later restructured to enhance its focus, ensuring that the most disadvantaged regions benefit the most. Toe, 18,273 students in the district have benefited from the programme. An amount of 25,582.20 Ghana cedis was designated for the programme; however, delays in fund disbursement have posed challenges to its effective implementation.

## Livelihood Empowerment Against Poverty (LEAP) programme

The Livelihood Empowerment Against Poverty (LEAP) program provides both conditional and unconditional cash transfers to extremely poor households lacking viable means to meet their basic needs and with limited capacity to earn a living. Beneficiaries include the elderly poor, individuals with severe disabilities, and children in challenging situations. The transfers aim to empower these households to meet their basic needs and facilitate their participation in the country's socio-economic development. In 2 the total cash transferred to beneficiaries was estimated at GH¢500,000, reaching 1,400 individuals. The Asly disbursed GH¢465,840 to 1,306 beneficiaries, comprising 1,109 females and 197 males.

## National Health Insurance Scheme

In the Shama District, the NHIS operates a district office to facilitate the registration and renewal of memberships, ensuring that residents can access health care services without financial barriers.

The Shama District Assembly has also been involved in initiatives to enhance healthcare accessibility, such the commissioning the new District National Health Insurance Authority (NHIA) office. Through these efforts, the NHIS aims to provide equitable access to essential healthcare services for all residents of the Shama District.

Under the year under review, 199,407 indigenes were recorded on the NHIS programme, with 40,699 being males and 158,708 being females. The total number includes renewals and new registrations.

## Planting for Food and Jobs Programme

The department had received a supply of seed rice and fertilizer under Planting for Food and Jobs 2.0 (PFJ 2.0) program in the third quarter. In all 1,131 farmers have been registered so far with more farmers expected to be registered.

With the department creating WhatsApp platforms to enable farmers to sell their produce through the digital medium. Currently the platform has participant of 70 agriculture value-chain actors with females being 16 and males 54.

The modernization of the agriculture sector was projected to be an important driver of growth to improved productivity and to create employment for the youth. The Assembly was therefore projected an amount of GH¢8,000 to a total beneficiary of 1,800. Assessment of progress in 2024 shows an overall amount of GH¢7,200 to a total beneficiary of 1,131 which shows a reduction in funds allocation as compared to the year 2023.

## Capitation Grant

The Shama District Assembly Estimated that 24,000 of its people will benefit from the Capitation grant for the 2024 academic year however, at the end of the year under review, 25,450 people benefitted from the grant which amounts 198,454.00 Ghana cedis

## Common Fund for Persons with Disability

As part of the effort to reduce incidence of unemployment among the People with Disability (PWDs), the Shama District Assembly received an amount of GH¢261,264.64 in support of beneficiaries to acquire various training in artisans. At the end of the year 2024, the social welfare department undertook a three-day pre monitoring exercise to beneficiaries across the district. The exercise was to assess the impact of the support on their daily livelihoods.

## Planting for Export and Rural Development (PERD)

The program is to promote seedlings to farmers that will aid in community development and also increase the chance of exportation in the country. These seedlings that benefitted were oil palm and coconut. A total of 32,000 oil palm seedlings and 75,000 coconut seedlings were distributed to farmers. Two hundred and forty-three (243) farmers benefited with sixty-eight (68) females and one hundred and seventy-five (175) males. The distribution lasted for one week. The collaborating institutions were Agriculture Department, Shama District Assembly, Shama Coconut Growers Association, Coconut Research Institute and farmers.

Farmers who registered with the department were able to benefit from the programs and farmers were able to cultivate their land and planted for future cash benefits. Seedlings were given free and household income will be increased in the future.

During the home and farm visits, farmers who have benefited from the first year (2019) program launch starts to harvest oil palm and coconut are yet to flower. Farmers encourage that seedlings should come and in their high numbers at the right time to increase food security and promote development in the country.

Table 9: Staff Strength for Shama District Assembly

| SHAMA DISTRICT ASSEMBLY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | REQUIREMENT |  | ACTUAL |  | TRAINING |
| DEPARTMENT | MINIMUM | MAXIMUM | 2024 | %COVERED | REQUIRED |
| Central Administration | 96 | 128 | 109 | 86% | Course in Local Government Administration, Report/Speech writing, Event management |
|  |  |  |  |  | Report Writing Skills, and Interrogation Skills |
|  |  |  |  |  | Database System Programming, Introduction to Project Management, A course in Local Government Administration |
|  |  |  |  |  | Research Methods and Impact Assessment, project Proposal Writing and Reporting, induction Training; |
|  |  |  |  |  | Records Management, Office Management and Practice, Introduction to Ghana’s Public Administration System |
|  |  |  |  |  | Defensive Driving, Traffic Regulations and Transport Policies, Management and Vehicle Maintenance |
|  |  |  |  |  | Continuous Professional Development in Statistics, Statistical Information Course, I CT (Data Management and Analysis) |
| Agriculture | 43 | 72 | 10 | 13.9% | Administrative and Staff Management, Administrative and Staff Management, |
|  |  |  |  |  | Business Entrepreneurship, Intermediate Agricultural Administration |
| Works | 49 | 70 | 12 | 17.2% | Project proposal writing, project financing, PPA Framework Agreement. Contract Administration and Procurement, Basic Management Practices, Design and supervision of works |
| Social Development (Social Welfare & Comm. Dev't) | 10 | 11 | 10 | 90.9% | Conflict resolution and Peace Building, Participatory Development Planning, Public Social Development Policies |
| Health / Environmental health | 76 | 113 | 12 | 10.7% | Public health administration, Health and Safety Course, Environmental Management, Environmental Health and Sanitation Policy and practice, Environmental Management |
| Physical Planning | 15 | 21 | 8 | 38.1% | Induction training, Development Planning Programmes, A Course in Local Government Administration |
| BAC | 11 | 17 | 1 | 5.9% | Customer care and ICT |
| Finance | 21 | 33 | 3 | 9.1% | Financial Planning and Control; Course in Local Government Administration; and ICT |
| NADMO | 54 | 89 | 23 | 25.8% | Training in emergency response, hazard mapping, Course in Disaster management, health, and safety |

Source: HR Department

The table presents a comprehensive overview of the training needs requirement of the various departments of the district. It is believed that the departments would function beyond expectation when these department specific training courses were provided.

Table 10: Staff Strengths of MMDAs (Trainings and Workshops)

| NAME OR TYPE OF THE CAPACITY DEVELOPMENT | VENUE/LOCATION | PURPOSE OF THE PROGRAMME | SOURCE OF FUNDING | FACILITATORS | TARGET GROUP | NO OF BENEFICIARIES |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | TOTAL | MALE | FEMALE |
| organize training for staff on SUI-Qeneris Attendance and Productivity Requisites Facility (Clocking in System) | Church of Pentecost - shama | To train staff on the functionalities, operational ability, and benefits of SAPRF facility (Clocking in System) | DACF-RFG/DACF/IGF | All Staff | Regional HRM | 180 | 110 | 70 |
| Organize Training for Staff on LGS Protocols; The Roles and Functions of Staff of Department Physical Planning Department and Works | GES Conference Hall, shama | To sharpen knowledge of staff on LGS The Roles and Functions of Staff at Department Physical Planning Department and Works | DACF-RFG/DACF/IGF | Staff of Physical Planning Department and Works Department | Senior Engineer (OHLGS) | 32 | 27 | 5 |
| Public Financial Management |  | To build the capacity of the staff on Public Financial Management | DACF-RFG/DACF/IGF | All Staff |  |  |  |  |
| The Roles and Functions of Assembly Members in Local Governance | GES Conference Hall, shama | To build the capacity of the Assembly Members | DACF-RFG/ DACF/IGF | Unit Committee members | Dr Amid and Dr. Amoako (Institute of Local Government Studies | 25 | 22 | 3 |

Source: HR Department 2024

Capacity building plays a critical role in strengthening the operational efficiency and delivery service of local government institutions. In the Shama District Assembly, various training programs have been organized to enhance the knowledge and skills of staff and Assembly members. These capacity development initiatives focus on key areas such as attendance and productivity tracking, local government service (LGS) protocols, public financial management, and the governance roles of Assembly Members. These efforts aim to equip personnel with the necessary competencies to fulfill their responsibilities effectively, thereby improving governance and service delivery in the district.

One of the key training programs organized was on the SUI-Qeneris Attendance and Productivity Requisites Facility (Clocking-in System). This training, held at the Church of Pentecost in Shama, was designed to enhance the staff’s understanding of the functionalities and benefits of the system. Funded by DACF-RFG, DACF, and IGF, this initiative targeted all staff members and was facilitated by the Regional Human Resource Manager (HRM). A total of 180 participants (110 males and 70 females) benefited from the program. By improving attendance monitoring and productivity tracking, this training is expected to enhance overall staff efficiency and ensure accountability within the Assembly.

Additionally, training on LGS protocols and the roles of staff within the Physical Planning and Works Departments was conducted at the GES Conference Hall in Shama. The objective was to sharpen the knowledge of staff on LGS protocols and clarify their specific roles within their respective departments. Facilitated by a Senior Engineer from OHLGS, the program benefited 32 staff members (27 males and 5 females). By equipping participants with relevant knowledge, this training contributes to the effective implementation of physical planning and infrastructure development policies in the district.

To further strengthen the capacity of the staff in the upcoming year, additional training programs will be introduced. These include Report and Speech Writing, Database System Programming, Introduction to Project Management, Records Management, Office Management and Practice, Conflict Resolution and Peace Building, Public Social Development Policies, Financial Planning and Control, and Training in Emergency Response and Hazard Mapping as mentioned in Table 10. These programs will enhance staff competency in administration, governance, project execution, public service delivery, and emergency preparedness.

Overall, these capacity-building initiatives are crucial in strengthening the human resource base of the Shama District Assembly. However, there are areas for improvement. Firstly, there is a need for greater female participation in these programs to ensure gender inclusivity in capacity development. Secondly, the reliance on DACF-RFG, DACF, and IGF for funding suggests the need to explore alternative sources, such as partnerships with non-governmental organizations (NGOs) and private sector actors, to sustain training efforts. Additionally, while the focus has primarily been on Assembly staff and members, expanding training opportunities to include community members can foster broader citizen engagement in governance and service delivery.

In summary, capacity-building programs in the Shama District Assembly have significantly enhanced the knowledge and skills of staff and Assembly Members. These initiatives contribute to improved service delivery, governance, and accountability. However, efforts should be made to ensure inclusivity, financial sustainability, and community engagement to maximize the impact of these programs. Continuous assessment and follow-ups will be essential in measuring the long-term effectiveness of these capacity development efforts.

Table 11: Staff Strengths of MMDAs (Logistics)

| REQUIRED | REQUIRED | ACTUAL | REMARKS |
| --- | --- | --- | --- |
| Computers | 70 | 31 | Most of the offices still lack computers to work. Over the previous year, the Assembly procured 3 desktop and 7 laptops for some offices. The gap is still evident and needs to be closed |
| Printers | 20 | 6 | Some offices move to other offices to print. The exchange of pendrives sometimes corrupts official information through virus attacks. |
| Projectors | 3 | 1 | The assembly sought for projector outside for programs which is sometimes difficult |
| Office Space | - | - | Office complex which was under construction in the previous year has been completed and in use |
| Vehicle | 15 | 7 | Departments sometimes find it difficult to get vehicles to work when the three functional ones are not available. The functional ones are the DCE’s vehicle, the coordinating director’s vehicle, and one Nissan patrol. |

Source: HR Department 2024

## Evaluations Conducted, their Findings and Recommendations

In the year under review, one (1) major evaluation was conducted by the Assembly in collaboration with other/ user agencies. The assembly with support from Friends of the Nation and Rural Aid Alliance within the period under review (2024) conducted an Ex-Post Evaluation/Impact Assessment on a sea defence constructed from Aboadze to Abuesi by the central government.

The purpose of the evaluation was to provide a critical analysis of the evidence-based changes in relation to the strategic intervention implemented.

Table 12: Evaluations Conducted

| Name of the Evaluation | Policy/Programme/Project involved | Consultants or Resource Persons involved | Methodology Used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Ex-Post Evaluation/Impact Assessment | Construction of sea defence from Aboadze to Abuesi | FON/RAAF | - Key Informants Interview - Focus Group Discussions - Observation | RELEVANCE - The project is very relevant to the development of the area as it addresses the local problems and provides adequate solutions to the needs of citizens. - The project was timely because it came at a point where the sea erosion was very high. Tidal waves destroying properties IMPACT - There has been improvement of conditions at the landing beaches. canoes can now land safely. - Reduction in the cost of repairing canoes. Repair works on canoes as compared to those days are limited because the shore has a low tidal wave now | - The Assembly should prioritize construction of a bigger drainage through Abuesi town to allow free flow of water into the sea since the defence has blocked the exit of some drains. |

## Participatory M&E Undertaken and Their Results

Participatory Monitoring and Evaluation is a process through which stakeholders at various levels engage in monitoring and evaluation of a particular project, programme, or policy, share control over the content, the process, the results of the monitoring and evaluation activity and engage in decision making or corrective actions.

During the period under review, the District Planning Coordinating Unit (DPCU) was supported by Friends of the Nation (FoN) and the tools used for the PM&E were beneficiary feedback and citizen Score Card approach involving conversational interviews, focus group discussions and stakeholder interface meeting to assess the value of the construction of some selected DACF-RFG projects in the District. These projects include:

- Renovation of Beposo Market

- Completion of football park at Nchaban

- Construction Of 1 No.3 Unit Classroom Block with Ancillary Facilities at Assorko.

The objective of the Participatory M&E exercise was to assess the impact of the utilization of the Assembly’s share of revenue on projects as perceived by project beneficiaries and as well to integrate findings into project activities. Details of the results/findings are presented in Table 10 below. The feedback from the stakeholders has been incorporated in the processes of the Assembly and generally, governance is enhanced.

Table 13: PM&E Conducted

| Name of the PM&E Tool | Policy/Programme/Project involved | Consultants or Resource Persons involved | Methodology Used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Beneficiary feedback | Renovation of Beposo Market | DPCU Friends of the Nation (CSO) | Questions and answers, Interviews, Focus group discussion, stakeholder and interface meetings | - The project was captured in the 2024 Annual Budget and 2024 Annual Action Plan. - The project was duly completed and in use. - The project has duly been completed and handed over - There are only two Security light at the market. - No storage facility at the market - Availability of urinal but no toilet facility - Inadequate access to some of the sheds for Persons with Disability (Disability ramp). | - Additional disability ramps should be constructed for easy access for persons with disability. - The Assembly Should install Security lights at the market. - Plans should be made to construct a Storage facility for the Market. - Assembly should construct a place of convenience for the market. - The assembly should add on to the security light at the market |
| Beneficiary Feedback | Completion of football park at Nchaban | DPCU Friends of the Nation (CSO) | Questions and answers, Interviews, Focus group discussion, stakeholder and interface meetings | - The project was captured in the 2024 Annual Budget and 2024 Annual Action Plan. - There was no signpost mounted for information on the project. - The project has been completed - The project had other exit points for spectators to use in case of emergencies. | - The assembly should consider additional work for other disciplines since the park can accommodate that. - The assembly should consider the construction of a changing room with washrooms |
| Citizen score cards | Construction of 1No. Three (3) unit Classroom Block with office and store, Staff Common room Assorko | DPCU, Friends of the Nation (FON) | Stakeholder engagement | - The project has been delayed and yet to be completed - There was no washroom included in the project - The disability ramp was very steep | - stakeholders recommended that the screeding of floors for classrooms should be changed to tiles to make the rooms look good - The stakeholders appealed to management to factor in the issue of washroom to save pupils from going to the bush to ease themselves. - The stakeholders appealed with District Assembly and GES to get furniture ready for the school block |

## CHAPTER THREE

## THE WAY FORWARD

## Introduction

The chapter presents key issues addressed, yet to be addressed, and recommendations made towards the improvement of monitoring and evaluation of programmes and projects in the District.

## Key Issues Addressed and yet to be Addressed.

## Key Issues Addressed

Some of the major development issues that were addressed during the year under review are enumerated as follows:

- The Assembly has thrived very well in the roads sector in the year under review. The DRIP initiative implemented in 2024 enabled the Assembly to reshape most of its feeder roads which were in bad condition and unmotorable.

- The challenge of limited community and stakeholder participation in project execution was effectively mitigated by decentralizing engagements to the Area Council level.

- A Project Resuscitation Meeting was held with contractors to strategize the seamless continuation and completion of stalled projects.

- The execution of projects and programs was enhanced through increased site visits, site meetings, and active community participation in project implementation and management.

- Efforts to minimize delays in project and program execution have been partially addressed, with the Assembly prioritizing projects that can be completed within available financial constraints.

- To strengthen internal revenue mobilization, the Assembly's management and staff conducted a quarterly revenue mobilization task force throughout 2024.

- The Assembly took deliberate steps to strengthen district substructures by inaugurating and training their members. Following the training, the Assembly decided to delegate market toll and property rate collection to Unit Committees.

- All children under the care of Social Welfare have been successfully enrolled in school.

### 3.1.2 Issues yet to be addressed.

Delay in the release of funds: The issue of delay in the release of funds for programmes implementation and the deductions from sources are yet to be addressed. However, the District has made steps in improving the Internally Generated Funds. A few strategies have also been put in place to improve revenue performance.

Illegal mining activities: Illegal mining continues to cause concern. Shama continues to suffer the consequences of illegal mining since the pollution from other neighboring districts enter the pra river into the sea. Efforts are being made to support clamping down on activities of illegal mining, especially on the pra River which serves as the main water source for distribution by the Ghana Water Company Limited in the municipality and beyond.

GET Fund Projects: There are abandoned GETFund projects that have not been completed.

Absence of a Dedicated Vehicle for Project Monitoring. The Absence of a dedicated Vehicle for Project Monitoring for the MPCU to enable it to embark on the monitoring and evaluation of projects is also yet to be addressed by the Assembly.

## Recommendations

The monitoring and evaluation exercises carried out by the District Planning Coordinating Unit and the District Works Department identified several challenges related to project implementation in the district.

These challenges included the need for capacity building, poor road conditions leading to project sites, and delays in executing projects, particularly those funded by the District Assemblies Common Fund.

Based on these findings, the following recommendations were proposed for the Assembly’s management:

- Collaboration between the Assembly, government agencies, quarry companies, and other stakeholders to improve access roads in the district.

- Incorporation of climate change adaptation measures in project implementation.

- Adoption of strategies to ensure timely completion of projects.

- Ensuring prompt release of funds to facilitate the execution of planned programs and projects.

- The assembly should priorities securing a dedicated vehicle for monitoring and evaluation activities

## Conclusion

The year 2024 marked a significant improvement in the implementation of the District Medium Term Development Plan (DMTDP) compared to previous years. This progress was largely due to strategic planning, enhanced stakeholder engagement, and increased revenue mobilization, which facilitated the execution of key programs and projects. Despite economic challenges, the Assembly achieved a 94.68% success rate in implementing its Annual Action Plan, demonstrating resilience and commitment to sustainable development.

However, the consistent delays in the release of the District Assemblies Common Fund (DACF), logistical constraints, and limited funding for critical sectors such as health, social welfare, and infrastructure remain key challenges. These issues affected the timely and effective execution of projects, emphasizing the need for innovative approaches to resource mobilization and financial management.

Moving forward, the Assembly aims to strengthen internal revenue generation, improve monitoring and evaluation mechanisms, and deepen stakeholder collaboration to ensure the successful implementation of the remaining activities in the DMTDP (2022–2025). Additionally, emphasis will be placed on capacity-building initiatives to enhance the efficiency of service delivery. With the continued support of development partners, government agencies, and community stakeholders, the Assembly remains committed to achieving its goal of fostering inclusive and sustainable development in the district.

APPENDICES

Appendix 1: Projects Status - Updated Project Register As At December, 2024

| Project Description |  | Development Dimension | Location | Contractor | Contract Sum | Date of Award | Source Of Funding | Date Started | Expected Date Of Completion | Expenditure to Date | Out Standing Balance | Implementation Status |  | Strategies To Improve Project Completion Rate | How Citizens were involved in monitoring of works contract | Remarks Summary on land acquisition and resettlement |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Code | Name |  |  |  |  |  |  |  |  |  |  | % | Pictures |  |  |  |
|  | Continue and Complete the Construction of 80 capacity market shed, 20 lockable stores and crèche | Economic Development | Upper Inchaban | I.B Clements Co. Ltd. | 651,245.86 |  | IGF | 02/10/2019 | 01/10/2020 | 33,583.96 | 617,661.90 | 15% Complete (On-going) |  |  | Planning, monitoring, execution of project | NA |
|  | Construction Of 1 No.3 Unit Classroom Block With Ancillary Facilities | Social Development | Assorko | M/S EAK CO. LTD. | 303,500.00 |  | DACF-RFG | 15/03/2022 | 14/09/2022 | 121,097.19 | 182,402.81 | 65% |  |  | Planning, monitoring, execution of project | NA |
|  | Const. Of 1 No.4 Unit Semi-Detached Chamber & Hall Teachers Quarters | Social Development | Shama Ridge | M/S EAK CO. LTD. | 449,500.00 |  | DACF-RFG | 15/03/2022 | 14/09/2022 | 268,236.43 | 181,263.57 | 65% |  |  | Planning, monitoring, execution of project | NA |
|  | Construct CHPS Compound with a Maternity Block And Nurse Quarters | Social Development | Abuesi | Eagle Talons Ltd. | 479,034.36 |  | MPHF | 06/11/2019 | 05/11/2020 | 275,915.35 | 203,119.01 | 51.2% Complete (On-going) |  |  | Planning, monitoring, execution of project | NA |
|  | Rehabilitation of 6-Unit Classroom Block (Lot 4) | Social Development | Shama Methodist Primary | Confidence Traders & Hardware Co. Ltd. | 120,836.18 |  | GETFUND | 04/10/2016 | 05/02/2017 | - | - | 75% Complete |  |  | Planning, monitoring, execution of project | INACTIVE |
|  | Rehabilitation of 6-Unit Classroom Block (Lot 5) | Social Development | Shama Model D/A Primary | Asanoc Construction Limited | 121,692.72 |  | GETFUND | 04/10/2016 | 05/02/2017 | - | - | 60% Complete (Joinery & Painting stage reached) |  |  | Planning, monitoring, execution of project | INACTIVE |
|  | Construction of 1No. 2-Storey6-Unit Classroom Block with Ancillary Facilities (Lot 1) | Social Development | Aboadze Islamic Primary | Erns Developers Limited | 348,806.33 |  | GETFUND | 04/10/2016 | 05/02/2017 | - | - | 67% Complete (Super-structure block complete to Gable) |  |  | Planning, monitoring, execution of project | INACTIVE |
|  | Construction of 1No. 2-Storey6-Unit Classroom Block with Ancillary Facilities (Lot 2) | Social Development | Shama Junction D/A Primary | Progrev Company Limited | 350,891.63 |  | GETFUND | 04/10/2016 | 05/02/2017 | - | - | 35% Complete ( Over site and concrete column) |  |  | Planning, monitoring, execution of project | INACTIVE |
|  | Continue and Complete the Construction of 3 Unit Classroom Block Kedzi Kran, | Social Development | Kedzi Cran, | Nakopong Co. Ltd. | 180,882.45 |  | GETFUND | 10/10/2016 | 11/07/2017 | - | - | 41% |  |  | Planning, monitoring, execution of project | INACTIVE |
|  | Continue and Complete the Construction of 3 Unit Classroom Block Abuesi | Social Development | Abuesi | Assess Aba Ghana Limited | 180,407.31 |  | GETFUND | 15/12/2016 | 16/06/2017 | - | - | 25% Complete (Over site Concrete stage) |  |  | Planning, monitoring, execution of project | INACTIVE |
|  | Continue and Complete the Construction of 3 Unit Classroom Block Old Daboase | Social Development | Old Daboase | 13:05 Engineering & Construction Company Limited | 180,689.48 |  | GETFUND | 22/12/2016 | 23/06/2017 | - | - | 45% |  |  | Planning, monitoring, execution of project | INACTIVE |
|  | Continue and Complete the Construction of 3 Unit Classroom Block Ohiamadwen | Social Development | Ohiamadwen | A-Plus Construction Company Limited | 180,578.57 |  | GETFUND | 22/12/2016 | 23/06/2017 | - | - | 55% Complete (Gable level stage) |  |  | Planning, monitoring, execution of project | INACTIVE |
|  | Construction of Community Centers | Social Development | ,Abuesi | B.T Ventures | 507,775.73 |  | MPCF | 10/08/2015 | 12/05/2016 | 233,482.45 | 274,293.28 | 55% Complete (Roofing stage) |  |  | Planning, monitoring, execution of project | NA |
|  | Construct/rehabilitate Area council offices | Governance, Corruption and Public Accountability | Abuesi | Messrs E.F.B. Co. Ltd. | 76,070.25 |  | DACF | 02/06/2015 | 02/09/2015 | 32,131.73 | 43,938.52 | 43% Complete (Joinery / Finishing stage |  |  | Planning, monitoring, execution of project | NA |
|  | Renovation of 5no. market sheds and graveling at beposo | Economic Development | Beposo | K.Benyah Co. Ltd | 380,020.45 |  | DACF-RFG | 30/09/2024 | 30/12/2024 | 271,600.00 | 106,420.45 | 100% |  |  | Planning, monitoring, execution of project | NA |
|  | Completion of football park | Social Development | Inchaban | K.Benyah Co. Ltd | 150,931.55 |  | DACF-RFG | 30/09/2024 | 30/12/2024 | 128,250.00 | 22,681.55 | 100% |  |  | Planning, monitoring, execution of project | NA |
|  | Construction of community market shed with store and urinal | Economic Development | Inchaban abease | K.Benyah Co. Ltd | 459,442.00 |  | DACF-RFG | 30/09/2024 | 30/12/2024 | 389,300.00 | 70,142.00 | 100% |  |  | Planning, monitoring, execution of project | NA |

Appendix 2: Repair and Maintenance of Existing Infrastructure

| Asset/ infrastructure | Location | Type of maintenance | Estimated Cost | Actual Release | Gap | Expenditure | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Beposo Market | Beposo | Renovation and graveling works | GHC 380,020.45 | GHC 381,000.00 |  | 380,020.45 | Completed |
| Old administration block | Shama | Repair Plumbing fittings | 15,430.00 | 15,000.00 |  | 15,000.00 | Completed |
| Reshaping of selected feeder roads | Komfueku, yabiw | Reshaping of 8.4km road | 60,000.00 | 52,304.59 |  | 52,304.59 | Reshaping completed |

| Appendix 3: Programme register |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S/N |  | Programme Description | Development Dimension Of Policy Framework | Amount Involved Sum Gh¢ | Source Of Funding | Date Started | Expected Date of Completion | Expenditure To Date | Out Standing Balance | Implementation Status (%) |  | Total Beneficiaries | Remarks |
|  |  |  |  |  |  |  |  |  |  | % | Picture (if any) |  |  |
| 1 |  | Build capacity of revenue collectors and managers and Data collection on Temporal Structures within the District (Statistics) | Economic Development | 8,958.00 | IGF/Donor (FoN) | May-2024 | Aug-2024 | 7,264.00 | 1,704.00 | 100% |  | Districtwide | Completed |
| 2 |  | Procure revenue collection and management logistics | Economic Development | 23,000.00 | IGF | 05/05/2022 | 13/12/2024 | 18,500.00 | 4,500 | 100% |  | 25 | Completed |
| 3 |  | Resource and empower the Revenue Mobilisation task force | Economic Development | 5,000.00 | IGF | 03/02/2024 | 16/11/2024 | 5,000.00 | 0 | 100% |  | 25 | On-going |
| 4 |  | Organize public sensitization on revenue mobilization of the Assembly | Economic Development | 5,000.00 | IGF | 17/01/2024 | 05/12/2024 | 5,000.00 | - | 100% |  | 25 | Completed |
| 5 |  | Organize Annual Public Forum on tax compliance | Economic Development | 10,000.00 | IGF | 23/11/2024 | 28/11/2024 | 10,000.00 | - | 100% |  | 40 | Completed |
| 6 |  | Training of Area Council Executives on Revenue Mobilization | Economic Development | 30,000.00 | DACF | 15/03/2024 | 14/10/2024 | 20,000.00 | 10,000.00 | 100% |  | 32 | Completed |
| 7 |  | Conduct Radio Sensitization on Revenue Mobilization and Performance of the Assembly | Economic Development | 5,000.00 | IGF | 01/06/2024 | 21/12/2024 | 5,000.00 | - | 100% |  | District Wide | Completed |
| 8 |  | Play Revenue Jingles on various Community Information Centres | Economic Development | 1,500.00 | IGF | 01/12/2022 | 31/12/2024 | 1,500.00 | - | 100% |  | District Wide | Completed |
| 9 |  | Implement the GIFMIS System and introduce sanctions(bye laws) | Economic Development | 8,000.00 | IGF | 02/12/2022 | 30/12/2024 | 8,000.00 | - | 100% |  | District Wide | Completed |
| 10 |  | Mount revenue performance and accountability bill boards | Economic Development | 4,000.00 | IGF/Donor (FoN) | 02/02/2023 | 23/09/2024 | 4,000.00 |  | 100% |  | RATE PAYERS | completed |
| 11 |  | Provide incentives to revenue collectors | Economic Development | 3,000.00 | IGF | 02/02/202 | 19/12/2024 | 3,000.00 |  | 100% |  | RATE PAYERS | Completed |
| 12 |  | Encourage and enhance the security of transactions on mobile money | Economic Development | 6,000.00 | Donor (FoN) | 02/02/2024 | 17/12/2024 | 6,000.00 | - | 100% |  | 6 Area councils | completed |
| 13 |  | Organize Local Economic Development (LED) Committee meetings. | Economic Development | 24,000 | IGF | 09/02/2024 | 23/11/2024 | 24,000.00 |  | 100% |  | 11 | Completed |
| 14 |  | Develop a database of trained apprentices and artisans within the District | Economic Development | 5,000.00 | Donor ( Master Card Foundation) | 07/06/2024 | 16/11/2024 | 5,000.00 |  | 100% |  | 105 | On-going |
| 15 |  | Establish marketing links between producers and buyer companies | Economic Development | 4,200.00 | IGF | 17/08/2022 | 17/08/2024 | 4,200.00 | - | 100% |  | 12 | Completed |
| 16 |  | Organize trade exhibition shows for SMEs | Economic Development | 2,000.00 | IGF | 03/10/2024 | 17/11/2024 | 2,000.00 | - | 100% |  | 54 | Completed |
| 17 |  | Establish a District Apprentice Recruitment Agency (SDG Target 17.18) | Economic Development | - | 0 | 05/05/2024 | 0 | - |  | 0 |  | 0 | On going |
| 18 |  | Establish a Modern Industrial Park | Economic Development | 100,000.00 | Donor (Free Zone) |  |  | 0.00 | - | 3% |  | District Wide | On-going |
| 19 |  | Train Artisans on the manufacturing of “cook stoves” | Economic Development | 10,000.00 | IGF/Donor (HURDs) | 08/10/2024 | 08/10/2024 | 10,000.00 |  | 100% |  | 50 | Completed |
| 20 |  | Strengthen SMEs capacities for enhanced operations (e.g. Soap making, baking, wielding, hairdressing, etc.) | Economic Development | 5,000.00 | IGF | 09/10/2024 | 16/09/2024 | 5,000.00 | - | 100% |  | 70 | Completed |
| 21 |  | Promote the formation of “ Village Savings and Loans Associations (VSLA) | Economic Development | 2,000.00 | IGF | 24/07/2022 | 23/12/2024 | 2,000.00 | - | 100% |  | 105 | Completed |
| 22 |  | Collaborate with Financial Agencies to provide soft loans to Small and Medium Scale Businesses | Economic Development | 10,000.00 | DACF | 08/10/2022 | 09/07/2024 | 10,000.00 | - | 100% |  | 40 | Completed |
| 23 |  | Establish a District Local Economic Development (LED) Platform. | Economic Development | 5,000.00 | IGF | 15/06/2024 | 17/11/2024 | 5,000.00 | - | 100% |  | 108 | Completed |
| 24 |  | Support Businesses to form Vibrant Groups, Cooperatives and Local Partnership | Economic Development | 2,000.00 | DACF | 02/09/2022 | 17/11/2024 | 2,000.00 |  | 100% |  | 250 | Completed |
| 25 |  | Create and maintain a one stop shop data base for all businesses in the District | Economic Development | 8,000.00 | Master Card Foundation | 08/10/2022 | 12/07/2024 | 7,000.00 | 1,000.00 | 89% |  | 239 | On-going |
| 26 |  | Assist Small and Medium enterprises to develop business proposals and link them to Financial Sources. | Economic Development | 5,430.00 | Donor (FoN) | 01/07/2022 | 30/09/2024 | 5,430.00 |  | 76% |  | 46 | On-going |
| 27 |  | Conduct yield studies on selected crops (rice, maize, cassava and plantain) | Economic Development | 0 | CSIR Sekondi Agric Regional Office | 04/04/2024 | 14/11/2024 | - | - | Successfully implemented |  | 24 Rice farmers (Whin-Valley, Anto) | Completed |
| 28 |  | Conduct demonstration and field days on improved technologies | Economic Development | 2,345.00 | MAG | Jan-24 | Dec-24 | 2,345.00 |  | 100 |  | District Farmers | Completed |
| 29 |  | Conduct regular farm and home visits to operational areas and facilitate activities on PJF, RFJ, PERD | Economic Development | 1,800.00 | MAG | 04/01/2024 | 31/12/2024 | 1,800.00 | - | Successfully implemented by (II) field officers |  | 2,000 farmers visited for the period January,February, March, 2023 | Completed |
| 30 |  | Organize campaign on Rabies, PPR, NCD and Gambro for local birds and vaccinations | Economic Development | 4,000.00 | USAID (break through) | 24/07/2024 | 03/11/2024 | 4,000.00 | - | Successfully implemented |  | 1) 262 dogs vaccinated 2) 15 cats vaccinated | Completed |
| 31 |  | Build capacity of livestock farmers on livestock management and IMO Technology | Economic Development | 5,046.00 | MAG | JAN.2024 | 01/12/2024 | 5,046.00 | 0 | 100% |  | livestock farmers | Completed |
| 32 |  | Ensure efficient system for pre-mix distribution | Economic Development | 0.00 | 0 | 01/01/2024 | 01/12/2024 | 0.00 | 0 | 100% |  |  | Completed |
| 33 |  | Supply of improved fish smoking facilities (Ahotor Ovens) at subsidized prices | Economic Development | 42,000.00 | IGF | Jan-24 | Dec-24 | 27,000.00 | 15,000.00 | 53% |  | Districtwide Fish Morngers | on-going |
| 34 |  | Train fish smokers on the usage and maintenance of Ahotor ovens | Economic Development | 6,000.00 | IGF | Jan-24 | Dec-24 | 6,000.00 | 0 | 100 |  | Districtwide Fish Smokers | Completed |
| 35 |  | Educate fisher folks on proper fish handling and management as well as bad fishing practices | Economic Development | 2,000.00 | IGF | 6TH MARCH,2024 | 16TH MARCH,20234 | 2,000.00 | 0.00 | 65 % |  | 308 FISHERFOLKS,234-MALES, 234-FEMALES WERE ENGAGED ACROSS THE FISHING COMMUNITIES IN THE DISTRICT. | On-going |
| 36 |  | Sensitize fisher-folks on healthy fish handling, illegal fishing and post-harvest loses and management | Economic Development | 2,000.00 | IGF | 7th MARCH,2024 | 7th MARCH,20234 | 2,000.00 |  | 100% |  | 6 coastal Communitoes | Completed |
| 37 |  | Update Database on Fishermen and fish vessels | Economic Development | 2,000.00 | IGF | 16TH-JULY,2024 | 30TH-JULY,2024 | 2,000.00 | 0.00 | 78% |  | 154 - NEW CANOES/VESSELS WERE REGISTERED IN THREE FISHING COMMUNITIES. THE CANOE REGISTER BOOK MUST BE VALIDATED. THERE ARE GHOST NAMES. | On-going |
| 38 |  | Facilitate the elections of landing beaches executives | Economic Development | 2,000.00 | IGF | 23/08/2024 | 23/08/2024 | 2,000.00 |  | 100% |  | Coastal communities | Completed |
| 39 |  | Establish a Modern Commercial Fish Market | Economic Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Yet to start |
| 40 |  | Organize Accountability Forum for Landing Beaches | Economic Development | 2,000.00 | IGF | 23/08/2024 | 23/08/2024 | 2,000.00 |  | 100% |  | Coastal communities | Completed |
| 41 |  | Document all landing beaches in the District. | Economic Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Completed |
| 42 |  | Promote public-private partnerships for investment in the tourism (SDG Target 17.17) | Economic Development | 0 | Donor (CoDA) | 02/03/2024 | 16/11/2024 | - | - | 28% |  | 0 | On-going |
| 43 |  | Develop available and potential sites to meet international standards and promote local tourism and (SDG Target 8.9) | Economic Development | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | Yet to start |
| 44 |  | Develop a comprehensive database on all tourist sites | Economic Development | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | Completed |
| 45 |  | Promote “culture” as a tourist attraction | Economic Development | 0 | 0 | 02/03/2024 | 16/11/2024 | 0 | 0 | 0 |  | 0 | Completed |
| 46 |  | Facilitate the training of tourist guides and other personnel in tourism and hospitality management | Economic Development | 0 | 0 | 02/03/2024 | 16/11/2024 | 0 | 0 | 0 |  | 0 | Completed |
| 47 |  | Develop Shama Estuary | Economic Development | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | Yet to start |
| 48 |  | Partner the Private Sector to Develop Beach Resorts along the Coast | Economic Development | 0 | Donor(CoDA) | 02/03/2023 | 16/11/2024 | - | - | 23% |  | 0 | On-going |
| 49 |  | Conferences, Workshops and Seminars for Director of Education | Social Development | 8,000.00 | Ministry of Education (MOE) | Jan-24 | August, 2024 | 8,000.00 | 0 | 100% |  | District Education Directorate | Completed |
| 50 |  | Provide adequate resources for Administrative Expenses (Stationery Utilities & Fuel) | Social Development | 20,000.00 | Ministry of Education (MOE) | Jan-24 | DEC,2024 | 20,000.00 | 0 | 100% |  | District Education Directorate | Completed |
| 51 |  | Conduct District SPAM | Social Development | 5,000.00 | Ministry of Education (MOE) | Jan-24 | DEC,2024 | 5,000.00 | 0 | 100% |  | All schools Distritwide | Completed |
| 52 |  | Conduct regular monitoring and inspection of schools (private and public) and monitor educational delivery programs | Social Development | 12,000.00 | Ministry of Education (MOE) | Jan-24 | DEC,2024 | 12,000.00 | 0 | 100% |  | All schools Distritwide | Completed |
| 53 |  | Organize enrolment drive in communities | Social Development | 12,000.00 | Ministry of Education (MOE) | Jan-24 | DEC,2024 | 12,000.00 | 0 | 100% |  | All schools Distritwide | Completed |
| 54 |  | Conduct frequent and Intermittent monitoring, visits to beneficiary schools of the school feeding Program (SFP) | Social Development | 3,000.00 | Ministry of Education (MOE) | FEB, 2024 | DEC,2024 | 3,000.00 | 0 | 100% |  | All schools Distritwide | Completed |
| 55 |  | Organize competition in spelling, reading and numeracy | Social Development | 5,000.00 | Ministry of Education (MOE)/DACF | Jun-24 | June, 2024 | 5,000.00 | 0 | 100% |  | 7 selcted schools | Completed |
| 56 |  | Organize “My first day at school” ceremony in all KG and Primary one schools | Social Development | 4,000.00 | DACF | Jan-24 | Jan-24 | 4,000.00 | 0 | 100% |  | Selected basic schools | Completed |
| 57 |  | Organize Independence Day Celebration and debate | Social Development | 120,000.00 | DACF/IGF | 06/03/2024 | 06/03/2024 | 120,000.00 | 0 | 100% |  | Six Area Councils | Completed |
| 58 |  | Organization of District Mock for all final year pupils in JHS 3 | Social Development | 4,000 | DACF/IGF | April, 2024 | MAY, 2024 | 4,000 | 0 | 100% |  | all JHS Districtwide | Completed |
| 59 |  | Organize DEOC Meetings | Social Development | 10,000.00 | DACF/IGF | MARCH, 2024 | Oct-24 | 10,000.00 | 0 | 100% |  | 12 | Completed |
| 60 |  | Organize Sports and Cultural Activities at District and Regional level | Social Development | 5,000.00 | DACF/IGF | MARCH, 2024 | Oct-24 | 5,000.00 | 0 | 100% |  | All schools Districtwide | Completed |
| 61 |  | Procurement, supply and embossment of 320 No. Hexagonal tables and 1920 chairs for Schools in Shama District | Social Development | 400,000.00 | DACF-RFG | APRIL, 2024 | Oct-24 | 415,800.00 | 0 | 100% |  | All schools | Completed |
| 62 |  | Organize Regional Science & Maths Clinic (STMIE) | Social Development | 8,000.00 | DACF | April, 2024 | June, 2024 | 8,000.00 | 0 | 100% |  | 6 students | Completed |
| 63 |  | Provide Scholarship to needy but brilliant students across the District | Social Development | 50,000.00 | DACF | Jan-24 | Nov-24 | 50,000.00 | 0 | 100% |  | 20 | Completed |
| 64 |  | Support girls by providing a life-skills development programs | Social Development | 3,000.00 | Donor (Hurds Foundation) | Jun-24 | Aug-24 | 3,000.00 | 0 | 100% |  | 25 GIRLS | Completed |
| 65 |  | Form gender clubs in schools and communities | Social Development | 2,000.00 | Donor (Gender in Focus) | Jun-24 | Aug-24 | 2,000.00 | 0 | 100% |  | 8 schools | Completed |
| 66 |  | Organize Community sensitization on Back to School / Re-Entry Policy. | Social Development | 6,000.00 | Donor (Hurds Foundation) | Jan-24 | Mar-24 | 6,000.00 | 0 | 100% |  | 10 communities | Completed |
| 67 |  | Equitable distribution of health workforce | Social Development | 8,000 | MOH | Jan-24 | Dec-24 | 8,000 | 0 | 100% |  |  | Completed |
| 68 |  | Train indigines of Shama District in health disciplines to augment workforce | Social Development | 1,000 | MOH | Jan-24 | Dec-24 | 1,000 | 0 | 100% |  |  | Completed |
| 69 |  | Procure health equipment for various health facilities | Social Development | 40,000 | MOH | Jan-24 | Dec-24 | 20,000 | 20,000 | 70% |  | Health Facilities Districtwide | On-going |
| 70 |  | Procure pick-ups for all sub districts and District Health Directorate | Social Development | 0 | 0 | Jan-24 | Dec-24 | 0 | 0 | 0 |  |  | Yet-to-start |
| 71 |  | Procure motorbikes for all health facilities | Social Development | 50,000 | 0 | Jan-24 | Dec-24 | 0 | 0 |  |  |  | Yet-to-start |
| 72 |  | Provide family services | Social Development | 2,000.00 | MOH | Jan-24 | Dec-24 | 2,000.00 | 0 | 100% |  | DistrictWide | Completed |
| 73 |  | Establish adolescent clubs in schools and communities | Social Development | 2,000.00 | Donor (Hurds Foundation) | Jan-24 | Dec-24 | 2,000.00 |  | 100% |  | four basic schools | Completed |
| 74 |  | Organize Stakeholders meeting at NHIA | Social Development | 20,000.00 | NHIA | Jan-24 | Dec-24 | 20,000.00 | 0 | 100% |  | 120 | Completed |
| 75 |  | Registration of LEAP members | Social Development | 0 | NHIA | Jan-24 | Dec-24 | 0 | 0 | 100% |  | 56 | Completed |
| 76 |  | Registration school children on NHIS scheme | Social Development | 0 | NHIA | Jan-24 | Dec-24 | 0 | 0 | 100% |  | 600 | Completed |
| 77 |  | Radio Education on NHIS | Social Development | 3,000.00 | NHIA | Jan-24 | Dec-24 | 3,000.00 | 0 | 100% |  | Districtwide | Completed |
| 78 |  | Community Sensitization/Registration on NHIS | Social Development | 5,000.00 | NHIA | Jan-24 | Dec-24 | 5,000.00 | 0 | 100% |  | Districtwide | Completed |
| 79 |  | Establish Community Wellness Corners | Social Development | 0.00 | MOH/DACF | Jan-24 | Dec-24 | 0.00 | 0 |  |  | Districtwide | Yet-to-start |
| 80 |  | Organize District wide Health Screening | Social Development | 15,000.00 | MOH/DACF | Jan-24 | Dec-24 | 15,000.00 | 0.00 | 100% |  | Districtwide | Completed |
| 81 |  | Procure weighing scales and infantometers for facilities | Social Development | 40,000 | MOH/DACF | Jan-24 | Dec-24 | 30,000 | 10,000.00 | 80% |  | Districtwide | On-going |
| 82 |  | Procure medicines for Health facilities | Social Development | 30,000 | MOH/DACF | Jan-24 | Dec-24 | 30,000 | 0.00 | 100% |  | Districtwide | Completed |
| 83 |  | conduct monitoring and supervision to facilities | Social Development | 8,000.00 | MOH/DACF | Jan-24 | Dec-24 | 8,000.00 | 0 | 100% |  | Districtwide health facilities | Completed |
| 84 |  | construct a standard DHMT Offices | Social Development | 0.00 | 0.00 | Jan-24 | Dec-24 | 0.00 | 0.00 |  |  |  | Yet-to-start |
| 85 |  | Operationalize the District Health committee and Community Health Management Committees | Social Development | 3,000 | MOH/DACF | Jan-24 | Dec-24 | 3,000 | 0 | 100% |  | Districtwide health facilities | Completed |
| 86 |  | Train health staff | Social Development | 20,000.00 | MOH | Jan-24 | Dec-24 | 20,000.00 | 0 | 100% |  | 42 nurses | Completed |
| 87 |  | Procure vaccines fridges and Freezers | Social Development | 25,000.00 | MOH/DACF | Jan-24 | Dec-24 | 15,000 | 10,000 | 85% |  | Districtwide health facilities | On-going |
| 88 |  | Conduct TB screening in communities | Social Development | 6,000.00 | DONOR(RAAF) | Jan-24 | Dec-24 | 6,000.00 | 0 | 100 |  | 50 | Completed |
| 89 |  | Distribute LLINs to vulnerable groups | Social Development | 2,000.00 | MOH | Jan-24 | Dec-24 | 2,000.00 | 0 | 100% |  |  | Completed |
| 90 |  | Conduct health education on Radio | Social Development | 2,000.00 | MOH/DACF | Jan-24 | Dec-24 | 2,000.00 | 0 | 100% |  | Districtwide | Completed |
| 91 |  | Train community information centre | Social Development | 7,000 | DACF | Jan-24 | Dec-24 | 7,000 | 0 | 100% |  | Districtwide | Completed |
| 92 |  | Print Health education materials | Social Development | 2,000.00 | MOH | Jan-24 | Dec-24 | 2,000.00 | 0 | 100% |  | Districtwide | Completed |
| 93 |  | Quarterly HIV/TB Review meetings | Social Development | 12,000.00 | DACF (MSHAP) | Jan-24 | Dec-24 | 12,000.00 | 0 | 100% |  | Districtwide | Completed |
| 94 |  | Half yearly DAC meetings | Social Development | 6,000.00 | DACF (MSHAP) | Jan-24 | Dec-24 | 6,000.00 | 0 | 100% |  | Districtwide | Completed |
| 95 |  | Conduct Quarterly DRMT Meeting | Social Development | 6,000.00 | DACF (MSHAP) | Jan-24 | Dec-24 | 6,000.00 | 0 | 100% |  | Districtwide | Completed |
| 96 |  | Assist in mobilization for HIV Activities | Social Development | 6,000.00 | DACF (MSHAP) | Jan-24 | Dec-24 | 6,000.00 | 0 | 100% |  | Districtwide | Completed |
| 97 |  | Activate Dormant HIV Alert schools and monitor their activities | Social Development | 0 | HIV FUNDS | Jan-24 | Dec-24 | 0 | 0 | 100% |  | Districtwide | Completed |
| 98 |  | Expand and intensify HIV Counselling and Testing (HTC) programs in the District (SDG Targets 3.3, 3.7 | Social Development | 5,000.00 | DACF | Jan-24 | Dec-24 | 5,000.00 | 0 | 100% |  | Districtwide | Completed |
| 99 |  | Organize quarterly Monitoring exercise on activities of HIV Related NGOs in the District. | Social Development | 6,000.00 | DACF | Jan-24 | Dec-24 | 6,000.00 | 0 | 100 |  | 15 | Completed |
| 100 |  | Train SHEP Coordinators and selected Teachers on HIV | Social Development | 0 |  | Jan-24 | Dec-24 | 0 | 0 | 100 |  | 15 | Completed |
| 101 |  | Identify HIV Champions in schools | Social Development | 0 |  | Jan-24 | Dec-24 | 0 | 0 | 100 |  | 15 | Completed |
| 102 |  | Organize Community sensitization on Mother to Child infection | Social Development | 12,720.00 | DONOR (RAAF) | Jan-24 | Dec-24 | 12,720.00 | 0 | 100 |  | 10 MOTHERS | Completed |
| 103 |  | Playing of jingles on community Information Centres in the District | Social Development | 2,000.00 | DACF | Jan-24 | Dec-24 | 2,000.00 | 0 | 100 |  | Districtwide | Completed |
| 104 |  | Celebration of World AIDS Day | Social Development | 2,000.00 | RAAF | Jan-24 | Dec-24 | 2,000.00 | 0 | 100 |  | Districtwide | Completed |
| 105 |  | Organize stakeholders Consultations on HIV | Social Development | 5,289.00 | DACF | Jan-24 | Dec-24 | 5,289.00 | 0 | 100 |  | Districtwide | Completed |
| 106 |  | Provide support to voluntary care supporters of PLHIV | Social Development | 7,000.00 | IGF/DACF | Jan-24 | Dec-24 | 7,000 | 0 | 100% |  | 17 | Completed |
| 107 |  | Conduct Assessment of People nominated by PLHIV | Social Development | 3,000.00 | RAAF | Jan-24 | Dec-24 | 3,000 | 0 | 100 |  | 29 | Completed |
| 108 |  | Organized education and sensitization on Nutrition (SDG 2.1, 2.2) | Social Development | 3,000.00 | RAAF | Jan-24 | Dec-24 | 3,000 | 0 | 100 |  | 29 | Completed |
| 109 |  | Conduct awareness on the importance of family planning and birth spacing | Social Development | 7,000 | UNICEF | Jan-24 | Dec-24 | 7,000.00 | 0 | 100 |  | 320 | Completed |
| 110 |  | Organize education in schools, hospitals and communities on birth and death registration | Social Development | 5,000.00 | IGF/DACF | Jan-24 | Dec-24 | 5,000 | 0 | 100 |  | 10 Basic Schools and 1 SHS | Completed |
| 111 |  | Conduct annual mobile registration | Social Development | 3,000.00 | SDA/ GOG | Jan-24 | Dec-24 | 5,000.00 | 4,000.00 | 90% |  | Districtwide | On-going |
| 112 |  | Conduct Mobile registration (child health promotion week | Social Development | 2, 000.00 | SDA/ GOG | Jan-24 | Dec-24 | 2,000.00 | 0.00 | 100 |  | Districtwide | Completed |
| 113 |  | Desilt choked drains and gutter in the communities | Social Development | 12000 | IGF/DACF | Jan-24 | Dec-24 | 12000 | 0 | 100 |  | All major drains districtwide | Completed |
| 114 |  | Evacuate and Push 10 refuse heaps sites | Social Development | 35,500 | IGF/DACF | Jan-24 | Dec-24 | - | - | 100 |  | Districtwide | Completed |
| 115 |  | Purchase of 15no. refuse containers | Social Development | 68,000 | DACF | Jan-24 | Dec-24 | - | - | 100 |  | Districtwide | Completed |
| 116 |  | Supervise activities of waste management contractors in the District | Social Development | 1,000 | IGF | Jan-24 | Dec-24 | - | - | 100 |  | Districtwide | Completed |
| 117 |  | To sensitize landlords on provision of household latrines. | Social Development | 500 | IGF | Jan-24 | Dec-24 | - | - | 100 |  | District Wide | Completed |
| 118 |  | Organize Community Clean-up activities across the District | Social Development | 5,000 | IGF | Jan-24 | Dec-24 | 5,000 | 0 | 100 |  | District Wide | Completed |
| 119 |  | Train Community Water and Sanitation Board members | Social Development | 3,000 | IGF | Jan-24 | Dec-24 | 3000 | 0 | 100 |  | Members of Water and Sanitation board | Completed |
| 120 |  | Public education on proper food handling & medical screening | Social Development | 500 | IGF | Jan-24 | Dec-24 | - | - | 100 |  | Districwide | Completed |
| 121 |  | To educate the public on the dangers of stray animals | Social Development | - | - | Jan-24 | Dec-24 | - | - | 100 |  | Districwide | Completed |
| 122 |  | Organize Public education on Proper waste management and Public cleansing | Social Development | - | - | Jan-24 | Dec-24 | - | - | 100 |  | Districwide | Completed |
| 123 |  | Scale-up sensitization campaigns to promote proper handwashing and hygiene practices particularly among children (SDGs Target 6.2) and Train caterers of SFP on hygienic and nutritious preparation of food | Social Development | - | - | Jan-24 | Dec-24 | - | - | 100% |  | Districwide | Completed |
| 124 |  | Enforce building regulation (including accessibility standards for PWDs) on the provision of toilet facilities in all homes | Social Development | - | - | Jan-24 | Dec-24 | - | - | 100% |  | Districwide | Completed |
| 125 |  | Organize community engagements and behavioural change campaigns to promote positive parenting attitudes and practices among parents and caregivers | Social Development | 2500 | UNICEF/SDA | Jan-24 | Dec-24 | 2500 | 0 | 100 |  | 368 | Completed |
| 126 |  | Sensitize communities/schools in the District on Gender Based Violence etc. (child Protection Toolkit) and Child Protection issues such as drug abuse, child abuse, child trafficking, etc. | Social Development | 1800 | DACF | Jan-24 | Dec-24 | 1800 | 0 | 100 |  | 306 | Completed |
| 127 |  | Collaborate with the relevant state institutions i.e. Police, Courts etc. on child related issues | Social Development | 0 | DACF | Jan-24 | Dec-24 | 0 | 0 | 100% |  | 0 | Completed |
| 128 |  | Train caregivers on the Standards Operating Procedures of the Department. | Social Development | 5,000 | DACF | Jan-24 | Dec-24 | 5000 | 0 | 100 |  | 7 caregivers | Completed |
| 129 |  | Organize Homes, Schools, Markets and Lorry Parks visits to identify Children of school drop outs who loiter and reinstate them in school. | Social Development | 4,000.00 | DACF | Jan-24 | Dec-24 | 4,000 | 0.00 | 100% |  | Districtwide | Completed |
| 130 |  | Organize Public sensitization on child labour issues (Celebration of World Day Against Child Labour) | Social Development | 2500.00 | DACF | Jan-24 | Dec-24 | 2,500.00 | 1,000.00 | 100% |  | Districtwide | Completed |
| 131 |  | Create Data on children in child labour, teenage mothers and school drop outs | Social Development | 4,000.00 | DACF | Jan-24 | Dec-24 | 4,000 | 0 | 100% |  | Districtwide | Completed |
| 132 |  | Create awareness on teenage Pregnancy in schools | Social Development | 2,000.00 | DACF | Jan-24 | Dec-24 | 2,000.00 | 0 | 100% |  | Districtwide | Completed |
| 133 |  | Institute child protection committees in all communities | Social Development | 3,000 | DACF | Jan-24 | Dec-24 | 3,000 | 0 | 100% |  | Districtwide | Completed |
| 134 |  | Create/update database for the aged in the district | Social Development | - | - | Jan-24 | Dec-24 | - | - | 100% |  | Districwide | Completed |
| 135 |  | Increase education and advocacy on Sexual and Gender-Based Violence and other Harmful Cultural Practices | Social Development | 7,000 | UNICEF/SDA | Jan-24 | Dec-24 | 7000 | 0 | 100% |  | 167 | Completed |
| 136 |  | Increase the advocacy of women in political participation | Social Development | 5,000 | UNICEF/SDA | Jan-24 | Dec-24 | 5000 | 0 | 100% |  | Districtwide | Completed |
| 137 |  | Organise skills training in income-generating activities for vulnerable women (SDG Targets 3.8, 4.5) | Social Development | 4000 | UNICEF/SDA | Jan-24 | Dec-24 | 4000 | 0 | 100% |  | Districtwide | Completed |
| 138 |  | Encourage women artisans and other tradespeople, including farmers, to form associations to facilitate their access to information and other support (SDG Targets 1.4, 5.c) | Social Development | 8,325 | DACF | Jan-24 | Dec-24 | 8,325 | 0 | 100% |  | Districtwide | Completed |
| 139 |  | Build the Capacity of DPCU on gender-responsive budgeting and financing (SDG Target 5.c) | Social Development | 4,200.00 | Donor(Hurds Foundation) | Jan-24 | Dec-24 | 4,200.00 | 0 | 100% |  | DPCU Members | Completed |
| 140 |  | Build capacity of sports managers, trainers, and trainees (SDG Target 16.6) | Social Development | 4,200.00 | Donor(Hurds Foundation) | Jan-24 | Dec-24 | 4,200.00 | 0 | 100% |  | Lower Pra PLC | Completed |
| 141 |  | Promote less-recognised sports (SDG Targets 1.a, 17.3) | Social Development | 0 | Donor(Hurds Foundation) | Jan-24 | Dec-24 | 0 | 0 | 100% |  | Lower Pra PLC | Completed |
| 142 |  | Organise Annual domestic competitive sporting events in the District (SDG Target 16.6) | Social Development | 10,000.00 | Donor(Hurds Foundation) | Jan-24 | Dec-24 | 4,200.00 | 0 | 100% |  | Lower Pra PLC | Completed |
| 143 |  | Provide adequate logistics and equipment for sports competition in the District (SDG Target 9.1) | Social Development | 7,500.00 | Donor(Hurds Foundation) | Jan-24 | Dec-24 | 4,200.00 | 0 | 100% |  | SDA | Completed |
| 144 |  | Promote formation of sports clubs and academies in all communities (SDG Target 4.7) | Social Development | 5,000 | MOE/IGF | Jan-24 | Dec-24 | 5,000 | 0 | 100% |  | Didtrictwide | Completed |
| 145 |  | Organize District Sports Committee Meetings | Social Development | 5,000 | MOE/IGF | Jan-24 | Dec-24 | 5,000 | 0 | 100% |  | Sport Committee Members | Completed |
| 146 |  | Participate in Regional Sports activities | Social Development | 6,000.00 | MOE/IGF | Jan-24 | Dec-24 | 6,000.00 | 0 | 100% |  | District Sport Team | Completed |
| 147 |  | Provide Skills and Entrepreneurship training for the youth | Social Development | 6,000.00 | MOE/IGF | Jan-24 | Dec-24 | 6,000.00 | 0 | 100% |  | Districtwide | Completed |
| 148 |  | Institute measures to reclaim lands earmarked for sporting and recreational activities (SDG Target 9.1) | Social Development | 0 | Donor(Hurds Foundation) | Jan-24 | Dec-24 | 0 | 0 | 100% |  | SDA | Completed |
| 149 |  | Develop and implement apprenticeship and employable skill training for out-of-school youth and graduates (SDG Targets 4.4, 8.6) | Social Development | 6,000.00 | DACF | Jan-24 | Dec-24 | 6,000.00 | 5,000.00 | 90% |  | Districtwidw | On-going |
| 150 |  | Support the youth to participate in modern and climate-smart agriculture (SDG Target 8.6) | Social Development | 2,000.00 | Donor (MAG) | Jan-24 | Dec-24 | 2,000.00 | 0 | 100 |  | 7 | Completed |
| 151 |  | Promote youth participation in all forms of creativity and innovative activities of the Assembly | Social Development | 0 | RAAF | Jan-24 | Dec-24 | 0 | 0 | 100% |  | Planning Unit | Completed |
| 152 |  | Encourage the formation of Community base Organizations to enhance community Development | Social Development | 0 | RAAF | Jan-24 | Dec-24 | 0 | 0 | 100% |  | Planning Unit | Completed |
| 153 |  | Strengthen and expand the coverage of existing social protection programmes to include all vulnerable people (SDG Target 1.3, 5.4, 10.4) | Social Development | 1000 | SDA | Jan-24 | Dec-24 | 1000 | 0 | 100 |  | 231 | Completed |
| 154 |  | Organise public /Radio sensitisation against stigma, abuse, discrimination, and harassment of vulnerable people (SDG Targets 16.2, 16.3, 16.b | Social Development | 162,936.00 | DACF | Jan-24 | Dec-24 | 113,000.00 | 8936 | 100 |  | 62 | Completed |
| 155 |  | Support People with Disabilities (PWDs) with items/cash, school fees and medical bills | Social Development | 28,000.00 | DACF | Jan-24 | Dec-24 | 28,000.00 | 0 | 78% |  | 24 PWDs | On-going |
| 156 |  | Organized Durbars to support PWDs | Social Development | 7500 | DACF | Jan-24 | Dec-24 | 7,500.00 | 0 | 100 |  | 62 | Completed |
| 157 |  | Monitor the activities of PWDs supported | Social Development | 0 | DACF | Jan-24 | Dec-24 | 0 | 0 | 100 |  | 62 | Completed |
| 158 |  | Identify and register PWDs in the District. | Social Development | 12,000 | SDA | Jan-24 | Dec-24 | 12,000 | 0 | 100 |  | 26 | Completed |
| 159 |  | Organize Social Services Sub Committee Meeting | Social Development | 5,000 | DACF | Jan-24 | Dec-24 | 5,000 | 0 | 100% |  | Social Service Subcommittee members | Completed |
| 160 |  | Sensitize citizens and organisations on eradication of disability-related discrimination | Social Development |  | Unicef | Jan-24 | Dec-24 | 7,432.00 | 0 | 100 |  | Districtwide | Completed |
| 161 |  | Procure Logistics for Social Welfare Department | Social Development | 10,000.00 | Unicef | Jan-24 | Dec-24 | 7,432.00 | 0 | 100 |  | Districtwide | Completed |
| 162 |  | Sensitize and educate populace on land Degradation | Environment, Infrastructure And Human Settlement | 2,500.00 | Donor (FoN) | Jan-24 | Dec-24 | 2,500.00 | 0 | 100% |  | District wide | Completed |
| 163 |  | Encourage all schools in the District to plant trees | Environment, Infrastructure And Human Settlement | 4,500.00 | DACF, DONOR(FoN) | Jan-24 | Dec-24 | 4,500.00 | 0 | 100% |  | District wide | Completed |
| 164 |  | Reforest degraded lands | Environment, Infrastructure And Human Settlement | 0.00 | 0.00 | Jan-24 | Dec-24 | 0.00 | 0.00 | 0.00 |  | 0.00 | Yet to start |
| 165 |  | Strengthen involvement of local communities in the management of forests and wetlands (SDG Targets 6.a, 6b) | Environment, Infrastructure And Human Settlement | 0.00 | 0.00 | Jan-24 | Dec-24 | 0.00 | 0.00 | 0.00 |  | 0.00 | Yet to start |
| 166 |  | Ensure mining activities are undertaken in an environmentally sustainable manner (SDG Targets 6.5, 8.4, 12.2,) | Environment, Infrastructure And Human Settlement | 2,000 | IGF | Jan-24 | Dec-24 | 1500 | 500 | 80 |  | Selected communities | On-going |
| 167 |  | Ensure land reclamation after mining operations (SDG Targets 15.1, 15.3) | Environment, Infrastructure And Human Settlement | 5000 | IGF | Jan-24 | Dec-24 | 4000 | 1000 | 80 |  | Selected communities | On-going |
| 168 |  | Monitor the activities of quarry and sand wining industries | Environment, Infrastructure And Human Settlement | - | IGF | Jan-24 | Dec-24 | - | - | 76% |  | Selected communities | On-going |
| 169 |  | Establish Quarry Development Fund | Environment, Infrastructure And Human Settlement | 2,000.00 | DACF | Jan-24 | Dec-24 | 2,000.00 | 0 | 100% |  | District wide | Completed |
| 170 |  | Establish District Community Mining Scheme | Environment, Infrastructure And Human Settlement | 1,500.00 | Donor (FoN) | Jan-24 | Dec-24 | 1,500.00 | 0 | 100% |  | District wide | Completed |
| 171 |  | Organize Community Clean Up exercises within the Coastal areas | Environment, Infrastructure And Human Settlement | 1,000 | IGF | Jan-24 | Dec-24 | 1,000 | 8,00 | 80 |  | 5 Coastal Communities | On-going |
| 172 |  | Undertake tree planting along banks of all major water bodies and tributaries to reduce silting and pollution from human activities (SDG Targets 6.5, 6.6) | Environment, Infrastructure And Human Settlement | 5000 | IGF | Jan-24 | Dec-24 | 5000 | 3000 | 70 |  | Selected communities | On-going |
| 173 |  | Intensify public education on indiscriminate disposal of waste (SDG Target 11.6) | Environment, Infrastructure And Human Settlement | 1000 | IGF | Jan-24 | Dec-24 | 1000 | 1000 | 100% |  | Distrwide | Completed |
| 174 |  | Implement SHEP (Sanitation, Env. & Safety Systems) in Schools (SDG Targets 1.4, 7.1) | Environment, Infrastructure And Human Settlement | 6,000.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 6,000.00 | 0 | 100% |  | District wide | Completed |
| 175 |  | Public sensitization on climate change, SDGs & COVID – 19 | Environment, Infrastructure And Human Settlement | 5000.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 5,000.00 | 0 | 100% |  | District wide | Completed |
| 176 |  | Plant trees in Schools and embark on community garden project | Environment, Infrastructure And Human Settlement | 12,500.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 5,000.00 | 0 | 100% |  | District wide | Completed |
| 177 |  | Build the capacity of farmers on climate smart agricultural practices in collaboration with B-BOVID | Environment, Infrastructure And Human Settlement | 5,000 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 5,000 | 0 | 100% |  | 120 | Completed |
| 178 |  | Enhanced knowledge of farmers on mitigation and adaptation measures on climate change | Environment, Infrastructure And Human Settlement | 1,500.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 1,500.00 | 0 | 100% |  | 15 | Completed |
| 179 |  | Promote climate-resilience policies for women and other vulnerable groups in agriculture (SDG Targets 1.5, 13.1, 13.2, 13.b, 16.6) | Environment, Infrastructure And Human Settlement | - | IGF | Jan-24 | Dec-24 | - | 0 | 0 |  | 0 | Yet to Start |
| 180 |  | Develop climate-responsive infrastructure (SDG Target 9.1) | Environment, Infrastructure And Human Settlement | 6,500.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 4,500.00 | 2000 | 75% |  | 10 | Completed |
| 181 |  | Organize Radio Sensitization on climate change to minimize its impacts | Environment, Infrastructure And Human Settlement | 1,500.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 1,500.00 | 0 | 100% |  | District wide | Completed |
| 182 |  | Initiate Green District campaign with traditional authorities, civil society, religious bodies and other recognized groups (SDG Target 13.3) | Environment, Infrastructure And Human Settlement | - | IGF,DONOR(FON) | Jan-24 | Dec-24 | - | 0 | 100 |  | District wide | Completed |
| 183 |  | Organise Radio Sensitization on Disaster Risk Reduction Measures | Environment, Infrastructure And Human Settlement | 2,000.00 | Donor(FoN)/VRA | Jan-24 | Dec-24 | 1,000.00 | 1000 | 50% |  | District wide | Completed |
| 184 |  | Conduct Community Engagements on Disaster Risk Reduction Measures | Environment, Infrastructure And Human Settlement | 2,000.00 | Donor(FoN)/VRA | Jan-24 | Dec-24 | 1,500.00 | 500 | 75% |  | District wide | Ongoing |
| 185 |  | Form Disaster Volunteer’s Groups(DVGs) across the District | Environment, Infrastructure And Human Settlement | - | 0 | Jan-24 | Dec-24 | - | 0 | 100% |  | District wide | Completed |
| 186 |  | Build the Capacity of NADMO Staff , DVGs And Organized Groups on Disaster Management | Environment, Infrastructure And Human Settlement | 3,500.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 3,500.00 | 0 | 100% |  | 7 | Completed |
| 187 |  | Organise Weekly Zonal Field Trips on Disaster Assessment | Environment, Infrastructure And Human Settlement | 5,000.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 2,000.00 | 3000 | 45% |  | District wide | Completed |
| 188 |  | Organise District Disaster Management Committee Meetings | Environment, Infrastructure And Human Settlement | 1,500.00 | IGF,DONOR(FON) | Jan-24 | Dec-24 | 1,500.00 | 0 | 100% |  | 15 | Completed |
| 189 |  | Observe International Day For Disaster Risk Reduction (IDDRR) | Environment, Infrastructure And Human Settlement | - | 0 | Jan-24 | Dec-24 | - | 0 | 0% |  | 0 | Yet-to-start |
| 190 |  | Provide Relief Support to Disaster Victims And reconstruction | Environment, Infrastructure And Human Settlement | 18,000.00 | DACF | Jan-23 | Dec-24 | 18,000.00 | 18,000.00 | 100% |  | Anglo Beach Community | Completed |
| 191 |  | Strengthen the Assembly’s cooperation with Transport Unions | Environment, Infrastructure And Human Settlement | - | 0 | Jan-24 | Dec-24 | - | 0 | 100% |  | GPRTU/SDA | Completed |
| 192 |  | Promote and institutionalize knowledge, skills and attitudinal change programmes for transport sector personnel | Environment, Infrastructure And Human Settlement | - | 0 | Jan-24 | Dec-24 | - | 0 | 100% |  | GPRTU | Completed |
| 193 |  | Enforce road regulations | Environment, Infrastructure And Human Settlement | - | 0 | Jan-24 | Dec-24 | - | 0 | 100% |  | City Guards | Completed |
| 194 |  | Organize Road safety Campaigns | Environment, Infrastructure And Human Settlement | - | IGF,DONOR(FON) | Jan-24 | Dec-24 | - | 0 |  |  | 0 | Completed |
| 195 |  | Extend electricity supply | Environment, Infrastructure And Human Settlement | - | 0 | Jan-24 | Dec-24 | - | 0 | 100% |  | 0 | Completed |
| 196 |  | Enhance self-help electrification project (SHEP) and use means testing approaches to enable the poor to connect to the national grid (SDG Targets 1.4, 7.1) | Environment, Infrastructure And Human Settlement | - | 0 | Jan-24 | Dec-24 | - | 0 | 100% |  | 0 | Completed |
| 197 |  | Intensify the use of Geographic Information System (GIS) in spatial/land use planning at all levels | Environment, Infrastructure And Human Settlement | 4,000.00 | DACF | Jan-24 | Dec-24 | 4,000.00 | 3,000.00 | 85% |  | Districtwide | On-going |
| 198 |  | Undertake regular monitoring and sensitisation on spatial planning and management | Environment, Infrastructure And Human Settlement | 3,000.00 | IGF | Jan-24 | Dec-24 | 2,500.00 | 2,500.00 | 100% |  | Districtwide | Completed |
| 199 |  | Undertake field trips to disaster prone areas | Environment, Infrastructure And Human Settlement | 5,000.00 | DACF | Jan-24 | Dec-24 | 5,000.00 | 1,000.00 | 100% |  | Districtwide | Completed |
| 200 |  | Develop asset register on infrastructure conditions | Environment, Infrastructure And Human Settlement | - | GOG, DACF | Jan-24 | Dec-24 | - | - | 90% |  |  | On-going |
| 201 |  | Preparation of new planning schemes | Environment, Infrastructure And Human Settlement | - | GOG, DACF | Jan-24 | Dec-24 | - | 0 | 60% |  | Ohiamadwen,Assorko | On-going |
| 202 |  | Sensitization of Chiefs and Families on the need to sell lands in conformity with the planning schemes | Environment, Infrastructure And Human Settlement | - | IGF | Jan-24 | Dec-24 | - | 0 | 100% |  | Districtwide | Completed |
| 203 |  | Extension of Street Naming and Property addressing to selected communities (Ituma, Dwomo, Beposo,Anto,Komfueku, Asemasa No.1) | Environment, Infrastructure And Human Settlement | 10000 | GOG | Jan-24 | Dec-24 | 6000 | 6000 | 100% |  | Selected communities | On-going |
| 204 |  | Organize Monthly Tech-Sub Comm and Spatial Planning Committee meeting | Environment, Infrastructure And Human Settlement | 3000 | GOG, DACF | Jan-24 | Dec-24 | 2000 | 1000 | 100% |  | - | Completed |
| 205 |  | Document all Assembly Landed properties. | Environment, Infrastructure And Human Settlement | - | GOG, DACF | Jan-24 | Dec-24 | - | - | 0% |  | - | Completed |
| 206 |  | Develop District Geo Spatial | Environment, Infrastructure And Human Settlement | 5000 | GOG, DACF | Jan-24 | Dec-24 | 5000 | 0 | 100 |  | - | Completed |
| 207 |  | Ensure the production of base, topographic and orthophoto maps to cover the entire country (SDG Target 12.2) | Environment, Infrastructure And Human Settlement | - | DACF | Jan-24 | Dec-24 | - | - | 0 |  | - | Yet-to-start |
| 208 |  | Promote the production of reliable maps and site plans to ensure security of land tenure | Environment, Infrastructure And Human Settlement | - | DACF | Jan-24 | Dec-24 | - | - | 78% |  | - | Ongoing |
| 209 |  | Intensify education on rights and responsibilities of electorates | Governance, Corruption And Public Accountability | 3,986.00 | Donor (SCMMP) | Jan-24 | Dec-24 | 3,986.00 |  | 100% |  | Districtwide | Completed |
| 210 |  | Intensify public awareness on the need for equal gender at the Assembly | Governance, Corruption And Public Accountability | 3,986.00 | Donor (SCMMP) | Jan-24 | Dec-24 | 3,986.00 |  | 100% |  | Districtwide | Completed |
| 211 |  | Provide logistics/Office facilities for the Area councils- - computers and accessories | Governance, Corruption And Public Accountability | 5,832.00 | DACF | Jan-24 | Dec-24 | 3,784.00 | 2,048.00 | 67% |  | 4 Area Councils | On-going |
| 212 |  | Reconstitution of the Area Councils | Governance, Corruption And Public Accountability | 4,612.00 | Donor (CDD) | Jan-24 | Dec-24 | 4,612.00 |  | 100% |  | Area Council Members | Completed |
| 213 |  | Train Area Council members on Participatory Planning, Budgeting , M&E | Governance, Corruption And Public Accountability | 4,612.00 | Donor (CDD) | Jan-24 | Dec-24 | 4,612.00 |  | 100% |  | Area Council Members | Completed |
| 214 |  | Allocate District officers to manage the Area Councils | Governance, Corruption And Public Accountability | 0 | 0 | Jan-24 | Dec-24 | 0 | 0 | 100% |  | 4 Area Councils | Completed |
| 215 |  | Organize Meet the Press on Assembly programs and Achievements. | Governance, Corruption And Public Accountability | 0 | 0 | Jan-24 | Dec-24 | 0 | 0 | 100% |  | District wide | Completed |
| 216 |  | Organise DCEs Community Engagements | Governance, Corruption And Public Accountability | 60,000 | 0 | Jan-24 | Dec-24 | 0 | 0 | 100% |  |  | Completed |
| 217 |  | Organize stakeholders forum on development planning process and Budgeting | Governance, Corruption And Public Accountability | 7,436.00 | FoN | Jan-24 | Dec-24 | 7,436.00 | 0 | 100% |  | 272 | Completed |
| 218 |  | Conduct Monthly Radio Sensitization on Assembly program Implementation and Achievements | Governance, Corruption And Public Accountability | 3,000.00 | FoN | Jan-24 | Dec-24 | 3,000.00 | 0 | 100% |  | Districtwide | Completed |
| 219 |  | Organise quarterly DCEs engagement with the Public on Radio | Governance, Corruption And Public Accountability | 10,247.90 | FoN | Jan-24 | Dec-24 | 10,247.90 | 0 | 100% |  | Districtwide | Completed |
| 220 |  | Organize quarterly DPCU Meetings. | Governance, Corruption And Public Accountability | 12,845.00 | FoN | Jan-24 | Dec-24 | 12,845.00 | 0 | 100% |  | DPCU Members | Completed |
| 221 |  | Prepare Annual Action Plan | Governance, Corruption And Public Accountability | 6,794.00 | FoN | Jan-24 | Dec-24 | 6,794.00 | 0 | 100% |  | 0 | Completed |
| 222 |  | Prepare Annual Budgets | Governance, Corruption And Public Accountability | 14,893.00 | IGF/FoN | Jan-24 | Dec-24 | 14,893.00 | 0 | 100% |  | 0 | Completed |
| 223 |  | Conduct Review of Annual Action Plans | Governance, Corruption And Public Accountability | 6,794.00 | FoN | Jan-24 | Dec-24 | 6,794.00 | 0 | 100% |  | 0 | Completed |
| 224 |  | Conduct Review of Annual Budgets | Governance, Corruption And Public Accountability | 6,794.00 | FoN | Jan-24 | Dec-24 | 6,794.00 | 0 | 100% |  | 0 | Completed |
| 225 |  | Preparation of Procurement Plan | Governance, Corruption And Public Accountability | 4,986.00 | IGF | Jan-24 | Dec-24 | 4,986.00 | 0 | 100% |  | 0 | Completed |
| 226 |  | Organize Town Hall Meetings and Organise DCEs Community Engagements | Governance, Corruption And Public Accountability | 30,467.90 | FoN | Jan-24 | Dec-24 | 30,467.90 | 0 | 100% |  | Districtwide | Completed |
| 227 |  | Mount Accountability bill boards at the various Area Councils | Governance, Corruption And Public Accountability | 99,673.00 | FoN | Jan-24 | Dec-24 | 99,673.00 | 0 | 100% |  | Districtwide | Completed |
| 228 |  | Conduct quarterly audit committee meeting | Governance, Corruption And Public Accountability | 8,465 | IGF | Jan-24 | Dec-24 | 8,465 | 0 | 100% |  | Audit Committee Members | Completed |
| 229 |  | Organize Social Audit Committee project monitoring (engagements to include marginalized groups) | Governance, Corruption And Public Accountability | 0 | SCHMP | Jan-24 | Dec-24 | 0 | 0 | 100% |  | 25 | Completed |
| 230 |  | Encourage and Support Communities to undertake self-help projects | Governance, Corruption And Public Accountability | 0 | 0 | Jan-24 | Dec-24 | 0 | 0 | 56% |  | Districtwide | Ongoing |
| 231 |  | Rent accommodation for officers who are entitled to official accommodation | Governance, Corruption And Public Accountability | 5,600 | IGF | Jan-24 | Dec-24 | 5,600 | 0 | 100 |  | 1 | Completed |
| 232 |  | Create a Client Service Department at the Assembly (SDG Targets 16.67, 16.a) | Governance, Corruption And Public Accountability | 5,600 | IGF | Jan-24 | Dec-24 | 5,600 | 0 | 100 |  | 1 | Completed |
| 233 |  | Educate and sensitize citizens on their rights and responsibilities. (SDG Targets 16.6, 16.a) | Governance, Corruption And Public Accountability | 5000 | IGF | Jan-24 | Dec-24 | 5000 | 0 | 100 |  | 1 | Completed |
| 234 |  | Organize Capacity Training capacity building for CBO, community members and the Sub- structures to improve service delivery and data Collection of the District assembly. | Governance, Corruption And Public Accountability | 10,000 | IGF | Jan-24 | Dec-24 | 9,600 | 0 | 100 |  | 1 | Completed |
| 235 |  | Procure and install VPN to connect to other offices outside of the Assembly (Area Council) | Governance, Corruption And Public Accountability | 6000 | IGF | Jan-24 | Dec-24 | 5,600 | 0 | 100 |  | 1 | Completed |
| 236 |  | Procure office equipment for offices (computers, printers, stationary ,Anti-virus, value book etc | Governance, Corruption And Public Accountability | 56,468.00 | DACF/IGF | Jan-24 | Dec-24 | 26,189.00 | 30,279.00 | 45% |  | District Assembly | On-going |
| 237 |  | Maintenance of furniture and fixtures | Governance, Corruption And Public Accountability | 14,594.00 | IGF | Jan-24 | Dec-24 | 5,378.00 | 9,216 | 36% |  |  | On-going |
| 238 |  | Intensify the use of Strategic Environmental Assessment (SEA) in the Assembly’s policy processes, plans and programs (SDG Targets 11.6, 16.6) | Governance, Corruption And Public Accountability | 0 | 0 | Jan-24 | Dec-24 | 0 | 0 | 100% |  |  | Completed |
| 239 |  | Organise capacity building training/workshops for Management & Assembly Members | Governance, Corruption And Public Accountability | 17,934.00 | IGF/Donor | Jan-24 | Dec-24 | 17,934.00 | 0 | 100% |  | Management and Assembly Members | Completed |
| 240 |  | Train Agric Officers on yield estimation | Governance, Corruption And Public Accountability | 3,848.00 | Donor (MAG) | Jan-24 | Dec-24 | 3,848.00 | 0 | 100% |  | All Agric Officers | Completed |
| 241 |  | Train Works Dept. staff on contract administration/project management | Governance, Corruption And Public Accountability | 5,600 | IGF | Jan-24 | Dec-24 | 5,600 | 0 | 100 |  | 1 | Completed |
| 242 |  | Train staff on new Microsoft office and other IT programs | Governance, Corruption And Public Accountability | 5,600 | IGF | Jan-24 | Dec-24 | 5,600 | 0 | 100 |  | 1 | Completed |
| 243 |  | Train Budget staff on Public Budgeting, financial management and gender budgeting | Governance, Corruption And Public Accountability | 5,600 | IGF | Jan-24 | Dec-24 | 5,600 | 0 | 100 |  | 1 | Completed |
| 244 |  | Planning Unit Staff to undertake policy analysis, Project Monitoring and Evaluation (SDG Target 17.9 | Governance, Corruption And Public Accountability | 6,000 | IGF | Jan-24 | Dec-24 | 5,600 | 0 | 100 |  | 1 | Completed |
| 245 |  | Train on Assets, Inventory and Procurement Management for HODs and selected staff | Governance, Corruption And Public Accountability | 8,984.00 | IGF | Jan-24 | Dec-24 | 8,984.00 |  | 100 |  | HoDs and Selected Staff | Completed |
| 246 |  | Ensure effective implementation of the National Anti-Corruption Action Plan (NACAP) (SDG Targets 16.5, 16.b) | Governance, Corruption And Public Accountability | 6,478.00 | Donor (Gender in Focus) | Jan-24 | Dec-24 | 6,478.00 | 0 | 100% |  |  | Completed |
| 247 |  | Sensitize staff on NACAP | Governance, Corruption And Public Accountability | 5,600 | IGF | Jan-24 | Dec-24 | 5,600 | 0 | 100 |  | 1 | Completed |
| 248 |  | Pursue an effective campaign for attitudinal change (SDG Targets 16.5, 16.7) | Governance, Corruption And Public Accountability | 2,934.00 | IGF | Jan-24 | Dec-24 | 2,934.00 | 0 | 100% |  |  | Completed |
| 249 |  | Mounting of Suggestion box at the Assembly | Governance, Corruption And Public Accountability | 500 | IGF | Jan-24 | Dec-24 | 500 | 0 | 100 |  | 1 | Completed |
| 250 |  | Engage CSOs and other stakeholders in the District in the Fight against Corruption. | Governance, Corruption And Public Accountability | 4,823.00 | GACC | Jan-24 | Dec-24 | 4,823.00 | 0 | 100% |  | 120 | Completed |
| 251 |  | Organize Public education and awareness programs on the evils of corruption and the ethos of anti-corruption in the Society. | Governance, Corruption And Public Accountability | 1000 | IGF | Jan-24 | Dec-24 | 1000 | 0 | 100 |  | 1 | Completed |
| 252 |  | Introduce the Clocking System to control absenteeism, lateness and moonlighting. | Governance, Corruption And Public Accountability | 0 | 0 | Jan-24 | Dec-24 | 0 | 0 | 0 |  | 0 | Yet to start |
| 253 |  | Organize monthly Radio education and sensitization on Corruption related issues. | Governance, Corruption And Public Accountability | 3,840 | FoN | Jan-24 | Dec-24 | 3,840 | 0 | 100 |  | districtwide | Completed |
| 254 |  | Develop and publicize sexual harassment policies at the work place. | Governance, Corruption And Public Accountability | 3,840 | DACF | Jan-24 | Dec-24 | 3,840 | 0 | 100 |  | SDA | Completed |
| 255 |  | Encourage the formation of community “watch-leads” | Governance, Corruption And Public Accountability | 0 | CSOs | Jan-24 | Dec-24 | 0 | 0 | 100 |  | districtwide | Completed |
| 256 |  | Provide office for city guards at Beposo Market | Governance, Corruption And Public Accountability | 4,500.00 | IGF | Jan-24 | Dec-24 | 4,500 | 0 | 0 |  | 0 | Completed |
| 257 |  | Provide support to the District Police Service | Governance, Corruption And Public Accountability | 4,984.00 | IGF | Jan-24 | Dec-24 | 4,984.00 | 0 | 100% |  |  | Completed |
| 258 |  | DISEC Activity | Governance, Corruption And Public Accountability | 48,394.00 | DACF/IGF | Jan-24 | Dec-24 | 48,394.00 | 0 | 100% |  |  | Completed |
| 259 |  | Strengthen the Shama Traditional Council to promote development (SDG Targets 16.6, 16.a | Governance, Corruption And Public Accountability | 5,038.00 | IGF | Jan-24 | Dec-24 | 5,038.00 | 0 | 100% |  |  | Completed |
| 260 |  | Enhance private sector participation in culture promotion (SDG Target 17.17) | Governance, Corruption And Public Accountability | 90,034.00 | IGF/PRIVATE SECTOR | Jan-24 | Dec-24 | 32,644.00 | 57,390.00 | 28% |  |  | On-going |
| 261 |  | Position the District as a preferred destination for business, education and tourism (SDG Targets 4.a, 8.9, 12.b, 16.6 | Governance, Corruption And Public Accountability | 3,000 | FoN/DACF | Jan-24 | Dec-24 | 3,000 | 0 | 100 |  | districtwide | Completed |
| 262 |  | Identify and initiate actions with relevant cities in Africa, USA, UK, Australia | Governance, Corruption And Public Accountability | 2,067,124,00 | PRIVATE SECTOR (TICO) | Jan-24 | Dec-24 | 203,876.00 | 1,863,248 | 34% |  |  | On-going |
| 263 |  | Support/Implement Open Governance Partnership(OGP) activities | Governance, Corruption And Public Accountability | 34,458.00 | Donor (CDD/FoN) | Jan-24 | Dec-24 | 13,475.00 | 20,983.00 | 76% |  |  | On-going |
| 264 |  | Organise home coming summit for citizens in the diaspora | Governance, Corruption And Public Accountability | 30,000.00 | PRIVATE SECTOR/CSO | Jan-24 | Dec-24 | 3,840 | 0 | 100 |  | Shama | Completed |
| 265 |  | Positioning Shama District as the gate way to the Western Region and Oil City | Governance, Corruption And Public Accountability | 0 | FoN | Jan-24 | Dec-24 | 0 | 0 | 100 |  | districtwide | Completed |
| 266 |  | Implement Open Governance Partnership(OGP) activities | Governance, Corruption And Public Accountability | 5,000.00 | FoN | Jan-24 | Dec-24 | 5,000.00 | 0 | 100 |  | districtwide | Completed |
| 267 |  | Strengthen early warning and response mechanisms for disasters | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 20,000 | DACF | Jan-24 | Dec-24 | 20,000 | 20,000 | 100% |  | Districtwide | Completed |
| 268 |  | Support data gathering, preparation of hazards/ risk maps and sensitization on natural hazards and human induced disasters | Emergency Planning And Response (Including Covid-19 Reacovery Plan) | 15,000 | DACF | Jan-24 | Dec-24 | 15000 | 15000 | 100% |  | Districtwide | Completed |
| 269 |  | Develop monitoring mechanism for disaster prevention and mitigation plan | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 10,000 | DACF | Jan-24 | Dec-24 | 9850 | 9850 | 100% |  | Districtwide | Completed |
| 270 |  | Build the Capacity of National Disaster Management Organization (NADMO) on Disaster Control and Management | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 12,000 | DACF | Jan-24 | Dec-24 | 11,500 | 11,500 | 100% |  | All staff | Completed |
| 271 |  | Strengthen the participation of civil society in disaster risk management | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 30,000 | DACF | Jan-24 | Dec-24 | 30,000 | 30,000 | 100% |  | Districtwide | Completed |
| 272 |  | Sensitize stakeholders on disaster risk reduction legislation | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 30,000 | DACF | Jan-24 | Dec-24 | 30,000 | 30,000 | 100% |  | Districtwide | Completed |
| 273 |  | Improve surveillance, monitoring and evaluation of Health threats and epidemics and pandemics | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 15,000 | DACF | Jan-24 | Dec-24 | 15,000 | 15,000 | 100% |  | Districtwide | Completed |
| 274 |  | Control of quarry and sand wining industries | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 5,000 | DACF | Jan-24 | Dec-24 | 5,000 |  | 100% |  | Shama | Ongoing |
| 275 |  | Ensure that planning activities of Departments are in line with the Coordinated Programme in DMTDP | Implementation, Coordination, Monitoring And Evaluation |  |  | Jan-24 | Dec-24 |  |  | 100% |  | Districtwide | Completed |
| 276 |  | Strengthen coordination between CSOs, NGOs, DPS and local authorities | Implementation, Coordination, Monitoring And Evaluation | 5,000 | DACF | Jan-24 | Dec-24 | 5,000 | 5,000 | 100% |  | Districtwide | Completed |
| 277 |  | Implement the District Development Data Platform (DDDP) | Implementation, Coordination, Monitoring And Evaluation | 1,000 | DACF | Jan-24 | Dec-24 | 1,000 | 1,000 | 100% |  | Districtwide | Completed |
| 278 |  | Strengthen and improve resource mobilization for plan implementation | Implementation, Coordination, Monitoring And Evaluation | 15,000 | DACF | Jan-24 | Dec-24 | 15,000 | 15,000 | 100% |  | Districtwide | Completed |
| 279 |  | Design uniform Reporting Format for all Departments | Implementation, Coordination, Monitoring And Evaluation |  |  | Jan-24 | Dec-24 |  |  | 100% |  | Districtwide | Successfully Completed |
| 280 |  | Develop effective participation and communication arrangements for M&E results | Implementation, Coordination, Monitoring And Evaluation | 10,000 | DACF | Jan-24 | Dec-24 | 10,000 | 10,000 | 100% |  | Districtwide | Monitoring Activities successfully conducted |
| 281 |  | Increase investments in the development and use of M&E results | Implementation, Coordination, Monitoring And Evaluation | 20,000 | DACF | Jan-24 | Dec-24 | 20,000 | 20,000 | 100% |  | Districtwide | Completed |
| 282 |  | Strengthen M&E technical and logistical capacities at all levels | Implementation, Coordination, Monitoring And Evaluation | 5,000 | DACF | Jan-24 | Dec-24 | 5,000 | 5,000 | 100% |  | Districtwide | Completed |
| 283 |  | Conduct Periodic Project Monitoring | Implementation, Coordination, Monitoring And Evaluation | 20,000 | DACF | Jan-24 | Dec-24 | 20,000 | 20,000 | 100% |  | Districtwide | 2 Project Monitoring Completed |
| 284 |  | Build the capacity of DPCU on data Management | Implementation, Coordination, Monitoring And Evaluation | 10,000 | DACF | Jan-24 | Dec-24 | 10,000 | 10,000 | 100% |  | DPCU Members | Completed |
| 285 |  | Organize exchange visits and peer leaning among other MMDAs | Implementation, Coordination, Monitoring And Evaluation | 35,000 | DACF | Jan-24 | Dec-24 | 10,000 | 35,000 | 100% |  | Districtwide | Completed |
| 286 |  | Digitize District records and retrieval processes | Implementation, Coordination, Monitoring And Evaluation | 10,000 | DACF | Jan-24 | Dec-24 | 2,000 | 10,000 | 20% |  | Districtwide | Ongoing |

Appendix 4: Performance Indicators (Core And District Specific) At The District Level

|  | Indicator (Categorised by Development Dimension | Baseline 2021 | Actual 2022 | Actual 2023 | Target 2024 | Actual 2024 | Key programmes undertaken during the year | Challenges encountered in the year | Departmental policy recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Economic Development |  |  |  |  |  | 1. Planting for export and rural development (PERD) 2. Planting for food and jobs (PFJI | 1.Unavailability of funds to run administrative programmes. 2. Inadequate/ Lack of personnels(AEA's) | The department recommends the abolishment of arable lands for clay mining , sand winning and other unrelated agricultural activities. |
|  | Total output in agricultural production - Maize - Rice (milled), - Cassava - Oil palm - Goat - Pig - Poultry - sheep - Plantain | 9200 | 25000 | 2112 | 919 | 1225 |  |  |  |
|  |  | 3012 | 18109 | 635 | 550 | 608 |  |  |  |
|  |  | 2,700,018 | 67120 | 12515 | 11,851 | 13,036 |  |  |  |
|  |  | 279,300 | 15000 | 211,647 | 900 | 1,233 |  |  |  |
|  |  | 7216 | 8532 | 13350 | 35,000 | 36,050 |  |  |  |
|  |  | 3030 | 2000 | 2000 | 15,000 | 15,700 |  |  |  |
|  |  | 279,300 | 15000 | 43,000 | 120,000 | 123,600 |  |  |  |
|  |  | 600 | 8520 |  | 40,000 | 42,000 |  |  |  |
|  |  | - | - | - | 251 | 351 |  |  |  |
|  | Average productivity of selected crop (mt/ha): |  |  |  |  |  |  |  |  |
| i. | Maize | 5.6 | 4.5 | 4.5 | 2.0 | 2.6 |  |  |  |
| ii. | Cassava | 23.5 | 20.5 | 23.76 | 22.8 | 24.1 |  |  |  |
|  | Percentage of arable land under cultivation | 88% | 65% | 60% |  | 7.71% |  |  |  |
|  | Number of AEAs Trained on Agric Technologies | 11 | 17 | 17 | 17 | 3 |  |  |  |
|  | Total Number farmers with access to agriculture technologies | 123 | 167 | 185 | 5000 | 7233 |  |  |  |
|  | Number of Farmers engaged in livestock production | 265 | 393 | 434 | 400 | 779 |  |  |  |
|  | Number of Farmers trained of Climate Smart Agriculture | 210 | 329 | 350 | 900 | 1889 |  |  |  |
|  | Number of new industries established - Agriculture, - Industry, - Service | 17 | 5 | 5 | 5 | 4 |  |  |  |
|  |  | 15 | 4 | 10 | 6 | 9 |  |  |  |
|  |  | 23 | 3 | 10 | 5 | 10 |  |  |  |
|  | Number of new jobs created - Agriculture - Industry - Service | 10,863 | 5,894 | 6,140 | 6,500 | 6,245 | Formation of LED platforms, Collaboration with Private Sectors for the development of Tourist sites, Capacity Building for SMEs, Support to SMEs, | Insufficient funds to carry out capacity building across the district | Government should massively support industrial development |
|  |  | 662 | 96 | 108 | 90 | 112 |  |  |  |
|  |  | 846 | 64 | 129 | 55 | 135 |  |  |  |
| 10. | Number of Tourism site developed | 1 | 1 | 1 | 1 | 1 |  |  |  |
| 11. | Number of SMEs trained on Business Development | 12 | 23 | 25 | 28 | 30 |  |  |  |
| 12. | Number of Market facilities in the District | 4 | 4 | 4 | 6 | 5 |  |  |  |
| 13. | Percentage change in IGF | 16.40% | 15.50% | 68.04% | 16% | 71.9% |  |  |  |
| i. | Number of Development Permit Issued | 109 | 186 | 178 | 170 | 171 |  |  |  |
| ii. | Number of Development Application Received | 199 | 197 | 190 | 170 | 179 |  |  |  |
|  | Number of Bills Distributed |  |  |  |  |  |  |  |  |
| i. | BOP | 1970 | 2,561 | 2771 | 3017 | 3003 | sensitization of chiefs and landlords on development issues, distribution of bills Formation of Revenue Mobilization task force |  | The Assembly should provide the Revenue unit with the necessary logistics, regular stakeholders engagement on the need for taxation |
| ii. | Property Rate | 6,331 | 6,845 | 561 | 11,453 | 994 |  |  |  |
|  | Social Development |  |  |  |  |  |  |  |  |
| 7 | Net enrolment ratio - Kindergarten - Primary - JHS | 88.50% | 89.50% | 84.24% | 75.6% | 69.4% |  |  |  |
|  |  | 93.60% | 94% | 101.1% | 92.3% | 86.1% |  |  |  |
|  |  | 47.80% | 49.80% | 64.55% | 75.3% | 68.0% |  |  |  |
| - 8 | Gender Parity Index - Kindergarten - Primary - JHS - SHS |  |  |  |  |  |  |  |  |
|  |  | 0.97 | 0.97 | 01:01 | 1:1 | 1:1 |  |  |  |
|  |  | 0.98 | 0.98 | 01:08 | 1:1 | 1:05 |  |  |  |
|  |  | 1.03 | 1.03 | 01:01 | 1:1 | 1:1 |  |  |  |
|  |  | 1.06 | 1.06 | 01:07 | 1:1 | 1:81 |  |  |  |
| - 9 | Completion rate - Kindergarten - Primary - JHS - SHS | 112.2% | 97.2% | 100% | 100% | 113.21% |  |  |  |
|  |  | 100.1% | 99.1% | 99.7% | 100% | 112.64% |  |  |  |
|  |  | 85.9% | 84.9% | 100% | 100% | 114.24% |  |  |  |
|  |  | 88.2% | 75.2% | 89.0% | 65.9% | 35.59% |  |  |  |
| - 10 | Pass rate • JHS • SHS | 59.48% | 55% | 55% | 75% | 58% |  |  |  |
|  |  | 71.21% | 75.3% | 79.8% | 95% | 76.4% |  |  |  |
| - 11 | Number of school furniture | 620 | 390 | 340 | 400 | 2240 |  |  |  |
| - 12 | Proportion of health facilities that are functional - CHPS Compound - Clinic - Health Center - Polyclinic - Hospital | 17 | 18 | 18 | 18 | 18 | - Sensitization and orientation of staff and other stakeholders on the network of practice concept. - Training of staff on wellness activities to reduce NCDs - Community outreach ervices - Cholora vaccination campaigns - EPI surveillance training - School screening for scabies and other skin diseases - Training on life saving skills - Training of CHMCs on health advoccy and behavioural change community durbars | - inadequate supply of drugs from regional medical stores - High cost of electricity charges. - Inconvenience of the usage of prepaid by health facilities - Inadequate space - Security challenges at various facilities leading to thefts - Inadequate suppl of water - Inadequate office space at some health facilities - No placenta pits for proper disposal of waste after delivery - No Staff accomodation for critical staff - Inadequate logistics and equipment. | Contractors should be paid Government should fast tract the completion of the hospital under construction under Agenda 111 in the district |
|  |  | 1 | 1 | 1 | 1 | 1 |  |  |  |
|  |  | 4 | 4 | 4 | 5 | 5 |  |  |  |
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  | 2 | 2 | 2 | 2 | 2 |  |  |  |
| - 13 | Prevalence of malnutrition (institutional) •Wasting •Underweight •Stunting •Overweight | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  | 30 | 156 | 245 | 141 |  |  |  |  |
|  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| - 13 | Maternal mortality ratio (Institutional) | 33.09 | 30.54 | 0 | 0 | 66.38 |  |  |  |
| - 14 | Malaria case fatality (Institutional) - District total - Under five years - Women between 15-49 | 0.39 | 0 | 0.18 | 0 | 0 |  |  |  |
|  |  | 0.39 | 0 | 0.18 | 0 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
| - 15 | Proportion of population who have tested positive for covid-19 | 0.68% | 0 | 0 | 0 | 0 |  |  |  |
| - 16 | Proportion of population with valid NHIS card - Total - Indigents - Informal - Aged - Under 18years - Pregnant Women | 99.99% | 99.99% | 46.56% |  | 44.08% | Integration of NHIS cards and Ghana cards Registration school children on NHIS scheme, Radio Education on NHIS, Community Sensitization/Registration on NHIS | Inadequate logistics, delay in the release of funds for mass registration | Provision of adequate logistics |
|  |  | 3.36% | 3.36% | 7.57% | 100% | 5.9% |  |  |  |
|  |  | 35.27% | 35.27% | 16.12% | 100% | 37.5% |  |  |  |
|  |  | 3.30% | 3.3%s | 1.59% | 100% | 3.8% |  |  |  |
|  |  | 49.60% | 49.60% | 19.81% | 100% | 42.0% |  |  |  |
|  |  | 3.46% | 3.46% | 1.47% | 100% | 2.8% |  |  |  |
| - 17 | Number of births and deaths registered - Birth (sex) - Death (sex, age group) | Male: 439 Female:621 | Male:522 Female:571 | Male: 722 Female:711 | Male:800 Female:1000 | Male;775 Female;740 | Mobile registration for new borns | 1.Low coverage of death registration due to the ownership of the cemetery. The cemeteries are owned by the churches and families and as a result of that the people bury their deceased without reporting to the office for the information to be captured in the death register. Introduction of new system to work with which makes it difficult to work effectively for the first quarter. Lack of logistics. Financial constraint to do more mobile registration. | 1.Sensitization and education of the public about the importance of birth and death registration. 2.To do more mobile registration to register children to achieve the target. 3.Visiting and liaising with the community health nurses to register children under one (1) year. |
|  |  | Male:24 Female:30 | Male: 30 Female:25 | Male: 42 Female:26 | Male: 0 Female:0 | Male;42 Female;20 |  |  |  |
| - 18 | Percent of population with sustainable access to safe drinking water sources - District - Urban - Rural | 92.00% | 82% | 92% | 100% | 93.8% | - IBES PHASE I - MPI REPORT DISSEMINATION CROP CUTTING | - Lack of logistics and insufficient office equipment - difficulty in accessing data from some agencies insufficient funds to embark on data collection processes | - want to edge the assembly to invest in data collection to provide accurate data to aid the preparation of budget - the assembly should make it a priority to update the data on properties and businesses within the district. Departments, agencies and management should abreast themselves with the new population project in their planning activities. |
|  |  | 89.50% | 58.90% | 61.33 | 100% | 62.83% |  |  |  |
|  |  | 72.40% | 23.70% | 30.67 | 100% | 32.97% |  |  |  |
| - 19 | Proportion of population with access to improved sanitation services - District - Urban - Rural | 89.00% | 52.60% | 58.60% | 100% | 66.1% |  |  |  |
|  |  | 98.50% | 34.90% | 39.06% | 100% | 46.56% |  |  |  |
|  |  | 79.50% | 17.70% | 19.54% | 100% | 27.04% |  |  |  |
| - 20. | Number of functional Sanitation Facilities |  |  |  |  |  |  |  |  |
| - i. | Public Toilet | 35 | 35 | 35 | 35 | 35 |  |  |  |
| - 21. | Dumping Site | 25 | 25 | 25 | 25 | 25 |  |  |  |
| - 22. | Number of Sanitation cases prosecuted | 45 | 37 | 44 | 45 | 42 |  |  |  |
| - 23. | Recorded cases of child abuse - Child trafficking, - child labour, - sexual abuse, - emotional abuse - neglect - early marriage - female genital mutilation - family-child separation | 0 | 0 | 0 | 4 | 1 | 1.child rights protection and promotion 2.community care 3.justice administration 4.Leap | Inadequate logistics | Timely release of funds to support activities |
|  |  | 0 | 0 | 0 | 1 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 5 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 2 | 2 |  |  |  |
|  |  | 0 | 0 | 0 | 1 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 4 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 1 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 1 | 0 |  |  |  |
|  |  | 0 | 0 | 4 | 5 | 4 |  |  |  |
| - 24. | Percentage of road network in good condition Total Urban Feeder | 64% | 64% | 64% | 100% | 67.4% | District road improvement program (DRIP) | Lack of logistics and delay in the arrival of machines. | To Ensure That Various Communities Have A Good Road Condition |
|  |  | NA | NA | NA | 100% | NA |  |  |  |
|  |  | 64% | 64% | 0% | 100% | 46.5% |  |  |  |
| - 25. | Percentage of communities covered by electricity - District - Rural - Urban | 96.70% | 96.70% | 100% | 90% | 100% | Extension of Electricity to Community. Collaboration meeting between the Assembly and ECG | Introduction of new meters,Faulty Meters, late payment of Electricity bills | Replacement of Faulty Meters. |
|  |  | 93.50% | 93.50% | 100% | 90% | 100% |  |  |  |
|  |  | 98.70% | 98.70% | 100% | 90% | 100% |  |  |  |
| - 26. | Reported cases of crime - Rape - Armed robbery - Defilement - Murder - Drug trafficking - Peddling - Drug abuse - Domestic violence | 0 | 0 | 4 | 0 | 1 | Radio Sensitization on the effects and consequences associated with crime and the need to thrive in peaceful society | Inadequate funds and logistics to cramp down criminals | Provision of logistics to facilitate the work of the security services in cramping down criminals |
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  | 0 | 0 | 14 | 0 | 3 |  |  |  |
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 0 | 5 |  |  |  |
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  | 0 | 0 | 4 | 0 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  |  | 0 | 0 | 14 | 0 | 0 |  |  |  |
|  |  | 0 | 0 | 0 | 0 | 0 |  |  |  |
| - 27. | Number of communities affected by disaster - Bushfire - Domestic fire - Floods - Wind/Rain Storm - Collapsed building | - | - | - | 4 | - | - Public education/sensitization - Field trip and assessment (Industrial and public places inspections ) - Public education/sensitization - Field trip and assessment Dredging & Desilting of major drainages - Public education/sensitization - Field trip and assessment Tree planting (green district project) • Public education/sensitization • Field trip and assessment | - Inadequate funding No official vehicle to carry out activities - Inadequate funding No official vehicle to carry out activities - Inadequate funding No official vehicle to carry out activities - Inadequate funding No official vehicle to carry out activities | - More funding needed Official vehicle to carry out activities - More funding needed Official vehicle to carry out activities - More funding needed Official vehicle to carry out activities - More funding needed Official vehicle to carry out activities |
|  |  | 4 | 3 | 2 | 8 | 2 |  |  |  |
|  |  | 5 | 4 | 8 | 16 | - |  |  |  |
|  |  | 3 | 1 | 1 | 3 | - |  |  |  |
|  |  | 20 | 1 | 2 | 20 | 2 |  |  |  |
| 28. | Percentage of annual action plan implemented | 91.60% | 92.96% | 92.98% | 100% | 94.68% | Monitoring and Evaluation of most projects and programmes in the AAP | Late submission of quarterly reports, noncollaboration of some decentralized agencies within the District | Workshop should be organized for decentralized agencies to cooperate with the Assembly |
| District Specific Indicators |  |  |  |  |  |  |  |  |  |
| 1 | Number of trainings conducted on ISSOPs | 1 | 5 | 4 | 1 | 0 | Training on how to use the CP toolkit App - 8th Dec. 2023 | Financial and logistical constraints | Training on the effective use of the toolkits |
| 2 | Proportion of case workers trained in child protection and family welfare | 7 | 4 | 9 | 10 | 11 | In - House training for officers on Child Protection and Case management issues | Financial and logistical | More training should be organized for officers |
| 3 | Number of child violence cases benefitting from social welfare/social services | 45 | 16 | 54 | 24 | 7 | In partnership with other NGOs, training was organized for selected community members on relevant topics such as Child labour and Gender Based Violence | Lack of resources: funds and logistics | More sensitization programme should be organized on child violence to educate them on their rights and responsibilities as children |
| 4 | Number of children reached by social work/social services | 36 | 62 | 58 | 50 | 47 | Specific officers are assigned to follow-up on affected children | Transportation problems | Adequate financial and logistical resources is needed to reach out to more children. |
| 5 | Number of people reached with child protection and SGBV information | 3,604 | 1279 | 1,088 | 1500 | 1308 | Community training and sensitization on Child Protection and SGBV issues. This was championed by the Gender Desk | Delay in funds disbursement | funds should be disbursed in time to meet deadlines |
| 6 | Number of LEAP household members on NHIS | 1,097 | 817 | 1,297 | 1239 | 1239 | Community engagement with Leap beneficiaries to educate them on the importance of the LEAP programme and to address their concerns | Transportation challenges | funds should be made available to educate beneficiaries |
| 7 | Number of households with adolescent girls benefiting from LEAP | 1,297 | 27 | 331 | 413 | 413 | Community engagement with Leap beneficiaries to educate them on the importance of the LEAP programme and to address their concerns | Common problems reported by beneficiaries include: 1. Lost/missing cards 2. Faulty | The department needs a vehicle to embark on its outreach visits/programme |
| 8 | Number of outreach visits to communities with LEAP households | 5 | 24 | 53 | 0 | 0 | Community engagement with Leap beneficiaries to educate them on the importance of the LEAP programme and to address their concerns | The department needs a vehicle to embark on its outreach visits/programme | More training packages should be organized for officers to keep them abreast on modern trends |
| 9 | Number of referrals received from GHS | 1 | 3 | 10 | 0 | 0 | Regular meeting with health directorate | Inadequate funds to follow up of referred casses | Timely release of funds |
| 10 | Proportion of referrals receiving adequate follow-up | 100% | 100% | 7 | 1 | 0 | Specific officers were assigned to follow-up on specific | inadequate funding lack of vehicular movement | Provision of adequate funds |
| 11 | Number of DSWCD’s that have shared their MMDA’s LEAP Household data with both NHIS and GHS | Yes | 1 | 1 | 10 | 7 |  |  |  |
| 12 | Number of regional intersectoral monitoring visits conducted | 1 | 1 | 1 | 1250 | 1239 | A team from the Regional Office visited the Department in Dec. 2023 to train officers on the CP toolkit | logistical challenges | Provision of logistics |
| 13 | Number of meetings organised to discuss integrated services | 1 | 1 | 1 | 2 | 1 | A meeting was organized with key stakeholders in the area of child welfare and disability | lack of funds to organize meetings | assembly should support/a |
| 14 | Number of girls reached by prevention and care services | 3,604 | 5 | 292 | 3 | 0 | The gender desk reached out girls in selected communities to educate them on relevant topics | most of the girls in schools are not met | The department should be well resourced for it to be able to organize more programmes for girls |
| 15 | Number of CP/SGBV cases referred to other services and followed up | 1 | 9 | 7 | 500 | 396 | In partnership with UNICEF. Community engagement was organized to educate community members on relevant topics | inadequate funding | The Gender Desk should be well resourced |
| 16 | Number of NGOs, including RHCs, trained | 2 | 2 | 2 | 10 | 7 | NRD | inadequate funds | Training should be organized for NGOs |
| 17 | Number of children in RHCs profiled and reunified | 7 | 7 | 1 | 4 | 0 | NRD | source of funding | Training should be organized for RHCs |
| 18 | Proportion of sub-standard RHCs closed | 0 | 0 | 1 | 7 | 1 | NRD | NRD | NRD |
| 19 | Number of children placed in foster care | 0 | 0 | 0 | 1 | 1 | No training was done. However, workshop on fostering was organized in 2022 | the number of persons picking up forms to register as foster parents is not encouraging | Workshop should be organized for interested persons on fostering |
| 20 | Proportion of population with access to basic drinking water sources | 92.00% | 82.60% | 92% | 6 | 0 | Construction of Boreholes, Collaboration with Ghana Water Company and Community Water and Sanitation | Broken pipes, late payment of water bills, low coverage of GWCL pipes, salinity of water from boreholes | Extension of GWCL pipelines, Filtration of saline water, repair of broken pipes |
| 21 | Proportion of population with access to improved sanitation services | 89.00% | 52.60% | 58.60% | 100% | 66.1% | Desilting of choked drains. Monitoring and Supervision of Service Provider. Evacuate and Push 10 refuse heaps sites | Lack of vehicle for regular visit to the communities, Inadequate equipment and unskilled laborers to improve on Sanitation in the district, Indiscriminate and open defecation in the communities and Beaches, Lack of cooperation and compliance by some of the community members. | The Regional Environment dpt should train staff on sanitation improvement activities, sensitization of indigenes to keep their homes neat. |
| 22 | Number of people in ODF communities | 40665 | 40665 | 39894 | 41,000 | 39,964 |  | Sensitization on radio and community engagement | Attitudinal change |
| 23 | Number of staff trained | 106 | 167 | 167 | 170 | 167 | Training on Local government Safety protocol Defensive driving, etc | Inadequate funds and logistics | Release of funds and logistical support |
| 24 | Number of Assembly Members and Unit Committee trained | 110 | 105 | 110 | 110 | 110 | Training on Local government Safety protocol Defensive driving, etc | Inadequate funds and logistics | Release of funds and logistical support |
| 25 | Police Citizen Ratio | 1:1450 | 1:1532 | 1:1620 | 1:1650 | 1:1720 | Training on Safety and Security | Inadequate Personnel | Government should recruit more personnel |
| 26 | Number of Public engagements organized | 32 | 47 | 72 | 80 | 75 | Assembly on Radio and community engagement | Funds and logistics | Timely release of funds and logistics |
| 27 | Number of Spatial Plans Prepared | 8 | 12 | 18 | 12 | 12 | Preparation of Local Plans | Inadequate logistics | Provision of adequate logistics to support the Department |
| 28 | Number of Radio Sensitization organized | 23 | 36 | 44 | 50 | 46 | Assembly on radio programmes | Inadequate funds | Timely release of funds |

NRD-No Reliable Data