SHAMA DISTRICT ASSEMBLY

+233 209 3236

P. O Box 37

Shamadistrict.gov.gh

2023 ANNUAL PROGRESS REPORT ON THE IMPLEMENTATION OF THE MEDIUM-TERM DEVELOPMENT PLAN 2022-2025

JANUARY - DECEMBER

FEB

2024

# TABLE OF CONTENTS

TABLE OF CONTENTS	2

LIST OF ACRONYMS	4

EXECUTIVE SUMMARY	7

CHAPTER ONE	9

GENERALINTRODUCTION	9

1.1.	INTRODUCTION	9

1.2.	Purpose of M&E for the Year, 2023	9

1.3.	Summary of Achievements of the Implementation of the DMTDP (2022-2025)	10

1.3.1 Analysis of the proportion of the Annual Action Plan implemented.	10

1.3.2 Implication of Results on the District Development Goals and Objectives	11

1.4.	Overall Proportion of the DMTDP (2022 -2025) Implemented	12

1.5.	Implication of Results on District Development Goals and Objectives	13

1.7.	Challenges Encountered in Implementing the DMTDP 2022-2025	15

1.8.	Processes Involved in M&E	17

CHAPTER TWO	20

MONITORING AND EVALUATION ACTIVITIES REPORT	20

2.1.	Introduction	20

Programme/Project Status for the Year 2023	20

PHYSICAL PROJECTS	20

PROGRAMMES	21

2.2.	Update on Funding Sources and Expenditure	23

Update on Revenue Sources	23

Analysis of Funding Sources Compared between 2022 and 2023	24

Update on Expenditure	25

2.3.	Update on Indicators & Targets	32

Implication of the Indicator Results on District Goals and Objectives	33

2.4.	Underlying Factors of Success or Failure in the Performance of the Indicators	37

2.5.	Update on Critical Development and Poverty Issues	38

School Feeding Programme (SFP)	39

Livelihood Empowerment Against Poverty (LEAP) programme	39

Planting for Food and Jobs Programme	40

Capitation Grant	40

Common Fund for Persons with Disability	40

2.6.	Evaluations Conducted, their Findings and Recommendations	46

2.7.	Participatory M&E Undertaken and Their Results	47

CHAPTER THREE	51

THE WAY FORWARD	51

3.1. Introduction	51

3.2. Key Issues Addressed and yet to be Addressed.	51

3.2.1. Key Issues Addressed	51

3.2.2. Issues yet to be addressed.	52

3.3. Recommendations	52

3.4. Conclusion	53

LIST OF TABLES

Table 1: Details on the Annual Action Plan Implemented under the Agenda for Jobs Policy Framework	11

Table 2:  Proportion of The DMTDP Implemented	12

Table 3: UPDATE ON REVENUE SOURCES	23

Table 4: Disbursement (Expenditure) between 2022 Compared with 2023	25

Table 5: Shama District Assembly CAPEX Analysis	27

Table 6:CAPEX budget allocation and implementation for ongoing projects	28

Table 7 - Staff Strengths of MMDAs	41

Table 8: Staff Strengths of MMDAs (Trainings and Workshops)	43

Table 9: Staff Strengths of MMDAs (Logistics)	44

Table 10: PM&E Conducted	49

LIST OF FIGURES

Figure 1 Graphical Presentation of the Status of Project Implementation from 2021 to 2023	14

Figure 2:Funding Sources compared between 2022 and 2023.	24

Figure 3: Analysis of Disbursement (Expenditure) for 2021, 2022 and 2023.	32

APPENDIX

Appendix 1: Projects Status - Updated Project Register As At December, 2023	56

Appendix 2: Repair and Maintenance of Existing Infrastructure	60

Appendix 3: Programme register	61

Appendix 4: PERFORMANCE INDICATORS  (CORE AND DISTRICT SPECIFIC) AT THE DISTRICT LEVEL	100

# LIST OF ACRONYMS

AAPs			- 	Annual Action Plans

AMSEC 		- 	Agricultural Mechanization Service Centers

CDD			- 	Center for Democratic Development

CHPS 			- 	Community Health Planning Service

CSLP 			- 	Coastal Sustainable Landscape Project

CSO 			- 	Civil Society Organization

CSR 			- 	Corporate Social Responsibility

CWSA 		- 	Community Water and Sanitation Agency

DACF 			- 	District Assemblies Common Fund

DACF-RFG	-District Assembly Common Fund, Responsive Factor       Grant

DADU 		- 	District Agricultural Development Unit

DBA 			- 	District Budget Analyst

DCAT 			- 	District Centre of Agriculture, Commerce and

DCC 			- 	District Communication Committee

DDF 			-	District Development Facility

DISEC 		- 	District Security Committee

DMTDP 		-	District Medium Term Development Plan

DPCU 			- 	District Planning Coordinating Unit

DPO 			- 	District Planning Officer

EHD 			- 	Environmental Health Department

FBOs 			-	Faith Based Organizations

FGD 			-	Focus Group Discussion

FoN 			- 	Friends of the Nation

GES 			- 	Ghana Education Service

GHS 			- 	Ghana Health Service

GoG 			- 	Government of Ghana

GSGDA 		- 	Ghana Shared Development Growth Agenda

GSS 			-	Ghana Statistical Service

GTZ 			-	German Technical Corporation

HIV 			- 	Human Immune virus

HoDs 			- 	Heads of Departments

ICT 			- 	Information and Communication Technologies

IGF 			- 	Internally Generated Fund

IVRDP 		- 	Inland Valley Rice Development Project

LEAP 			- 	Livelihood Empowerment Against Poverty

LI 			- 	Legislative Instrument

M&E 			- 	Monitoring and Evaluation

MLGRD 		- 	Ministry of Local Government & Rural Development

MMDAs 		- 	Metropolitan, Municipal, District Assemblies

MoFA 			-	Ministry of Food and Agriculture

MOFAD 		- 	Ministry of Fisheries & Aqua-culture Development

MTDP 		- 	Medium Term Development Plan

NADMO 		-	National Disaster Management Organization

NBSSI 		- 	National Board for Small Scale Industries

NDPC 			- 	National Development Planning Commission

NGO 			- 	Non-Governmental Agency

NMTDPF 		-	National Medium Term Development Policy

OBK 			- 	Obinyim Okyina

PFJ 			- 	Planting for Food and Jobs

PHC 			- 	Population and Housing Census

PJI 			- 	Planting for Jobs and Investment

PLHIV 		– 	People Living with HIV

PM&E 		- 	Planning, Monitoring and Evaluation

PPP 			– 	Public – Private Partnership

PWDs 			- 	Persons with Disabilities

SAEMA 		- 	Shama Ahanta East Metropolitan Assembly

SDA 			- 	Shama District Assembly

SDGs 			- 	Sustainable Development Goals

STMA 		- 	Sekondi Takoradi Metropolitan Assembly

SW&CD 		- 	Social Welfare and Community Development

WRCC 		- 	Western Regional Coordinating Council

YEP 			– 	Youth Employment Programme

# EXECUTIVE SUMMARY

The Assembly is required by Section 2 sub-section (1) f and g of the National Development Planning Commission Systems Act, 1994 (ACT 480); Regulation 8 section 3 and Regulation 19 of the NDPC Legislative Instrument (L.I. 2232) and section 12 (3a, b, e; 4e), 46 (1b) and 83 (g & h) of the Local Governance Act, 2016 (Act,936) to plan, implement and monitor and evaluate the development of policies, programmes and projects being executed in the district.

In partnership with beneficiary/host departments, NGOs, traditional authorities, beneficiary communities, the Internal Audit Unit, members of the Social Accountability Committee, opinion leaders and Assembly members, and execution agencies like contractors, the Shama District Assembly, through the District Planning Coordinating Unit, conducted M&E. This gives the Assembly the chance to examine, monitor, evaluate, as well as understand the challenges and lessons encountered during the projects' and programmes implementation.

The 2023 Annual Action Plan contained 285 projects and programmes expected to cost GH¢ 25,892,292.25. At the end of the year 2023, a total of 265 activities representing 92.98% of the Annual Action Plan were implemented, 20 activities representing 7.02% were yet to be started and 49.36% of activities in the MTDP were also implemented.

In 2023, the Assembly aimed for a revenue target of GHȼ14,186,743.61, sourced from various channels. By the end of year under review, 92.6% of this target was achieved, amounting to GHȼ13,134,575.64. The projected expenditure for the Assembly was also GHȼ14,186,743.61, but by the end of 2023, the actual expenditure stood at GHȼ13,192,710.83.

The repair and maintenance of existing infrastructures in Shama District play a pivotal role in ensuring the longevity, functionality, and safety of essential assets. Maintenance activities encompass a wide range of tasks, including repairing structural damages, addressing wear and tear, and conducting routine inspections to prevent potential hazards. With the regular maintenance attitude, it has also fostered economic stability by preserving property values, attracting investment, improving infrastructure, and reducing disruptions to business operations which is linked to the district’s goals and visions.

This report is centered around 25 Core Indicators recommended by the NDPC, along with specific District performance indicators. These include metrics for Integrated Social Services, aligning with the development goals in the 2022–2025 DMTDP of the Assembly. The Annual Progress Report offers comprehensive insights into the progress made, challenges faced, and recommendations for informed decision-making.

The report is organized into three chapters. Chapter one provides a general introduction, while chapter two delves into Monitoring and Evaluation reports. Chapter three focuses on recommendations and the path forward. Performance analysis is visually presented through charts and graphs for easy comprehension.

# CHAPTER ONE

# GENERALINTRODUCTION

## INTRODUCTION

The Shama District Assembly was carved out of the former Shama Ahanta East Metropolitan Assembly (SAEMA) and established in December 2007 by Legislative Instrument (LI 1882) with Shama town as its administrative Capital. Officially, it was inaugurated in March 2008. The Assembly is required by Section 2 sub-section (1) f and g of the National Development Planning Commission Systems Act, 1994 (ACT 480); Regulation 8 section 3 and Regulation 19 of the NDPC Legislative Instrument (L.I. 2232) and section 12 (3a, b, e; 4e), 46 (1b) and 83 (g & h) of the Local Governance Act, 2016 (Act,936) to plan, implement and monitor and evaluate the development of policies, programmes and projects being executed in the district.

The aforementioned provisions mandate the Assembly to regularly inform Central, Regional, and Local Level Authorities, along with all concerned stakeholders, about the advancements in policies, programs, and projects within the district. To fulfill this responsibility, the Assembly compiles and submits reports detailing the progress and impact of these initiatives on a quarterly and annual basis to the National Development Planning Commission (NDPC), facilitated through the Regional Coordinating Council (RCC). Simultaneously, the contents of the report are disseminated to other pertinent stakeholders within the district.

This Annual Progress Report comprehensively outlines the activities carried out by the Assembly from January to December 2023. These activities have been duly reported by the various departments of the Assembly and are presented in three sections with headings, subheadings, and concluded with key findings, recommendations, and conclusions.

## Purpose of M&E for the Year, 2023

For the period under discussion, the Shama District Assembly, collaborating with beneficiary/host departments, NGOs, traditional authorities, beneficiary communities, the Internal Audit Unit, members of the Social Accountability Committee, and execution agencies like contractors, conducted M&E through the District Planning Coordinating Unit.

The main reasons for the M&E exercise are enumerated below:

- To ascertain the achievements being made (progress) with regard to meeting the Development Goals, Objectives and Targets as outlined in the District Medium Term Development Plan (DMTDP 2022-2025).

- To track, assess and compare actual performance of programmes and projects against our set targets effectively and efficiently.

- To generate reliable and accurate information/ data to help make sound policies and improved decisions making for the realization of the district goals and objectives.

- To review actions on implementation of plans and budgets and assess the impact of the various interventions as stated in the DMTDP (2022-2025).

- To establish the level or extent of citizens’ satisfaction with services delivery in the district.

- To provide opportunities for stakeholders to familiarize themselves with the various projects and programs being implemented in the district and ask questions.

- To provide feedback to the Stakeholders in the District.

- To increase stakeholders’ commitment in the participation of programme implementation to achieve holistic success of programmes.

- To build and strengthen stakeholders’ relationship for enhanced program implementation.

- To provide information for better transparency and accountability.

The outcomes and findings of the M&E exercise generated through reports are disseminated to various stakeholders and validated with emphasis on the achievements, challenges, and recommendations.

## Summary of Achievements of the Implementation of the DMTDP (2022-2025)

This section presents the analysis of the proportion of the Annual Action Plan and the DMTDP (2022-2025) implemented at the end of 2023. It discussed the key results achieved and the implication on the attainment of the district goals and objectives. Below are the details.

## 1.3.1 Analysis of the proportion of the Annual Action Plan implemented.

The successful implementation of 265 out of 285 programmes and activities outlined in the Shama District Assembly's 2023 Action Plan reflects a commendable achievement and signifies a robust commitment to local development representing 92.98% success rate as against 92.96% in 2022, an appreciation in the level of development and progress demonstrating a high level of commitment and efficiency in executing the outlined action plan. Despite the economic hardship and its associated effects on inflation and standard of living, the success of the Assembly can be attributed to the effective community engagements and collaboration with stakeholders, fostering a sense of ownership and participation in local development initiatives, transparency in reporting the status of each initiative and proactive approaches to addressing community needs and promoting sustainable growth across the district.

Table 1: Details on the Annual Action Plan Implemented under the Agenda for Jobs Policy Framework

| S/N | DEVELOPMENT DIMENSION | 2022 |  | 2023 |  |
| --- | --- | --- | --- | --- | --- |
|  |  | PLAN | EXECUTED | PLAN | EXECUTED |
| 1 | Economic Development | 51 | 46 | 52 | 49 |
| 2 | Social Development | 117 | 111 | 129 | 123 |
| 3 | Environment, Infrastructure and Human Settlement | 44 | 42 | 41 | 34 |
| 4 | Governance, Corruption and Public Accountability | 50 | 45 | 43 | 39 |
| 5 | Emergency Planning and Response (Including Covid-19 Recovery Plan) | 10 | 9 | 8 | 8 |
| 6 | Implementation, Coordination, Monitoring and Evaluation | 12 | 11 | 12 | 12 |
| TOTAL |  | 284 | 264 | 285 | 265 |

## 1.3.2 Implication of Results on the District Development Goals and Objectives

Based on the provided table, the district excelled across all six development dimensions by allocating resources and implementing a range of interventions for overall progress. Specifically, in Economic Development, 49 out of 52 activities were carried out, and in Social Development, 123 out of 129 activities were implemented according to the table. In the categories of Environment, Infrastructure, and Human Settlement, 34 out of 41 activities were successfully implemented. Concerning Governance, Corruption, and Public Accountability, 39 out of 43 activities were effectively executed. Emergency Planning and Response witnessed the completion of all 8 activities, and Implementation, Coordination, Monitoring, and Evaluation saw the successful implementation of all 12 activities. In total, 265 out of 285 activities were implemented, leaving 20 activities pending.

Notably, the Assembly focused extensively on Social Development, surpassing efforts in other sectors. This success significantly contributed to fortifying the healthcare management system, enhancing sanitation, and promoting gender equality across all sectors in the district.

Economic Development received heightened attention as the Assembly aimed to support small and medium-scale enterprises, resulting in a marked improvement in the business climate. The formation of the District Local Economic Development Platform facilitated business promotion and networking opportunities. Public sensitization efforts, conducted through radio broadcasts and public forums, emphasized the importance of tax compliance, contributing to the realization of the Assembly's 2023 goal for a robust and resilient economy.

In addition, the Assembly increased its focus on Environment, Infrastructure, and Human Settlement development in 2022 compared to the previous year, 2023. This emphasis led to notable improvements in spatial planning, with an increased number of developers seeking approval for development permits. Governance, Corruption, and Public Accountability experienced significant enhancements, fostering transparency, inclusivity, and accountability within the district.

## Overall Proportion of the DMTDP (2022 -2025) Implemented

This section analyzes the overall implementation of the first and second years of the District Medium Term Development Plan (2022-2025). The implementation of the plan started in 2022 and it is critical for the Assembly to analyze the trends of implementation and identify challenges as well as lessons learned for improved implementation of the next two years of the DMTDP (2022 – 2025).

Since the year under review is the second year of the DMTDP (2022 – 2025), the Assembly conducted a review of the implementation of activities as captured in the DMTDP. The review revealed that, the Assembly was able to implement 49.36% of the activities as overall proportion of implementation of the DMTDP (2022-2025) as of December 2023 as against 24.20% in 2022.

Table 2 below presents a summary of the proportion of the overall  implementation of the DMTDP (2022 – 2025).

Table 2:  Proportion of The DMTDP Implemented

| INDICATORS | 2021 | 2022 | 2023 |  |
| --- | --- | --- | --- | --- |
|  | BASELINE | ACTUAL | TARGET | ACTUAL |
| Proportion of the annual action plans implemented by the end of the year | 89.2% | 92.96 | 100% | 92.98 |
| - Percentage completed | 85.7% | 62.1% | 100% | 69.82% |
| - Percentage of ongoing interventions | 13.1% | 26.9% | 0 | 20.35% |
| - Percentage of interventions abandoned | 0.0% | 3% | 0 | 2.81% |
| - Percentage of interventions yet to start | 1.2% | 8% | 0 | 7.02 |
| Proportion of overall MTDP Implemented by the end of the year. | 90.02% | 24.20% | 50% | 49.36% |

Source DPCU, 2023

## Implication of Results on District Development Goals and Objectives

As shown above, Tables 1 and 2 provide an overview of all the projects and activities the Assembly carried out in 2023 to meet its development goals and objectives. Of the 285 activities that were scheduled for the year 2023, 265 projects and programmes were carried out.   Of those, 199 (69.82%) were effectively finished, 58 (20.25%) were in progress, 20 (7.02%) had not yet begun, and eight (8), or 2.81% of the total, had been abandoned. All the development parameters included in the AAP and DMTDP were advantageous to the projects. To ensure accountability, transparency, and value for money in project execution, the Assembly implemented a participatory approach during project implementation and monitoring.

As a result of the successful implementation of the projects and programmes in 2023, several achievements were realized. Notable among them include the following:

- The disbursement DACF to PWDs and the LEAP programme has gone a long way to reduce poverty among People Living with Disabilities, the poor and the vulnerable in the district and enhanced their economic growth.

- Improved engagement with Development Partners and NGOs especially GIZ and Friends of the Nation to support the district in the implementation of its activities.

- Improved project implementation leading to enhanced education, health, and water services delivery.

- Enhanced citizens’ participation in Assembly’s activities. We successfully organized two (2) Town Hall Meetings despite the surge on the economy which interrupted most of the Assembly’s activities to communicate to the achievements, challenges and share best practices with stakeholders.

- Improved efficiency of Agriculture Department leading to increase in food production such as maize, cassava, rice, and animal production especially for goat, pigs and poultry.

- Increased PWDs from 773 PWDs to 835 have been registered (400 males; 435 females).

- Increased support to PWDs with various materials and funds to engage in productive business/activities, education and payment for medical bills in the District.

- There is an increased in access to potable water and reduction in the occurrence of water borne diseases due the provision of boreholes across the rural areas in the district.

- Increased access to potable water for Urban centers/ duelers as they now enjoy increased access to the Ghana Water Supply due to expansion of the facilities.

- Increased support for the vulnerable. PWDs who received cash have appropriately invested the amount into their business and are making profit out from it to support their family.

Figure 1 Status of Project implementation from 2021 to 2023.

Source DPCU, 2023

  - Analysis of Graph and Implication of Results

The above data demonstrates unequivocally that in 2023, the Assembly performed better in terms of carrying out initiatives and plans.

These outcomes were specifically the result of increased DPCU supervision, monitoring, and evaluation exercises, increased citizen engagement through radio programmes about taxation, increased support from citizens and stakeholders, increased relationships with donors, and the activities of auditors who consistently made sure that funds intended for ongoing projects were paid on time. Ultimately, the Assembly decided that, considering the insufficient resources, projects should be awarded to contractors who can pre-finance and finish them.

Meanwhile, the inability of the Assembly to accomplish 100% implementation of the plan were identified to include but not limited to the following:

- Lack of leadership commitment to direct resources for the implementation of the plan (AAP/DMTDP)

- Budgeting was always done using mainly new submissions from the departments and most often new activities are submitted to the Budget Analyst for preparation of the budget. This is always against the laid procedures but because of lack of management support to address this issue, the plan especially the AAP is not followed as required.

- the limited commitment of the populace to the programmes, the poor participation of women in the gender and social protection programmes.

- The impact of Economic Hardship which affected the smooth implementation of the projects. Revenue mobilization efforts were reduced due to the prevention protocols instituted by the President, most institutions also took advantage to either drag their feet or delay payment of the rates while others boldly appeal for discount.

- Finally, delay in the release of funds for the Programme implementation.

## Challenges Encountered in Implementing the DMTDP 2022-2025

- Even though the DMTDP was implemented with great success, there were obstacles that made it difficult to carry out all the plan's scheduled activities. The following list includes the main difficulties that arose during the execution of the 2023 AAP and the DMTDP (2022–2025):

- Inability to mobilize adequate revenue. Due to the Post Coronavirus effect, the implementation of the Assembly’s activities was highly affected because of inadequate funds to implement all planned activities. This resulted in irregular release of funds earmarked for projects/programmes.

- Apathetic attitude among some contractors towards projects/programmes execution particularly GETFUND projects.

- Lack of Logistics for the Social Welfare department to effectively carry out their functions.

- Inadequate capacity building for staff

- Apparent lack of co-operation from some key departments to participate in monitoring.

- Non-release/Delay in the release of funds for monitoring and DPCU meetings

- Inadequate relief items, safety gears and official Vehicle for NADMO Staff in the fight against possible Disasters,

- Indiscriminate selling of large areas of farmlands to multi-nationals and para-rubber farmers leading to destruction of existing cocoa and other food crop farms. This situation if not halted is potentially potent for food insecurity in in the future.

- Poor farming practices because of financial constraints, inappropriate equipment and reluctance of farmers to embrace new technologies.

- Poor supervision of projects also affected quality of output particularly project execution leading to huge public outcry in the district.

- Late start of projects due to late availability of funds particularly DACF.

- Internal Revenue Mobilisation weaknesses and leakages

- Weak capacity of Revenue Collectors as most of the items are wrongly posted.

- Lack of a dedicated revenue mobilisation vehicle.

- Lack of Vehicle for DPCU leading to irregular monitoring of projects and programmes

- Difficulty in obtaining data from some Departments of the Assembly due to poor records keeping.

- Poor office condition of the Planning Unit (broken computers, broken louvres blades and tattered curtains)

- Poorly equipped DCPU Secretariat.

- Untimely submission of reports from some of the Decentralized Departments.

- Difficulty and delays in obtaining data from some decentralized governmental agencies who report to their regional and national offices.

- Lack of data to assess progress and impact of some critical development and poverty issues.

- Improper documentation of data by most decentralized agencies and departments.

- Late reporting by some departments affected the early compilation of this report.

- Inadequate funds for health activities

- Poor Data capture among health facilities

- Poor road network continues to be a major problem district wide. Most roads from farming communities to marketing centers are not in good shape. Roads are deplorable and, in some cases, not accessible especially during rainy season. This makes it difficult for farmers to transport food commodities to marketing centers. The situation brought huge fares from transport operators.

- Low case detection of TB and HIV

- Lack of vaccine fridges for EPI activities in the district

## Processes Involved in M&E

Each major intervention being carried out by the district's departments and agencies, as well as the private sector, is compiled in this annual progress report. The following are some of the primary procedures used in the creation of this report and project monitoring:

- Project Site inspection and Meetings: As part of activities to gather reliable information for the preparation of the APR, a team was constituted (Core DPCU) and site meetings and inspection was conducted at all projects sites and the reports harmonised and fed into the content of this APR. Besides, previous site meeting and inspections reports were reviewed, and the issues harmonised and used as part of this APR.

- Monitoring and Evaluation Exercise. The DPCU is required to conduct quarterly monitoring visits to the various project sites track and assess the progress of ongoing and impact of completed projects. Before these M&E activities are conducted, the DPO who is the Secretary to the DPCU prepares and invite all members to a meeting where the purpose of the M&E is disclosed and extensively discussed. The members are grouped into teams of two (2) and the projects shared among the teams.

- Use of Checklist: Each team uses the M&E guidelines/Checklist prepared by the DPCU to carry out the M&E exercise. This always ensured that we have consistency in the presentation of the reports and easy harmonisation.

- Compilation of M&E Reports and Presentations: Each team has a Leader and Secretary who ensured that comprehensive reports are prepared and presented to the DPCU at its meetings. The contents of these reports have been harmonized and used for the compilation of this report (APR). These M&E exercises is always participatory and involved all members of the DPCU, Development Planning and Works Sub Committees, Assembly members of the host communities, project beneficiaries and lead departments/user agencies as well as the chiefs in these areas.

- DPPCU Meetings: The DPCU convened meetings where Heads of Department who were present made presentations on their activities after which, copies were handed over to the Secretary to the DPCU for harmonisation. These departmental reports have been used as the main content of this APR. At an earlier meeting of the DPCU, the format for the report (APR) was discussed and the feedback from the National Development Planning Commission shared with the members. This facilitated the harmonisation process as all HODs prepared their reports in line with the prescribed format.

- Official Requests: The DPCU Secretariat made official requests to each department to submit their activities (including) all programmes and projects, meetings, updates on national programmes/policies/interventions among others that they have been able to carry out. The activities were captured in their Annual Reports and submitted to the Secretary to the DPCU as requested and the content of these reports were sieved and harmonised and the results fed into the preparation of this APR.

- Data Collection: The DPCU engaged in data collection from both primary and secondary sources to analyze and evaluate the impact of the programs and projects on the recipient communities. Secondary data utilized in this report were sourced from the annual reports for the year 2023 submitted by various Departments, NGOs, Development Partners, and Ministries, Departments, and Agencies (MDAs), as well as minutes from management meetings, sub-committees, and other substructures of the Assembly. Conversely, primary information was obtained through structured interview questionnaires and open-ended interviews conducted with designated officers overseeing key interventions such as NHIS, 1D1F, DCAT, Planting for Food and Jobs (PFJ), Planting for Export and Rural Development (PERD), Planting for Jobs and Investments (PJI), District Committee Against Illegal Mining, LEAP, NYEP, and others.

- Data Validation Exercise: A data validation session was held with the key stakeholders on Wednesday, 23rd January 2024 at the Riverside Conference Hall (See pictures at appendix) where the report was presented to the participants for scrutiny and validation. The content of the report was authenticated and endorsed by the various HODs, Assembly members, Chiefs and community members, leaders of the various associations present. Emphasis was placed on the projects and programmes being implemented in the district, the revenue generation progress, Critical Poverty Reduction programmes, District Core Indicators and the results of the Evaluation conducted. The stakeholders had the opportunity to ask relevant questions to clarify their doubt where necessary.

- Review of Report by the DCD and DCE: After the DPCU Secretariat completed the report, copies were given to the DCE and the DCD to review and ensure that, the information contained in the report was the actual reflection of the situation on the ground before it was packaged for submission to the WRCC and the NDPC.

# CHAPTER TWO

# MONITORING AND EVALUATION ACTIVITIES REPORT

## Introduction

This section of the report provides a comprehensive overview of the 2023 Annual Action Plan's performance within the development dimensions outlined in the Medium-Term National Development Policy Framework (An Agenda for Jobs: Creating Prosperity and Equal Opportunity for All 2022-2025). Additionally, it covers the activities of decentralized agencies and departments affiliated with the Shama District Medium-Term Development Plan (2022-2025) during the specified year.

The report follows a structured format, encompassing key headings such as Program/Project Status for the Year, Updates on Funding Sources, Disbursements, Indicators and Targets, Critical Development and Poverty Issues, Evaluations Conducted, their Findings and Recommendations, Participatory Monitoring and Evaluations (PM&E) Undertaken and their Results, and finally, a Conclusion and the Way Forward.

## Programme/Project Status for the Year 2023

### PHYSICAL PROJECTS

Several physical projects were implemented in the year under review. The project description, contract sum, and implementation status among other details of these projects have been presented in a register/ matrix as Appendix 1 as well as the repair and maintenance of existing infrastructure as Appendix 1b.

In the 2023 project registry, a total of 24 physical projects were recorded. The DPCU and all stakeholders conducted quarterly monitoring and evaluation exercises to track the status of work on these projects. The programs were funded by the DACF, MPCF, DACF-RFG, and GETFund, among other sources. The projects were in varying degrees of completion by the end of the year. The untimely release of external funds prolongs the project duration and delays its completion date. A careful analysis of the Project Register shows clearly that most of the projects had lived beyond their expected completion dates. Others that were completed has outstanding retention amounts to be paid to the contractors. However, all outstanding and ongoing projects have been rolled over to 2024 to ensure they are fully completed to enable the district to achieve its goals and objectives. All the projects from the various funding sources will go a long way to impact the quality of life of citizens in the district.

### REPAIR AND MAINTENANCE OF EXISTING INFRASTRUCTURE

The repair and maintenance of existing infrastructures in Shama District play a pivotal role in ensuring the longevity, functionality, and safety of essential assets. Maintenance activities encompass a wide range of tasks, including repairing structural damages, addressing wear and tear, and conducting routine inspections to prevent potential hazards. By prioritizing maintenance, the Shama District Assembly can prolong the lifespan of its infrastructure, thus minimizing the need for costly replacements or major repairs in the future. From the table (Appendix 2) it can be observed the Assembly well-maintained existing infrastructures which contributed to the overall quality of life for residents by providing reliable services such as transportation, utilities, and public facilities. With the regular maintenance attitude, has also fostered economic stability by preserving property values, attracting investment, improving infrastructure, and reducing disruptions to business operations which is linked to the district’s goals and visions. Furthermore, ensuring the safety and reliability of infrastructure enhances community resilience to natural disasters and other emergencies. Therefore, investing in repair and maintenance initiatives is essential for promoting sustainable development, fostering economic growth, and safeguarding the well-being of the residents in Shama District.

### PROGRAMMES

A total of 261 activities were captured in the programmes register in the reporting year. The programmes cut across all the six (6) development dimensions of the National Medium-Term Development Policy Frameworks: AGENDA FOR JOBS: CREATING PROSPERITY AND EQUAL OPPORTUNITY FOR ALL, 2022-2025. The total number of beneficiaries among other details of the programmes has been captured in a matrix in Appendix 3.

The population's low commitment to the activities and the delay in the allocation of money for programme execution are among the difficulties faced during programme implementation.

The accomplishment of the Assembly's overall development goals and objectives was made possible in large part by the execution of most of the Annual Action Plan's activities. The implementation of these activities has greatly impacted the various indicator outcomes in education, health, water and sanitation, and roads. Generally, the quality of life has been improved with poverty levels declining while significant capital has also been developed, and a small number of job opportunities have been generated by the business training programmes.

## Update on Funding Sources and Expenditure

This section presents an analysis of the sources of funds for the Assembly, total amount received and how these funds were utilized (expenditure) within the period under review. The information is presented in tabular and graphical format to enhance readers understanding.

### Update on Revenue Sources

The traditional revenue sources of the Assembly are District Assembly Common Fund (DACF), Government of Ghana (GoG), District Performance Assessment Tool (DPAT /DACF - RFG), Member of Parliament Common Fund (MPCF), School Feeding Grant (SFG), Donor Support (DS) and the Internal Generated Funds (IGF). The District Assemblies’ Common Fund (DACF) remains the major funding source for developmental projects and programs in the district. Other funding sources which featured prominently include DDF, MPCF, SFG, Donor Support and IGF. Within the year under review, there were delays and irregularities in the releases of funds from Government of Ghana especially the DACF. The table 3 below shows the various sources of funds received from January to December 2023 with reference to previous years.

Table 3: UPDATE ON REVENUE SOURCES

| Revenue Sources | Estimates |  |  | Performance |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | 2021 | 2022 | 2023 | 2021 | 2022 | 2023 |
| DACF | 3,961,475.00 | 3,919,126.10 | 1,800,000.00 | 901,296.82 | 1,680,385.51 | 1,203,911.36 |
| DACF- RFG | 1,180,906.00 | 1,204,832.56 | 1,744,566.24 | 1,115,329.00 | 1,174,498.30 | 0.00 |
| MP’s CF | 594,221.00 | 320,000.00 | 696,390.00 | 432,321.66 | 460,777.15 | 446,101.35 |
| IGF | 2,000,000.00 | 2,100,000.00 | 3,680,000.00 | 1,813,231.85 | 2,105,590.37 | 3,538,327.53 |
| MSHAP/HIV | 83,600.00 |  |  |  | 12,526.38 |  |
| PWDs CF |  | 250,000.00 | 200,000.00 |  |  | 106,443.63 |
| UNICEF |  | 30,000.00 | 30,000.00 |  | 30,000.00 | 30,000.00 |
| LEAP |  |  |  |  |  |  |
| GOG SALARIES | 4,369,075.08 | 3,101,669.80 | 5,121,894.29 | 3,710,591.90 | 5,147,122.64 | 7,754,649.74 |
| GOG GOODS & SERVICES | 71,913.00 | 109,017.00 | 56,000.00 | 50,643.78 | 51,296.98 | 55,142.03 |
| TOTAL | 12,261,190.08 | 11,034,645.46 | 13,323,494.31 | 8,023,415.01 | 10,662,197.33 | 13,134,575.64 |

Source: Finance Dept., 2023

Figure 2:Funding Sources compared between 2022 and 2023.

### Analysis of Funding Sources Compared between 2022 and 2023

Table 3 and Figure 2 illustrate the funding levels received from diverse sources, revealing that the Assembly acquired more funds in 2023 compared to 2022, particularly in terms of IGF, MP’s CF, and DACF. Consequently, the total for 2023 surpassed that of 2022, contributing to the Assembly's success rate of 92.98% in 2023, a 0.2% increase from 92.96% in 2022. Additionally, in 2023, the Assembly mobilized a higher amount of IGF than in 2022 and 2021, leading to the implementation of more program-based activities compared to physical projects. This performance significantly contributed to accomplishing the district's goals and objectives, focusing on enhancing access to socio-economic services and sustaining peace and security.

Nevertheless, the Assembly could have performed even better in 2023 if expected amounts were released in a timely manner and if the Assembly oversaw Property Tax Collection. To address these challenges in 2024 and boost revenue collection, strategic interventions have been implemented. These include the establishment of the IGF Working Group and Task Force, the utilization of National Service personnel for revenue collection, bonding of Area Councils, and capacity-building initiatives for market queens to collect revenue for the Assembly. Additionally, management has introduced a reward system and created a revenue league table that displays records of revenues received from various collectors based on Area Councils. This initiative aims to boost the enthusiasm of collectors and prevent the diversion of revenue into unauthorized areas.

### Update on Expenditure

Based on the gathered records, the Assembly allocated its financial resources across three main categories: Compensation, Goods and Services, and CAPEX. The data reveals that, within the designated period (2022-2025), the Assembly dedicated more resources to Compensation in 2023 compared to 2022. The total expenditure on goods and services in 2022 was slightly higher than in 2023, showing a percentage change of 48.6%. This shift can be attributed to heightened activities such as monitoring and evaluation, DISEC meetings, and expenses related to the Anto explosion.

The overall annual expenditure for 2023 exceeded the 2022 amount by 23.66%. This trend can be attributed to various factors, including increased sensitization programs, regular stakeholder engagement activities, emergency General Assembly meetings, support to the health sector, and backing government flag

ship programs like Free SHS, Planting for Food and Jobs, Planting for Export and Rural Development, among others. A detailed breakdown of the Assembly's expenditures from 2022 to 2023 is presented in Table 4.

This financial investment played a pivotal role in advancing the district's goals and objectives. It fostered a conducive environment for business growth, improved access to essential social services, reduced crime rates and other social vices, promoted Local Economic Development, and enhanced the international image of the district. The provided information outlines the utilization of revenue by the District Assembly during the reviewed year. Expenditure comprises three primary components: Compensation, Goods and Services, CAPEX (Investment/Asset), and additional expenses not specifically outlined in this template.

Table 4: Disbursement (Expenditure) between 2022 Compared with 2023

| Budget Items | 2021 |  |  | 2022 |  |  | 2023 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Approved | Released | Expenditure | Approved | Released | Expenditure | Approved | Released | Expenditure |
| Compensation | 3,990,123.08 | 3,961,795.20 | 3,961,795.20 | 4,320,352.06 | 5,254,750.61 | 5,254,750.61 | 4,471,388.32 | 8,244,306.38 | 8,244,306.38 |
| Goods and Services | 4,353,147.97 | 3,079,311.22 | 3,079,311.22 | 4,161,499.65 | 4,059,380.15 | 4,059,380.15 | 4,636,473.18 | 4,523,507.27 | 4,523,507.27 |
| CAPEX | 3,917,919.03 | 367,873.61 | 367,873.61 | 2,552,793.75 | 1,354,927.64 | 1,354,927.64 | 4,164,989.03 | 424,897.18 | 424,897.18 |
| Total | 12,261,190.08 | 7,408,980.03 | 7,408,980.03 | 13,134,645.46 | 10,669,058.40 | 10,669,058.40 | 13,272,850.53 | 13,192,710.83 | 13,192,710.83 |

Source: Finance Dept., 2023

As depicted in the table, the expenditure in 2023 surpassed that of 2022, attributed to the Assembly's engagement in various high-cost activities. Noteworthy among these activities are investment projects, regular monitoring and evaluation efforts, and costs associated with the Anto explosion.

This financial commitment contributed to the accomplishment of district goals and objectives. It fostered a conducive environment for business growth, enhanced access to essential social services, reduced crime rates and other social vices, promoted Local Economic Development, and cultivated a positive international image for the district. These expenditure patterns are further visually represented in Figure 3 below.

Figure 3: Analysis of Disbursement (Expenditure) for 2021, 2022 and 2023.

Source: Finance Dept., 2023

Table 5: Shama District Assembly CAPEX Analysis

| Proposal | Release | Expenditure |  | Variations |  |  | Recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Unconstrained Capex- plan (A) | Constrained Capex-budget (B) | (C) Release | (D) Expenditure | (A-B) | (B-C) | C-D |  |
| 13,715,000.00 | 7,278,146.55 | 2,861,066.27 | 3,905,915.89 | 6,436,853.45 | 4,417,080.28 | -1,044,849.62 | - Minimal balances in relation to Capital projects should be paid. - The Assembly should comply with the payment plan made. - DACF allocations to MMDAs should be released on time |

Source DPCU

The table present information related to proposed plan and budget for the year 2023, release, expenditure, variations, and recommendations, possibly in the context of a financial or budgetary analysis. The Unconstrained Capex plan depicts the total number of capital projects in the 2023 AAP that has been planned for while constrained is the actual projects budgeted. In the year under review, GH₵ 7,278,146.55 was budgeted while only GH₵ 2,861,066.27 was released for the execution of those projects. At the end of the year, it can be observed that the actual expenditure used in carrying out the projects is more than the actual released. This can be attributed to the late release and reductions of DACF.

Table 6:CAPEX budget allocation and implementation for ongoing projects

| Multi-Year CAPEX throw forward. |  |  |  | MTBF envelope |  |  | Performance |  | Details on Capital Projects 2023 |  |  |  |  |  |  |  |  | Summary |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Project |  |  |  |  |  |  |  |  |  |
| Total Medium-Term Plan Estimate (plan) | Annual Estimate (plan) | Annual Estimate (plan) | Annual Estimate (plan) | Annual Ceiling |  |  | Approved/Released | Expenditure/ | Project code | Name | Age | Original Estimate | Revised Estimate | Expenditure to date | Completion status |  | Time overruns | Land acquisition and resettlement |
| 2025 | 2025 | 2024 | 2023 | 2025 | 2024 | 2023 | 2023 | 2023 |  |  |  |  |  |  | 0% | Picture |  |  |
| 4,874,346.15 | 781,936.09 | 1,104,829.50 | 1,320,092.44 | 213,876.96 | 2,563,114.54 | 4,387,650.82 | 3,813,849.63 | 3,813,849.63 |  | Construction of 1No. 3 Unit Classroom Block with ancillary facilities at Essaman | 12months | 281,904.02 | NA | 155,048.48 | 60% |  | 48 months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of 1No. 3 Unit Classroom Block with ancillary facilities Phase 1 at Komfueku | 12months | 282,667.55 | NA | 94,915.54 | 85% |  | 48 months | NA |
|  |  |  |  |  |  |  |  |  |  | Continuation and completion of Inchaban - Abease Market and Creche at Upper Inchaban | 12months | 651,245.86 | NA | 33,583.96 | 15% |  | 36months | NA |
|  |  |  |  |  |  |  |  |  |  | Continuation and Completion of Dressing Room & Fence Wall around Football Park at Aboadze | 12months | 234,383.49 | NA | 201,777.26 | 96% |  | 84months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of Community park with ancillary facilities at Upper Inchaban | 12months | 549,646.38 | NA | 373,481.61 | 67% |  | 36months | NA |
|  |  |  |  |  |  |  |  |  |  | Const. of 3-unit classroom Block with ancillary facilities at Ituma (Revised) | 6months | 195,545.37 | NA | 113,214.20 | 85% |  | 96months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of Area Council Office at Abuesi | 6months | 76,070.25 | NA | 32,131.73 | 43% |  | 96months | NA |
|  |  |  |  |  |  |  |  |  |  | Continuation & Completion of District Assembly Administrative Block Phase 1 at Shama | 9months | 234,943.78 | NA | 90,661.03 | 89% |  | 72months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of 1No. CHPS Compound with ancillary facilities at Komfueku | 12month | 495,939.36 | NA | 445,588.83 | 100% |  | 0 months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of Public Bath House and U-drain at Upper Inchaban | 12months | 34,018.38 | NA | 30614.06 | 100% |  | 24months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of Community Centre at Asem-Asa No.2 | 12months | 131,147.10 | NA | 101,603.46 | 100% |  | 0months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of Community Centre at Nkwantakesedo | 12months | 130,939.73 | NA | 72,619.02 | 100% |  |  | NA |
|  |  |  |  |  |  |  |  |  |  | Continuation and completion of community Centre at Supomu Dunkwa | 6months | 111,237.06 | NA | 94,712.06 | 98% |  | 96months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of 6-Unit Classroom Block with Office Atta Na Atta (Revised) | 6months | 222,320.64 | NA | 131,408.32 | 85% |  | 98months | NA |
|  |  |  |  |  |  |  |  |  |  | Continuation and completion of Community Centre Abuesi (DACF MP) | 9months | 507,775.73 | NA | 233,482.45 | 55 |  | 91months | NA |
|  |  |  |  |  |  |  |  |  |  | Continuation of Lower Inchaban Market, Culvert & Lorry Park, phase I(Lot 3) | 9months | 344,741.35 | NA | 51,711.20 | 45% |  | 80months | NA |
|  |  |  |  |  |  |  |  |  |  | Continuation of Upgrading Works for Beposo Market (Lot 2) | 12months | 150,163.38 | NA | 115,851.29 | 100% |  | 0months | NA |
|  |  |  |  |  |  |  |  |  |  | Const. of 1No. 10-Seater W/C Place of Convenience Lower Inchaban | 12months | 44,988.05 | NA | 40,404.18 | 100% |  | 0months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of 1 No. 3-Unit Classroom block with Ancillary Facilities Phase1 Assorko | 12months | 277,860.83 | NA | 96,163.21 | 45.8 |  | 53months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of CHPS Compound Yabiw | 12months | 340,969.65 | NA |  | 100 |  | 0months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of CHPS Compound Abuesi (DACF MPHF) | 12months | 479,034.36 | NA | 275,915.35 | 60% |  | 36months | NA |
|  |  |  |  |  |  |  |  |  |  | Construct 1 No. 2-Unit KG Classroom block with Office, Kitchen and Urinal/toilet facilities for Aboso D/A primary school. | 6months | 473,800.00 | NA | 346458.46 | 100 |  | 0months | NA |
|  |  |  |  |  |  |  |  |  |  | Rehabilitate 4 No. Market sheds for Shama | 6months | 160,300.00 | NA | 156292.5 | 100 |  | 0months | NA |
|  |  |  |  |  |  |  |  |  |  | Construct 1 No. 4units Semi-Detached Chamber and Hall Teachers Quarters | 6months | 449500 | NA | 268236.43 | 65 |  | 9months | NA |
|  |  |  |  |  |  |  |  |  |  | Construction of 3 Units Classroom Block at Assorko | 6months | 303,500.00 | NA | 257,975.00 | 65 |  | 9months | NA |

NA-Not Applicable

### Analysis of Capex Budget Allocation and Implementation for Active Projects

Active infrastructure projects in the Shama district have encountered significant delays due to a confluence of factors. Primarily, administrative hurdles have hampered the swift progression of these projects. Issues such as delay and reduction in DACF, regulatory compliance challenges, and funding uncertainties have further compounded the problem, impeding the seamless execution of projects. Additionally, logistical constraints and manpower shortages have exacerbated the situation, leading to a frustrating standstill in the development of crucial infrastructure. In the under review, the Assembly has contributed immensely to the development of the district where some active projects with available resources are strictly under development, and this has given the Assembly the opportunity to build a resilient economy as this is one of the major goals of the Assembly.

## Update on Indicators & Targets

There are some indicators needed to monitor the degree of project and program implementation progress. These indicators will act as a benchmark to assess whether the programs and projects are progressing well.

The NDPC, working in conjunction with MMDAs, RPCUs, DPCUs, CSOs, and DPs, prescribed district key indicators and targets to be tracked in all MMDAs across the country. Under the development dimensions of the National Medium-Term Development Policy Framework, each of the sets of indicators has been classified. Appendix 3 of the report contains specifics about the indicator levels, baseline, targets, and actuals for the period under review.

Also, the District formulated specific indicators that served as units of measurements that helped management of the Assembly to determine the progress being made towards the achievement of the goal and objectives of the Assembly as outlined in the DMTDP 2022 to 2025. These came with targets which assisted management to quantify level of performance to be achieved in each period.

### Implication of the Indicator Results on District Goals and Objectives

This section highlights the performance of district core indictors and specific indicators and target set under the Agenda for Jobs. The indicators and their corresponding target have been categorized under the development dimensions and their assessment focuses on the goals of the Assembly.

#### Economic Development

Based on the gathered data, the combined output of oil palm and poultry in the agricultural sector exceeded their target for 2023. However, there was a decline in the total production of staple foods such as Maize, Rice, and Cassava in 2023 compared to 2022. This decrease can be attributed to external factors like flooding and a mineral explosion. Additionally, there was a reduction in the percentage of arable land available for cultivation. While 2022 provided 65% arable land, 2023 saw a decrease to 60%, primarily due to clay mining activities in certain parts of the district. Some landowners converted their properties into illegal clay mining sites, diverting the attention of the youth from agriculture and its entire value chain, leading to diminished agricultural productivity. This activity also contributes to the depletion of nutrients in the soil. Furthermore, the number of new industries established in 2023 decreased compared to 2022, resulting in a decline in the creation of new jobs.

#### Social Dimension

Activities implemented under Social Development Dimension focused on improving Education and Training, Health and Health Services, Population Management, Water and Sanitation, Child, and Family Welfare, The Aged, Disability and Development, Employment and decent work, Gender Equality, and Sports and Recreation. A total 123 of activities were implemented under this dimension.

As part of the Assembly’s quest to promote equal opportunities, especially for the Vulnerable in society, the Assembly enrolled 76 people with Disabilities (PWDs) in the Disability Fund where all 76 PWDs were trained on Income Generation Activities. Also 1309 persons were enrolled on the Livelihood Empowerment program.

The performance indicators highlight the district’s success in the education sector, with a net enrolment rate exceeding 60% at the Basic level, improved gender parity, and enhanced completion rates. These achievements result from strategic interventions implemented by the assembly to enhance educational outcomes, aligning with the pursuit of SDG 4.

In Junior High School (JHS), there was a notable increase in the pass rate from 55% in the 2021/2022 academic year to 64.6% in the 2022/2023 academic year. This improvement is credited to logistical support that facilitated effective monitoring at the JHS level. The District Education Directorate remains committed to strengthening monitoring activities for sustained performance in the upcoming years.

Despite numerous health challenges in the district, it demonstrated commendable results in disease control, achieving a zero maternal mortality rate and malaria case fatality. However, health facilities recorded low Outpatient Department (OPD) attendance, possibly due to residents relying on pharmacies and local herbs for their healthcare needs.

Regarding water and sanitation progress, the district witnessed a significant enhancement in sanitation services, with 58.6% of the population having improved sanitation compared to 52.6% the previous year. Additionally, 92% of the district population gained access to clean drinking water. The Assembly's interventions in water and sanitation align with SDG6 goals, aiming to further improve these essential services.

Issues relating to crime and security, the major crimes recorded in the year under review was defilement and Rape. Defilement recorded the highest crime incidence of 14 followed by Rape with 4 incidences. This increasing crime rate creates a high level of insecurity in the District. The District Police Command and the Assembly are however putting strategies in place to contain the situation which is geared towards SDG 16.

Social Service Delivery improved in terms of gender activities and persons with disability. To attain SDG 5 and 10 which indicate “Gender Equality and Reduced Inequality “respectively, the district executed sensitization exercises on economic empowerment, governance, and skills training for women groups and PWDs.

#### Environment, Infrastructure and Human Settlements

This Development Dimension focused on creating a work environment that is safe, healthy, and conducive to facilitating socioeconomic activity.

For this reason, to promote holistic growth, well-planned communities must have sustainable infrastructure. The district's goal is to "Promote spatially integrated and orderly human settlement" in accordance with this. Human settlement and housing, protected areas, transportation infrastructure, drainage, and flood management are among the issues covered by this purpose. In order to accomplish these overarching objectives, the Assembly carried out sixteen initiatives in 2023. The Assembly further carried out climate change-related initiatives to fulfill SDGs 11, 13, and 15. These consist of reclaiming degraded lands, educating the public about agroforestry, and planting trees. Under this development dimension, these actions contributed to an improvement in indicator performance.

Roads

The condition of the road infrastructure in the district has been a significant cause for concern. The district encompasses a total road network of 65km, with 5km being paved and 60km remaining unpaved.

Throughout the period, the Assembly engaged in reshaping feeder roads within the communities. The inefficiencies in the road sector have had widespread repercussions on all other sectors, impeding the Assembly's capacity to attain its objectives fully and effectively. In alignment with the national agenda to enhance the efficiency and effectiveness of road transport infrastructure and services, the District Assembly will prioritize road maintenance.

Electricity Coverage

The district has completed electricity coverage in all communities (rural and urban) connected to the national grid. This is in fulfilment of the national agenda to ensure efficient transmission and distribution system and impacted the wellbeing of the people in the district. The effort is also towards the attainment of SDG7 target 7.1.

#### Governance, Corruption, and Public Accountability

The district’s goal in line with this development dimension is “To ensure transparent, and accountable governance”. This translates to ensuring the popular participation of the people in the governance and decision-making processes as well as strengthening the capacity of the district and sub-district administration to be efficient and effective in discharging their mandates.

Executing 39 activities and projects in the year 2023 within this framework, the District Assembly followed the principles of Good Governance, many of which align with the objectives of SDG16. These principles encompass openness, transparency, responsiveness, and sustainability. Various initiatives were undertaken to uphold government transparency, including the organization of town hall meetings, open governance partnership meetings, and other engagements with stakeholders. These efforts contributed to enhancing the performance indicators within this development dimension.

#### Emergency Planning and Response (Including Covid-19 Recovery Plan)

The overarching objective of the emergency planning and response dimension, including the COVID-19 recovery plan, is to advance proactive planning and implementation for disaster and disease prevention and mitigation while enhancing adaptive capacity to withstand national and global threats.

The indicators within this development dimension aim to assess the Assembly's readiness for emergencies, including disaster and COVID-19 cases. Situated in a coastal and agricultural area, the Assembly experienced fewer community impacts from disasters in the reviewed year compared to the previous year, 2022. Specifically, the District encountered four communities affected by bushfires, two communities affected by floods, and two communities affected by rainstorms.

Notably, there were no reported cases of COVID-19 in the reviewed year, as the District Health Directorate continued its efforts in sensitization and COVID-19 vaccination. The District Assembly through it continued education and sensitization successfully decreased the number of fatalities and individuals affected by disasters, leading to a substantial reduction in direct economic losses attributed to disasters, focusing on safeguarding the well-being of the poor and individuals in vulnerable situations.

#### Implementation, Coordination, Monitoring and Evaluation

Broadly, this dimension aims to enhance the preparation, execution, and coordination of plans at all levels, reinforce monitoring and evaluation systems, improve the production and utilization of statistics, boost resource mobilization, efficiently manage resource utilization, and elevate knowledge management and learning processes.

The indicators within this development dimension shows the advancement in the implementation of the 2023 Annual Action Plan. The district achieved a 92.98% implementation rate, showing improvement from 92.96% in 2022. This success can be credited to the Assembly's dedication and effort to enhance its revenue generation and foster strengthened collaboration with all stakeholders.

Additionally, effective monitoring and evaluation mechanisms culminated in this improved performance. The Assembly sought to attain SDG 17. The Municipal Assembly collaborated with various stakeholders such as Friends of the Nation, CDD, and other stakeholders to implement its planned activities.

## Underlying Factors of Success or Failure in the Performance of the Indicators

From the data gathered from the various departments, we observed that, the successes and failures encountered were due to certain factors. These have been categorized as success factors and Failure factors.

Success Factors

- Enhanced project/programme supervision

- Regular site inspections

- Improved revenue mobilization

- Enhanced cooperation of stakeholders

- The use of the Participatory Monitoring and Evaluation Strategy which offered opportunity to the citizens/beneficiaries to participate in the programmes/project implementation processes.

- Engagement of Assembly members in revenue collection

Failure Factors

- Inability to meet revenue target due to the following reasons.

- Inadequate Permanent Revenue Staff,

- High Attrition Rate of Trained Revenue Collectors,

- Inadequate Logistics (Lack of Dedicated Vehicle for Revenue Mobilization),

- Effect of post covid-19 era as many organizations called for rebates or fees waivers.

- Late or non-release of funds from Central Government especially DACF) leading to inability to implement projects budgeted against the DACF.

- Inadequate funds for data collection and untimely submission of reports from some decentralized departments.

- Inadequate logistics (computers, laptops, vehicle) for departments and units.

- Inadequate and untimely release of funds for implantation activities.

## Update on Critical Development and Poverty Issues

This section discusses programs and intervention to protect the vulnerable and the marginalized in the society who are most often considered the poor as well. These interventions are necessary to cushion the target group from socio-economic shocks. The District Planning Unit, together with the Department of Social Welfare and Community Development administer the social interventions in the district. The major social protection interventions in the district are Livelihood Empowerment against Poverty (LEAP), interventions for the disabled, school feeding programs, Capitation Grant, NHIS, 1D1F, Free SHS and Agricultural programmes.

Table 7: Update on Critical Development and Poverty Issues

| Critical Development and Poverty Issues | Allocation GH¢ | Actual receipt GH¢ | No of beneficiaries |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Targets | Actuals |
| Ghana School Feeding Programme | 3,942,000.00 | 3,377,715.84 | 18,000 | 16,066 |
| Capitation Grants | 245,130.00 | N/A | 24,513 | NA |
| National Health Insurance Scheme | NRD | NRD | 83,408 | Total=56821 Male= 23644 Female = 33177 |
| Livelihood Empowerment Against Poverty (LEAP) programme | 235,195.67 | 235,195.67 | 1306 | Total=1306 Male = 197 Female = 1109 |
| National Youth Employment Program | N/A | N/A | N/A | N/A |
| One District-One Factory Programme | N/A | N/A | 5 | 5 |
| Planting for Food and Jobs Programme | 7,000 | 7,000.00 | 120 | M – 84 F – 14 T- 98 |
| Free SHS Programme | 1,848,946.22 | 232,640.25 | 2640 | T- 3300 |
| Common fund for persons with disability | 149,008.02 | 106,443.63 | 100 | Total =76 Male = 32 Female =44 |

N/A1 - Not Applicable				N/A – Not Available     NRD- No reliable data

According to the data presented in Table 6, the Assembly executed eight interventions aimed at tackling critical development and poverty issues identified in the district during the reviewed year. For all these interventions, the Assembly saw some level of success.

The free SHS policy is ongoing with the numbers increasing every year.

Consequently, information concerning the costs of NHIS programs is not accessible to the Assembly sometimes very difficult to get. As a resolution, the Assembly suggests that the NDPC take up this matter with the relevant ministries to ensure that the expenditure on such interventions is disclosed to the Assembly through the respective mother Ministries.

### School Feeding Programme (SFP)

The introduction of the School Feeding Programme with the objective of providing one hot meal for every school child during school periods, has contributed to improved enrolment and retention in basic schools. The programme subsequently underwent re-organization with the primary objective of improving its targeting mechanism and prioritizing it for the benefit of the most deprived areas.

The School Feeding Programme (SFP) has so far benefited 16,066 as against 18,000 estimated targets for the year 2023. The number of beneficiary pupils was the same as 2022. Though there was an increase in the number of pupils fed under the Programme however the Assembly could not meet its target within the year.

### Livelihood Empowerment Against Poverty (LEAP) programme

The LEAP programme continues to provide conditional and unconditional cash transfers to the extremely poor households who have no viable alternatives to meet their basic needs and have limited capacity to earn a living. It covers the elderly poor, persons with severe disabilities and children in difficult circumstances. The cash transfer is to empower these households to provide for their basic needs and to help them participate in the socio-economic development of the country. The total amount of cash transferred to beneficiaries was estimated at GH¢235,195.67 to 1,306 beneficiaries in the year 2023.  The Assembly was able to disburse an amount of GH¢ 235,195.67 to 1, 2971, beneficiaries including 1,109 females and 197males.

### Planting for Food and Jobs Programme

The modernization of the agriculture sector was projected to be an important driver of growth to improved productivity and to create employment to the youth. The Assembly was therefore projected an amount of GH¢7,000 to a total beneficiary of 120. Assessment of progress in 2023 shows an overall amount of GH¢7,000 to a total beneficiary of 98 which shows a reduction in funds allocation as compared to the year 2022. The relatively reduction of the performance in 2023 can be attributed to the government not sponsoring the flagship programme. However, the District Assembly was able to purchase Eight (8) bags of 45kg Abontem seed mazie from AgroCrown CO.LTD-Kumasi to continue the flagship program for 2023. Chemicals were available for farmers who report to control the Fall Army Infestation. Most maize fields recovered from the infestation after spraying.

### Capitation Grant

The Shama District Assembly Estimated that 24,513 of its people will benefit from the Capitation grant for the 2023 academic year however, at the end of the year 2023 the office could not provide any relevant information on such programme.

### Common Fund for Persons with Disability

As part of the effort to reduce incidence of unemployment among the People with Disability (PWDs), the Shama District Assembly estimated an amount of GH¢162,936 in support of 67 beneficiaries to acquired various training in artisans. At the end of the year 2023, GH¢106,443.63 was received and the Assembly supported 76 Persons with Disability.

Table 7 - Staff Strengths of MMDAs

| SHAMA DISTRICT ASSEMBLY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | REQUIREMENT |  | ACTUAL |  | TRAINING |
| DEPARTMENT | MINIMUM | MAXIMUM | 2023 | %COVERED | REQUIRED |
| Central Administration | 96 | 128 | 95 | 100 | Course in Local Government Administration, Report/Speech writing, Event management |
|  |  |  |  |  | Report Writing Skills, and Interrogation Skills |
|  |  |  |  |  | Database System Programming, Introduction to Project Management, A course in Local Government Administration |
|  |  |  |  |  | Research Methods and Impact Assessment, project Proposal Writing and Reporting, induction Training; |
|  |  |  |  |  | Records Management, Office Management and Practice, Introduction to Ghana’s Public Administration System |
|  |  |  |  |  | Defensive Driving, Traffic Regulations and Transport Policies, Management and Vehicle Maintenance |
|  |  |  |  |  | Continuous Professional Development in Statistics, Statistical Information Course, I CT (Data Management and Analysis) |
| Agriculture | 43 | 72 | 11 | 100 | Administrative and Staff Management, Administrative and Staff Management, |
|  |  |  |  |  | Business Entrepreneurship, Intermediate Agricultural Administration |
| Works | 49 | 70 | 11 | 100 | Contract Administration and Procurement, Basic Management Practices, Design and supervision of works |
| Social Development (Social Welfare & Comm. Dev't) | 10 | 11 | 9 | 100 | Conflict resolution and Peace Building, Participatory Development Planning, Public Social Development Policies |
| Health / Environmental health | 76 | 113 | 11 | 100 | Public health administration, Health and Safety Course, Environmental Management, Environmental Health and Sanitation Policy and practice, Environmental Management |
| Physical Planning | 15 | 21 | 7 | 100 | Induction training, Development Planning Programmes, A Course in Local Government Administration |
| BAC | 11 | 17 | 1 |  |  |
| Finance | 21 | 33 | 5 | 100 | Financial Planning and Control; Course in Local Government Administration; and ICT |
| NADMO | 54 | 89 | 19 | 100 | Course in Disaster management, health, and safety |

Source: HR Department

The table presents a comprehensive overview of the training needs requirement of the various department of the district. It is believed that the departments would function beyond expectation when these department specific trainings are provided.

Table 8: Staff Strengths of MMDAs (Trainings and Workshops)

| NAME OR TYPE OF THE CAPACITY DEVELOPMENT | VENUE/LOCATION | PURPOSE OF THE PROGRAMME | SOURCE OF FUNDING | FACILITATORS | TARGET GROUP | NO OF BENEFICIARIES |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | TOTAL | MALE | FEMALE |
| Defensive Driving | D/A Conference Room | To ensure Drivers and City Guards are aware of potential hazards and other road users around them | IGF/DACF | Dist. Road Safety Officer | Drivers/City Guards | 27 | 24 | 3 |
| LGS Protocols | The Church of Pentecost | To equip them with knowledge on the LGS Protopcols | IGF/DACF | Assist. Dir. IIA/SNR HRM | All Staff | 94 | 55 | 39 |
| The 2022 LGS Records Mgt. Manual | The Church of Pentecost | To ensure effective and efficient records keeping | IGF/DACF | RHRM | All Staff | 105 | 57 | 48 |
| Training on the new Client Service Manual | The Church of Pentecost | to ensure proper and effective magt. Of complaints, enquiries and feedback in the Assembly | IGF/DACF | RHRM | All Staff | 112 | 59 | 53 |

Source: HR Department

The table provides details on different capacity development programs conducted by the Shama District Assembly, covering various topics and targeting specific groups. A Defensive Driving techniques training was organized for all drivers working in the Assembly. At the end of the training, about 27 drivers were trained on road safety awareness. All staff of the Assembly were also trained on LGS Protocols which was to enhance staff knowledge on these set protocols in order to efficiently carry out their duties as technocrats in the district.

In summary, the Shama District Assembly has organized diverse capacity development programs targeting different aspects of operations, ranging from road safety to record management and client service. The distribution of beneficiaries reflects a commendable effort in ensuring inclusivity and gender diversity in training initiatives. The funding from IGF/DACF indicates a commitment to using internal resources for staff development.

Table 9: Staff Strengths of MMDAs (Logistics)

| REQUIRED | REQUIRED | ACTUAL | REMARKS |
| --- | --- | --- | --- |
| Computers | 80 | 26 | Some offices have no desktop to allow office work to go on smoothly. This affects productivity. It again piles up work of the office in offices with none or just one desktop. In such situations, report submission goes beyond deadlines. |
| Printers | 30 | 14 | Some offices move to other offices to print. The exchange of pendrives sometimes corrupts official information through virus attacks. |
| Projectors | 3 | 1 | The assembly sought for projector outside for programs which is sometimes difficult |
| Office Space | 35 | 18 | Some departments have been merged. Typical are NCCE and CHRAJ, birth and death merging with national service. Radio room merging with drivers. Office complex is currently under construction |
| Vehicle | 15 | 7 | Departments sometimes find it difficult to get vehicles to work when the three functional ones are not available. The functional ones are the DCE’s vehicle, the coordinating director’s vehicle, and one Nissan patrol. |

## Evaluations Conducted, their Findings and Recommendations

In the year under review, one (1) major evaluation was conducted by the Assembly in collaboration with other/ user agencies. The facilities used for the evaluation included Shama Methodist School and the Evaluation was to ascertain whether access to quality education has improved after Construction of 6-unit Classroom block been successfully completed 10 years after. (2013 -2023). The details of the evaluation are presented in Table 7 below.

Table 9: Evaluations Conducted

| Name of the Evaluation | Policy/Programme/Project involved | Consultants or Resource Persons involved | Methodology Used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Impact Evaluation (To ascertain whether access to quality education has improved after Construction of 6-unit Classroom block been successfully completed 10 years after. (2013 -2023.) | Construction of 6 – unit classroom block at Shama Methodist | DPCU/CIDA | - Key Informants Interview - Focus Group Discussions - Observation | - The facility is providing quality education to the people. - Evidence of increase in school going rate - Evidence of broken windows and door | - The Assembly should ensure regular maintenance of the facility. |

Source: DPCU

## Participatory M&E Undertaken and Their Results

Participatory Monitoring and Evaluation is a process through which stakeholders at various levels engage in monitoring and evaluation of a particular project, programme, or policy, share control over the content, the process, the results of the monitoring and evaluation activity and engage in decision making or corrective actions.

During the period under review, District Planning Coordinating Unit (DPCU) was supported by Friends of the Nation (FoN) and the tools used for the PM&E were beneficiary assessment, impact assessment, and community Score Card approach involving conversational interviews and focus group discussions to assess the value of the construction of some selected DACF-RFG projects in the District and School feeding Flagship Program. These projects include:

- Renovation of Shama Market

- Construction of 1 No.2 Unit KG Block with Office, Kitchen and Urinal/ Toilet Facilities and Furniture for Anto/Aboso D/A Primary School.

- Construction Of 1 No.3 Unit Classroom Block with Ancillary Facilities at Assorko.

- Impact of School Feeding Programs on Basic school education in the district.

The objective of the Participatory M&E exercise was to assess the impact of the utilization of the Assembly’s share of revenue on projects as perceived by project beneficiaries and as well to integrate findings into project activities. Details of the results/findings are presented in Table 10 below. The feedback from the stakeholders has been incorporated in the processes of the Assembly and generally, governance is enhanced.

Table 10: PM&E Conducted

| Name of the PM&E Tool | Policy/Programme/Project involved | Consultants or Resource Persons involved | Methodology Used | Findings | Recommendations |
| --- | --- | --- | --- | --- | --- |
| Beneficiary Assessment | Renovation of Shama Market | DPCU Friends of the Nation (CSO) Assembly Members Market queens | Observations. Transit walk. Beneficiary Interviews | - The project was captured in the 2023 Annual Budget and 2023 Annual Action Plan. - The project was duly completed and in use. - There is no Security light at the market. - No storage facility at the market - Inadequate place of convenient | - The Assembly Should install Security lights at the market. - Plans should be made to construct a Storage facility for the Market. - Assembly should construct additional place of convenient for the market. |
| Community score card | Construction of 1 No.2 Unit KG Block with Office, Kitchen and Urinal/ Toilet Facilities and Furniture for Anto/Aboso D/A Primary School. | DPCU Friends of the Nation (CSO) Assembly Members Headteacher Chief Opinion Leaders | Observation Questions and answers, Interviews, Focus group discussion, stakeholder, and interface meetings | - The project was captured in the 2023 Annual Budget and 2023 Annual Action Plan - Project initiation and planning was done in consultation with community members. - Project board indicating basic details of the project is mounted. - The project was completed and in use. - Inadequate furniture. - Poor condition of access road to the project site. | - Additional furniture should be added to the already existing ones. - The access road to the site should be reshaped. |
| Impact Assessment | Impact of School Feeding Programs on Basic school education in the District. | DPCU Friends of the Nation (CSO) Assembly Members Chief Opinion Leaders | Observation Interviews. | - Increase in enrollment. - Queuing for food. - Poor Nutritional Value. - Delay in serving of food. - Break time eats into contact time. - Delay in release of funds. - Food is not served a hygienic environment | - Matrons should employ additional staff. - Continuous Monitoring by School Feeding Secretariat. - Funds should be released on time. |
| Midterm evaluation | Construction Of 1 No.3 Unit Classroom Block With Ancillary Facilities at Assorko | - DPCU - Friends of the Nation (CSO) - Assembly Members - Chief - Opinion Leaders | Observations. Transit walk. Beneficiary Interviews | - The project was captured in the 2023 Annual Budget and 2023 Annual Action Plan. - There was no contractor on site. - There were materials on site. - Project initiation and planning was done in consultation with community members. - There was no project board mounted for information on the project. - Poor condition of access road to the project site. - The date of completion is behind schedule. - Project site is weedy. - There were 2 additional constructions on-going at the project site. | - The contractor project should be urged to complete the project as it is behind schedule. - Project board with basic information about the project should be mounted. - Access road to the project site should be reshaped |

# CHAPTER THREE

# THE WAY FORWARD

## 3.1. Introduction

The chapter presents key issues addressed, yet to be addressed, and recommendations made towards the improvement of monitoring and evaluation of programmes and projects in the District.

### 3.2. Key Issues Addressed and yet to be Addressed.

### 3.2.1. Key Issues Addressed

Some of the major development issues that were addressed during the year under review are enumerated as follows:

- Inadequate involvement of community representatives, and other key stakeholders in project implementation was conveniently addressed by decentralizing the engagement to Area Council level.

- Project Resuscitation Meeting. A meeting with contractors to streamline the continuation and completion of forestalled projects.

- Improved projects/programmes execution. This was addressed through enhanced site visits, site meetings and community involvement in the implementation and management of projects.

- Avoiding of delays in implementation of projects/programmes. This has been partially addressed as the Assembly resolved to tackle projects that it could conveniently complete with the limited funding challenge in view.

- Internal Revenue Mobilisation weaknesses. Management of Assembly together with subordinates embarked on revenue mobilisation taskforce every quarter of 2023.

- Inauguration and training of members of the Substructures. The Assembly took pragmatic steps to ensure that the district sub structures are well positioned to discharge their mandate effectively. After the training, the Assembly took a decision to delegate its role of collecting market tolls and property rates to the Unit Committees and pursue the construction of the Area Council Offices.

- Improved Sanitation especially along the coastal towns/communities in the district and this has improved a great deal in the year under review.  The district is being supported to organize competition in the various communities to award best clean communities. This project is funded by the Friends of Nation. Through this project, the level awareness about the dangers of poor sanitation along the beaches has improved tremendously and communities are taken serious steps to ensure that their communities are clean.

- All the children in homes under the care of Social Welfare have been enrolled in schools.

### 3.2.2. Issues yet to be addressed.

Upgrading of roads.

The district is yet to address issues of deplorable nature of main roads from Shama Junction to Shama Town and some feeder roads linking most communities.

Delay in release of funds.

The issue of delay in the release of funds for programmes implementation and the deductions from source are yet to be addressed. However, the District has made steps in improving the Internally Generated Funds. A few strategies have also been put in place to improve revenue performance.

GETFund Projects

There are abandoned GETFund projects that have not been completed.

Absence of a Dedicated Vehicle for Project Monitoring

The Absence of a Dedicated Vehicle for Project Monitoring for the MPCU to enable it to embark on the monitoring and evaluation of projects is also yet to be addressed by the Assembly.

## 3.3. Recommendations

The monitoring and evaluation exercises conducted by the District Planning Coordinating Unit and the District Works Department respectively, revealed a few challenges of the team and with the implementation of physical projects in the District.

These challenges included capacity building of staff, poor condition of roads leading to most project sites, delay in the execution of projects particularly funded by the District Assemblies Common Fund delay in execution of projects among others.

The following recommendations were therefore made based on the challenges identified for the consideration of the Management of the Assembly.

- Land for development projects should be documented to prevent future litigations against the Assembly.

- The Assembly must collaborate with government authorities, Quarry companies, and other stakeholders to upgrade the poor nature of linking roads in the district.

- Climate change intervention should be considered in project implementation.

- Steps must be taken to ensure projects are completed within time schedule.

- Ensure timely release of funds to enable the Assembly to complete all planned programmes and projects is also recommended.

## 3.4. Conclusion

The year 2023 has demonstrated remarkable performance compared to 2022, attributed to reassessing strategic decisions and implementing program strategies. The challenges posed by the nationwide Economic Hardship prompted ingenuity, innovation, and strategic thinking in executing programs and projects. This led to the efficient use of resources, time, and space, particularly in achieving value for money.

However, the consistent deductions of the District Assemblies Common Fund (DACF) from the source and delays in its release pose significant threats and concerns to the district. These challenges impact the timely and high-quality implementation of programs and projects, hindering the fulfilment of tasks on schedule. Despite the aspiration to implement all projects outlined in the 2023 Annual Action Plan (AAP), these aspirations were hampered by unfortunate delays in fund disbursement.

Citizen engagement faced challenges due to government restrictions stemming from the COVID-19 pandemic, limiting various activities, especially comprehensive citizen involvement. Furthermore, some departments experienced difficulties as they did not receive government subventions, particularly in the third and fourth quarters.

Going forward, there is a need to enhance the District Assembly's capacity in revenue mobilization to increase the funds collected, ultimately improving service delivery, and supporting various departments. While the Assembly is implementing pragmatic strategies to boost internal revenue for its programs and projects in the upcoming year, it is also anticipated that the Central Government will allocate increased resources. The Assembly has identified innovative approaches, such as proposal writing, to generate funds, resulting in notable successes. The full cooperation of all stakeholders is sought to achieve the goals of delivering quality health, education, and water services to citizens, ultimately improving the general well-being of the served population.

APPENDICES

Appendix 1: Projects Status - Updated Project Register As At December, 2023

| Project Description |  | Development Dimension | Location | Contractor | Contract Sum | Date of Award | Source Of Funding | Date Started | Expected Date Of Completion | Expenditure to Date | Out Standing Balance | Implementation Status |  | Strategies To Improve Project Completion Rate | How Citizens were involved in monitoring of works contract | Remarks Summary on land acquisition and resettlement |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Code | Name |  |  |  |  |  |  |  |  |  |  | % | Pictures |  |  |  |
|  | Renovation Of Shama Market – Shama, Western Region | Economic Development | Shama | M/S EAK CO. LTD. | 160,300.00 |  | DACF-RFG | 15/03/2022 | 14/09/2022 | 156,292.50 | 4,007.5 | 100% |  | The assembly will intensify revenue collection to gather more revenue for IGF projects. Reminder will be sent to the GETFUND secretariate on FETFUND projects. Certificates will be honoured without delay when contractors raises them for payment | Planning, monitoring, execution of project | NA |
|  | Continue and Complete the Construction of 80 capacity market shed, 20 lockable stores and crèche | Economic Development | Upper Inchaban | I.B Clements Co. Ltd. | 651,245.86 |  | IGF | 02/10/2019 | 01/10/2020 | 33,583.96 | 617,661.90 | 15% Complete (On-going) |  |  | Planning, monitoring, execution of project | NA |
|  | Construction Of 1 No.3 Unit Classroom Block With Ancillary Facilities | Social Development | Assorko | M/S EAK CO. LTD. | 303,500.00 |  | DACF-RFG | 15/03/2022 | 14/09/2022 | 121,097.19 | 182,402.81 | 65% |  |  | Planning, monitoring, execution of project | NA |
|  | Construction Of 1 No.2 Unit Kg Block With Office, Kitchen And Urinal/ Toilet Facilities And Furniture For Anto D/A Primary School | Social Development | Anto-Aboso D/A Primary School | M/S POWERFUL VENTURES LTD. | 473,800.00 |  | DACF-RFG | 15/03/2022 | 14/09/2022 | 346,458.46 | 127,341.54 | 100% |  |  | Planning, monitoring, execution of project | NA |
|  | Const. Of 1 No.4 Unit Semi-Detached Chamber & Hall Teachers Quarters | Social Development | Shama Ridge | M/S EAK CO. LTD. | 449,500.00 |  | DACF-RFG | 15/03/2022 | 14/09/2022 | 268,236.43 | 181,263.57 | 65% |  |  | Planning, monitoring, execution of project | NA |
|  | Construct CHPS Compound with a Maternity Block And Nurse Quarters | Social Development | Abuesi | Eagle Talons Ltd. | 479,034.36 |  | MPHF | 06/11/2019 | 05/11/2020 | 275,915.35 | 203,119.01 | 51.2% Complete (On-going) |  |  | Planning, monitoring, execution of project | NA |
|  | Continue and Complete the Construction of 6 Unit Classroom Block | Social Development | Atta ne Atta | Messrs Sima Plus | 222,320.64 |  | DACF | 02/06/2015 | 03/12/2015 | 172,028.51 | 50,2 | 95% Completed (Toilet left) |  |  | Planning, monitoring, execution of project | NA |
|  | Rehabilitation of 6-Unit Classroom Block (Lot 4) | Social Development | Shama Methodist Primary | Confidence Traders & Hardware Co. Ltd. | 120,836.18 |  | GETFUND | 04/10/2016 | 05/02/2017 | - | - | 75% Complete |  |  | Planning, monitoring, execution of project | NA |
|  | Rehabilitation of 6-Unit Classroom Block (Lot 5) | Social Development | Shama Model D/A Primary | Asanoc Construction Limited | 121,692.72 |  | GETFUND | 04/10/2016 | 05/02/2017 | - | - | 60% Complete (Joinery & Painting stage reached) |  |  | Planning, monitoring, execution of project | NA |
|  | Construction of 1No. 2-Storey6-Unit Classroom Block with Ancillary Facilities (Lot 1) | Social Development | Aboadze Islamic Primary | Erns Developers Limited | 348,806.33 |  | GETFUND | 04/10/2016 | 05/02/2017 | - | - | 67% Complete (Super-structure block complete to Gable) |  |  | Planning, monitoring, execution of project | NA |
|  | Construction of 1No. 2-Storey6-Unit Classroom Block with Ancillary Facilities (Lot 2) | Social Development | Shama Junction D/A Primary | Progrev Company Limited | 350,891.63 |  | GETFUND | 04/10/2016 | 05/02/2017 | - | - | 35% Complete ( Over site and concrete column) |  |  | Planning, monitoring, execution of project | NA |
|  | Continue and Complete the Construction of 3 Unit Classroom Block Kedzi Kran, | Social Development | Kedzi Cran, | Nakopong Co. Ltd. | 180,882.45 |  | GETFUND | 10/10/2016 | 11/07/2017 | - | - | 41% |  |  | Planning, monitoring, execution of project | NA |
|  | Continue and Complete the Construction of 3 Unit Classroom Block Abuesi | Social Development | Abuesi | Assess Aba Ghana Limited | 180,407.31 |  | GETFUND | 15/12/2016 | 16/06/2017 | - | - | 25% Complete (Over site Concrete stage) |  |  | Planning, monitoring, execution of project | NA |
|  | Continue and Complete the Construction of 3 Unit Classroom Block Old Daboase | Social Development | Old Daboase | 13:05 Engineering & Construction Company Limited | 180,689.48 |  | GETFUND | 22/12/2016 | 23/06/2017 | - | - | 45% |  |  | Planning, monitoring, execution of project | NA |
|  | Continue and Complete the Construction of 3 Unit Classroom Block Ohiamadwen | Social Development | Ohiamadwen | A-Plus Construction Company Limited | 180,578.57 |  | GETFUND | 22/12/2016 | 23/06/2017 | - | - | 55% Complete (Gable level stage) |  |  | Planning, monitoring, execution of project | NA |
|  | Construction of Community park with ancillary facilities at Upper Inchaban | Social Development | Upper Inchaban | US Global Co. Ltd | 549,646.38 |  | DACF-RFG | 02/10/2019 | 01/10/2020 | 373,481.61 | 176,164.77 | 67% Complete (On-going) |  |  | Planning, monitoring, execution of project | NA |
|  | Construction of Community Centers | Social Development | Asem-Asa No.2, | Adumeku Company Ltd | 131,147 .10 |  | MPCF | 30/07/2018 | 29/07/2019 | 101,603.46 | 29,543.64 | 99% Complete (installation of ECG Meter |  |  | Planning, monitoring, execution of project | NA |
|  | Construction of Community Centers | Social Development | Supomu Dunkwa, | Richlucky Co. Ltd | 111,237.06 |  | MPCF | 19/06/2015 | 22/12/2015 | 94,712.06 | 16,525.00 | 98% Complete (Finishing stage) |  |  | Planning, monitoring, execution of project | NA |
|  | Construction of Community Centers | Social Development | ,Abuesi | B.T Ventures | 507,775.73 |  | MPCF | 10/08/2015 | 12/05/2016 | 233,482.45 | 274,293.28 | 55% Complete (Roofing stage) |  |  | Planning, monitoring, execution of project | NA |
|  | Renovation of DCE’s Office & Residential Accommodation Shama | Governance, Corruption and Public Accountability | Shama | BEEKEN COMPANY LIMITED | 199,487.22 |  | DACF | 15/11/2021 | 14/05/2022 |  | - | 0% |  |  | Planning, monitoring, execution of project | NA |
|  | Continuation & Completion of District Assembly Administrative Block Phase 1 at Shama | Governance, Corruption and Public Accountability | Shama | WILLCORNAH ENTERPRISE | 234,943.78 |  | DACF | 04/07/2016 | 29/04/2017 | 90,661.03 | 144,282.75 | 89% Complete (finishing stage) |  |  | Planning, monitoring, execution of project | NA |
|  | Construct/rehabilitate Area council offices | Governance, Corruption and Public Accountability | Abuesi | Messrs E.F.B. Co. Ltd. | 76,070.25 |  | DACF | 02/06/2015 | 02/09/2015 | 32,131.73 | 43,938.52 | 43% Complete (Joinery / Finishing stage |  |  | Planning, monitoring, execution of project | NA |
|  | Repairs/Maintenance of Residential Buildings, office and vehicles | Governance, Corruption and Public Accountability | Assembly | - | 191,404.02 |  | BECH International Company Limited | 15/11/21 | 14/05/2022- | 91,149.30- | 100,254.72 | 100% |  |  | Planning, monitoring, execution of project | NA |
|  | Construct . Mechanized bole holes at Gr | Social Development | Grabodo, Komfueku and Aboso | 0 | 0.00 |  | Qatar Foundation | Jan-23 | Dec-23 | 0.00 | 0.00 | 100% |  |  | Planning, monitoring, execution of project | NA |

Appendix 2: Repair and Maintenance of Existing Infrastructure

| Asset/ infrastructure | Location | Type of maintenance | Estimated Cost | Actual Release | Gap | Expenditure | Recommendation |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Dwellings (Residential Buildings) | Shama | Internal maintenance (ie plumbing, electrical, carpentry etc) | 26,274.62 | 26,274.62 |  | 26,274.62 | Maintenance successfully done. Assembly should put in place mechanisms for regular checks to ensure the execution of quick repairs and maintenance works on infrastructure |
| Non-Residential Buildings | Selected Communities | General Maintenance | 305,048.00 | 305,048.00 |  | 305,048.00 |  |
| Machinery & Equipment’s | Shama District Assembly | General Maintenance | 11,806.24 | 11,806.24 |  | 11,806.24 |  |
| Maintenance and Repairs – Official Vehicles | Shama District Assembly | General Maintenance | 95,827.18 | 95,827.18 |  | 95,827.18 |  |
| Roads, Driveways and Grounds | Selected Communities | Reshaping, Spot improvement | 549,750.00 | 549,750.00 |  | 549,750.00 |  |
| Repairs of Office Buildings | Shama District Assembly | General Maintenance | 2,095.00 | 2,095.00 |  | 2,095.00 |  |
| Maintenance of Furniture and Fixture | Shama District Assembly | General Maintenance | 2,000.00 | 2,000.00 |  | 2,000.00 |  |
| Maintenance of Market | Shama | General Maintenance | 10,500.00 | 10,500.00 |  | 10,500.00 |  |
| Streetlights/Traffic Light | Shama District | General Maintenance | 770.00 | 770.00 |  | 770.00 |  |
| Maintenance of Computer Software | Shama District Assembly | Software Maintenance | 6,352.00 | 6,352.00 |  | 6,352.00 |  |

Appendix 3: Programme register

| S/N | Programme Description | Development Dimension Of Policy Framework | Amount Involved Sum Gh¢ | Source Of Funding | Date Started | Expected Date Of Completion | Expenditure To Date | Out Standing Balance | Implementation Status (%) |  | Total Beneficiaries | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | % | Picture (if any) |  |  |
| 1 | Build capacity of revenue collectors and managers and Data collection on Temporal Structures within the District (Statistics) | Economic Development | 8,958.00 | IGF/Donor (FoN) | May-23 | Aug-23 | 7,264.00 | 1,704.00 | 100% |  | Districtwide | Completed |
| 2 | Procure revenue collection and management logistics | Economic Development | 23,000.00 | IGF | 05/05/2022 | 13/12/2023 | 18,500.00 | 4,500 | 100% |  | 25 | Completed |
| 3 | Resource and empower the Revenue Mobilisation task force | Economic Development | 5,000.00 | IGF | 03/02/2023 | 16/11/2023 | 5,000.00 | 0 | 100% |  | 25 | On-going |
| 4 | Organize public sensitization on revenue mobilization of the Assembly | Economic Development | 5,000.00 | IGF | 17/01/2023 | 05/12/2023 | 5,000.00 | - | 100% |  | 25 | Completed |
| 5 | Organize Annual Public Forum on tax compliance | Economic Development | 10,000.00 | IGF | 23/11/2023 | 28/11/2023 | 10,000.00 | - | 100% |  | 40 | Completed |
| 6 | Pay regular visits to Trade Organizations in the District. | Economic Development | 10,000.00 | DACF | 18/03/2023 | 07/10/2023 | 10,000 | - | 100% |  | 72 | Completed |
| 7 | Training of Area Council Executives on Revenue Mobilization | Economic Development | 30,000.00 | DACF | 15/03/2023 | 14/10/2023 | 20,000.00 | 10,000.00 | 100% |  | 32 | Completed |
| 8 | Conduct Radio Sensitization on Revenue Mobilization and Performance of the Assembly | Economic Development | 5,000.00 | IGF | 01/06/2023 | 21/12/2023 | 5,000.00 | - | 100% |  | District Wide | Completed |
| 9 | Play Revenue Jingles on various Community Information Centres | Economic Development | 1,500.00 | IGF | 01/12/2022 | 31/12/2022 | 1,500.00 | - | 100% |  | District Wide | Completed |
| 10 | Implement the GIFMIS System and introduce sanctions(bye laws) | Economic Development | 8,000.00 | IGF | 02/12/2022 | 30/12/2022 | 8,000.00 | - | 100% |  | District Wide | Completed |
| 11 | Mount revenue performance and accountability bill boards | Economic Development | 4,000.00 | IGF/Donor (FoN) | 02/02/2023 | 23/09/2023 | 4,000.00 |  | 100% |  | RATE PAYERS | completed |
| 12 | Provide incentives to revenue collectors | Economic Development | 3,000.00 | IGF | 02/02/2023 | 19/12/2023 | 3,000.00 |  | 100% |  | RATE PAYERS | Completed |
| 13 | Encourage and enhance the security of transactions on mobile money | Economic Development | 6,000.00 | Donor (FoN) | 02/02/2023 | 17/12/2023 | 6,000.00 | - | 100% |  | 6 Area councils | completed |
| 14 | Organize Local Economic Development (LED) Committee meetings. | Economic Development | 24,000 | IGF | 09/02/2023 | 23/11/2023 | 24,000.00 |  | 100% |  | 11 | Completed |
| 15 | Develop a database of trained apprentices and artisans within the District | Economic Development | 5,000.00 | Donor ( Master Card Foundation) | 07/06/2023 | 16/11/2023 | 5,000.00 |  | 100% |  | 105 | On-going |
| 16 | Establish marketing links between producers and buyer companies | Economic Development | 4,200.00 | IGF | 17/08/2023 | 17/08/2023 | 4,200.00 | - | 100% |  | 12 | Completed |
| 17 | Organize trade exhibition shows for SMEs | Economic Development | 2,000.00 | IGF | 03/10/2023 | 17/11/2023 | 2,000.00 | - | 100% |  | 54 | Completed |
| 18 | Establish a District Apprentice Recruitment Agency (SDG Target 17.18) | Economic Development | - | 0 | 05/05/2023 | 0 | - |  | 0 |  | 0 | Yet to start |
| 19 | Establish a Modern Industrial Park | Economic Development | 100,000.00 | Donor (Free Zone) | 25/07/2022 | 29/07/2023 | 0.00 | - | 3% |  | District Wide | On-going |
| 20 | Train Artisans on the manufacturing of “cook stoves” | Economic Development | 10,000.00 | IGF/Donor (HURDs) | 08/10/2023 | 08/10/2023 | 10,000.00 |  | 100% |  | 50 | Completed |
| 21 | Strengthen SMEs capacities for enhanced operations (e.g. Soap making, baking, wielding, hairdressing, etc.) | Economic Development | 5,000.00 | IGF | 09/10/2023 | 16/09/2023 | 5,000.00 | - | 100% |  | 70 | Completed |
| 22 | Promote the formation of “ Village Savings and Loans Associations (VSLA) | Economic Development | 2,000.00 | IGF | 24/07/2022 | 23/12/2022 | 2,000.00 | - | 100% |  | 105 | Completed |
| 23 | Collaborate with Financial Agencies to provide soft loans to Small and Medium Scale Businesses | Economic Development | 10,000.00 | DACF | 08/10/2022 | 09/07/2022 | 10,000.00 | - | 100% |  | 40 | Completed |
| 24 | Establish a District Local Economic Development (LED) Platform. | Economic Development | 5,000.00 | IGF | 15/06/2022 | 17/11/2022 | 5,000.00 | - | 100% |  | 108 | Completed |
| 25 | Support Businesses to form Vibrant Groups, Cooperatives and Local Partnership | Economic Development | 2,000.00 | DACF | 02/09/2022 | 17/11/2022 | 2,000.00 |  | 100% |  | 250 | Completed |
| 26 | Create and maintain a one stop shop data base for all businesses in the District | Economic Development | 8,000.00 | Master Card Foundation | 08/10/2022 | 12/07/2023 | 7,000.00 | 1,000.00 | 89% |  | 239 | On-going |
| 27 | Assist Small and Medium enterprises to develop business proposals and link them to Financial Sources. | Economic Development | 5,430.00 | Donor (FoN) | 01/07/2022 | 30/09/2023 | 5,430.00 |  | 76% |  | 46 | On-going |
| 28 | Conduct yield studies on selected crops (rice, maize, cassava and plantain) | Economic Development | 0 | CSIR Sekondi Agric Regional Office | 04/04/2023 | 14/11/2023 | - | - | Successfully implemented |  | 24 Rice farmers (Whin-Valley, Anto) | Completed |
| 29 | Conduct demonstration and field days on improved technologies | Economic Development | 2,345.00 | MAG | Jan-23 | Dec-23 | 2,345.00 |  | 100 |  | District Farmers | Completed |
| 30 | Conduct regular farm and home visits to operational areas and facilitate activities on PJF, RFJ, PERD | Economic Development | 1,800.00 | MAG | 04/01/2023 | 31/03/2023 | 1,800.00 | - | Successfully implemented by (II) field officers |  | 2,000 farmers visited for the period January,February, March, 2023 | Completed |
| 31 | Organize campaign on Rabies, PPR, NCD and Gambro for local birds and vaccinations | Economic Development | 4,000.00 | USAID (break through) | 24/07/2023 | 03/11/2023 | 4,000.00 | - | Successfully implemented |  | 1) 262 dogs vaccinated 2) 15 cats vaccinated | Completed |
| 32 | Build capacity of livestock farmers on livestock management and IMO Technology | Economic Development | 5,046.00 | MAG | JAN.2023 | 01/12/2023 | 5,046.00 | 0 | 100% |  | livestock farmers | Completed |
| 33 | Ensure efficient system for pre-mix distribution | Economic Development | 0.00 | 0 | 01/01/2023 | 01/12/2023 | 0.00 | 0 | 100% |  |  | Completed |
| 34 | Supply of improved fish smoking facilities (Ahotor Ovens) at subsidized prices | Economic Development | 42,000.00 | IGF | Jan-23 | Dec-23 | 27,000.00 | 15,000.00 | 53% |  | Districtwide Fish Morngers | on-going |
| 35 | Train fish smokers on the usage and maintenance of Ahotor ovens | Economic Development | 6,000.00 | IGF | Jan-23 | Dec-23 | 6,000.00 | 0 | 100 |  | Districtwide Fish Smokers | Completed |
| 36 | Educate fisher folks on proper fish handling and management as well as bad fishing practices | Economic Development | 2,000.00 | IGF | 6TH MARCH,2023 | 16TH MARCH,2023 | 2,000.00 | 0.00 | 65 % |  | 308 FISHERFOLKS,234-MALES, 234-FEMALES WERE ENGAGED ACROSS THE FISHING COMMUNITIES IN THE DISTRICT. | On-going |
| 37 | Sensitize fisher-folks on healthy fish handling, illegal fishing and post-harvest loses and management | Economic Development | 2,000.00 | IGF | 7th MARCH,2023 | 7th MARCH,2023 | 2,000.00 |  | 100% |  | 6 coastal Communitoes | Completed |
| 38 | Update Database on Fishermen and fish vessels | Economic Development | 2,000.00 | IGF | 16TH-JULY,2023 | 30TH-JULY,2023 | 2,000.00 | 0.00 | 78% |  | 154 - NEW CANOES/VESSELS WERE REGISTERED IN THREE FISHING COMMUNITIES. THE CANOE REGISTER BOOK MUST BE VALIDATED. THERE ARE GHOST NAMES. | On-going |
| 39 | Facilitate the elections of landing beaches executives | Economic Development | 2,000.00 | IGF | 23/08/2023 | 23/08/2023 | 2,000.00 |  | 100% |  | Coastal communities | Completed |
| 40 | Establish a Modern Commercial Fish Market | Economic Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Yet to start |
| 41 | Organize Accountability Forum for Landing Beaches | Economic Development |  |  |  |  |  |  |  |  |  |  |
| 42 | Document all landing beaches in the District. | Economic Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Yet to start |
| 43 | Expand the tourism sector through investment, innovation, and pursuit of service excellence | Economic Development |  |  |  |  |  |  |  |  |  |  |
| 44 | Promote public-private partnerships for investment in the tourism (SDG Target 17.17) | Economic Development | 0 | Donor(CoDA) | 02/03/2023 | 16/11/2023 | - | - | 28% |  | 0 | On-going |
| 45 | Develop available and potential sites to meet international standards and promote local tourism and (SDG Target 8.9) | Economic Development | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | Yet to start |
| 46 | Develop a comprehensive database on all tourist sites | Economic Development | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | Yet to start |
| 47 | Promote “culture” as a tourist attraction | Economic Development | 0 | 0 | 02/03/2023 | 16/11/2023 | 0 | 0 | 0 |  | 0 | Yet to start |
| 48 | Facilitate the training of tourist guides and other personnel in tourism and hospitality management | Economic Development | 0 | 0 | 02/03/2023 | 16/11/2023 | 0 | 0 | 0 |  | 0 | Yet to start |
| 49 | Develop Shama Estuary | Economic Development | 0 | 0 |  |  | 0 | 0 | 0 |  | 0 | Yet to start |
| 50 | Partner the Private Sector to Develop Beach Resorts along the Coast | Economic Development | 0 | Donor(CoDA) | 02/03/2023 | 16/11/2023 | - | - | 23% |  | 0 | On-going |
| 51 | Conferences, Workshops and Seminars for Director of Education | Social Development | 8,000.00 | Ministry of Education (MOE) | Jan-23 | August, 2023 | 8,000.00 | 0 | 100% |  | District Education Directorate | Completed |
| 52 | Provide adequate resources for Administrative Expenses (Stationery Utilities & Fuel) | Social Development | 20,000.00 | Ministry of Education (MOE) | Jan-23 | DEC,2023 | 20,000.00 | 0 | 100% |  | District Education Directorate | Completed |
| 53 | Conduct District SPAM | Social Development | 5,000.00 | Ministry of Education (MOE) | Jan-23 | DEC,2023 | 5,000.00 | 0 | 100% |  | All schools Distritwide | Completed |
| 54 | Conduct regular monitoring and inspection of schools (private and public) and monitor educational delivery programs | Social Development | 12,000.00 | Ministry of Education (MOE) | Jan-23 | DEC,2023 | 12,000.00 | 0 | 100% |  | All schools Distritwide | Completed |
| 55 | Conduct frequent and Intermittent monitoring, visits to beneficiary schools of the school feeding Program (SFP) | Social Development | 3,000.00 | Ministry of Education (MOE) | FEB, 2023 | DEC,2023 | 3,000.00 | 0 | 100% |  | All schools Distritwide | Completed |
| 56 | Organize competition in spelling, reading and numeracy | Social Development | 5,000.00 | Ministry of Education (MOE)/DACF | Jun-23 | June, 2023 | 5,000.00 | 0 | 100% |  | 7 selcted schools | Completed |
| 57 | Organize “My first day at school” ceremony in all KG and Primary one schools | Social Development | 4,000.00 | DACF | Jan-23 | Jan-23 | 4,000.00 | 0 | 100% |  | Selected basic schools | Completed |
| 58 | Organize Independence Day Celebration and debate | Social Development | 120,000.00 | DACF/IGF | 06/03/2023 | 06/03/2023 | 120,000.00 | 0 | 100% |  | Six Area Councils | Completed |
| 59 | Organization of District Mock for all final year pupils in JHS 3 | Social Development | 4,000 | DACF/IGF | April, 2023 | MAY, 202 | 4,000 | 0 | 100% |  | all JHS Districtwide | Completed |
| 60 | Organize DEOC Meetings | Social Development | 10,000.00 | DACF/IGF | MARCH, 2023 | Oct-23 | 10,000.00 | 0 | 100% |  | 12 | Completed |
| 61 | Organize Sports and Cultural Activities at District and Regional level | Social Development | 5,000.00 | DACF/IGF | MARCH, 2023 | Oct-23 | 5,000.00 | 0 | 100% |  | All schools Distritwide | Completed |
| 62 | Provide Entrepreneurial Training for ICCES Students (TVET). | Social Development | 10,000.00 | DACF/IGF | APRIL, 2023 | Oct-23 | 10,000.00 | 0 | 100% |  | Selected schools | Completed |
| 63 | Organize Regional Science & Maths Clinic (STMIE) | Social Development | 8,000.00 | DACF | April, 2023 | June, 2023 | 8,000.00 | 0 | 100% |  | 6 students | Completed |
| 64 | Provide Scholarship to needy but brilliant students across the District | Social Development | 50,000.00 | DACF | Jan-23 | Nov-23 | 50,000.00 | 0 | 100% |  | 20 | Completed |
| 65 | Support girls by providing a life-skills development programs | Social Development | 3,000.00 | Donor (Hurds Foundation) | Jun-23 | Aug-23 | 3,000.00 | 0 | 100% |  | 25 GIRLS | Completed |
| 66 | Form gender clubs in schools and communities | Social Development | 2,000.00 | Donor (Gender in Focus) | Jun-23 | Aug-23 | 2,000.00 | 0 | 100% |  | 8 schools | Completed |
| 67 | Organize Community sensitization on Back to School / Re-Entry Policy. | Social Development | 6,000.00 | Donor (Hurds Foundation) | Jan-23 | Mar-23 | 6,000.00 | 0 | 100% |  | 10 communities | Completed |
| 68 | Equitable distribution of health workforce | Social Development | 8,000 | MOH | Jan-23 | Dec-23 | 8,000 | 0 | 100% |  |  | Completed |
| 69 | Train indigines of Shama District in health disciplines to augment workforce | Social Development | 1,000 | MOH | Jan-23 | Dec-23 | 1,000 | 0 | 100% |  |  | Completed |
| 70 | Procure health equipment for various health facilities | Social Development | 40,000 | MOH | Jan-23 | Dec-23 | 20,000 | 20,000 | 70% |  | Health Facilities Districtwide | On-going |
| 71 | Procure pick-ups for all sub districts and District Health Directorate | Social Development | 0 | 0 | Jan-23 | Dec-23 | 0 | 0 | 0 |  |  | Yet-to-start |
| 72 | Procure motorbikes for all health facilities | Social Development | 50,000 | 0 | Jan-23 | Dec-23 | 0 | 0 |  |  |  | Yet-to-start |
| 73 | Provide family services | Social Development | 2,000.00 | MOH | Jan-23 | Dec-23 | 2,000.00 | 0 | 100% |  | DistrictWide | Completed |
| 74 | Establish adolescent clubs in schools and communities | Social Development | 2,000.00 | Donor (Hurds Foundation) | Jan-23 | May, 2023 | 2,000.00 |  | 100% |  | four basic schools | Completed |
| 75 | Organize Stakeholders meeting at NHIA | Social Development | 20,000.00 | NHIA | Jan-23 | Dec-23 | 20,000.00 | 0 | 100% |  | 120 | Completed |
| 76 | Registration of LEAP members | Social Development | 0 | NHIA | Jan-23 | Dec-23 | 0 | 0 | 100% |  | 56 | Completed |
| 77 | Registration school children on NHIS scheme | Social Development | 0 | NHIA | Jan-23 | Dec-23 | 0 | 0 | 100% |  | 600 | Completed |
| 78 | Radio Education on NHIS | Social Development | 3,000.00 | NHIA | Jan-23 | 01-12-202 | 3,000.00 | 0 | 100% |  | Districtwide | Completed |
| 79 | Community Sensitization/Registration on NHIS | Social Development | 5,000.00 | NHIA | Jan-23 | Dec-23 | 5,000.00 | 0 | 100% |  | Districtwide | Completed |
| 80 | Establish Community Wellness Corners | Social Development | 0.00 | MOH/DACF | Jan-23 | Dec-23 | 0.00 | 0 |  |  | Districtwide | Yet-to-start |
| 81 | Organize District wide Health Screening | Social Development | 15,000.00 | MOH/DACF | Mar-23 | Sep-23 | 15,000.00 | 0.00 | 100% |  | Districtwide | Completed |
| 82 | Procure weighing scales and infantometers for facilities | Social Development | 40,000 | MOH/DACF | Jan-23 | Dec-23 | 30,000 | 10,000.00 | 80% |  | Districtwide | On-going |
| 83 | Procure medicines for Health facilities | Social Development | 30,000 | MOH/DACF | Jan-23 | Dec-23 | 30,000 | 0.00 | 100% |  | Districtwide | Completed |
| 84 | conduct monitoring and supervision to facilities | Social Development | 8,000.00 | MOH/DACF | Jan-23 | Dec-23 | 8,000.00 | 0 | 100% |  | Districtwide health facilities | Completed |
| 85 | construct a standard DHMT Offices | Social Development | 0.00 | 0.00 | Jan-23 | Dec-23 | 0.00 | 0.00 |  |  |  | Yet-to-start |
| 86 | Operationalize the District Health committee and Community Health Management Committees | Social Development | 3,000 | MOH/DACF | Mar-23 | Jun-23 | 3,000 | 0 | 100% |  | Districtwide health facilities | Completed |
| 87 | Train health staff | Social Development | 20,000.00 | MOH | Jan-23 | Dec-23 | 20,000.00 | 0 | 100% |  | 42 nurses | Completed |
| 88 | Procure vaccines fridges and Freezers | Social Development | 25,000.00 | MOH/DACF | Jan-23 | Dec-23 | 15,000 | 10,000 | 85% |  | Districtwide health facilities | On-going |
| 89 | Create Child Welfare Clinics in all communities | Social Development | 14,000.00 | MOH/DONOR | May-23 | Dec-23 | 14,000.00 | 0 | 100 |  | 6 communities | Completed |
| 90 | Conduct TB screening in communities | Social Development | 6,000.00 | DONOR(RAAF) | May-23 | Dec-23 | 6,000.00 | 0 | 100 |  | 50 | Completed |
| 91 | Establish TB treatment centres in the district | Social Development | 50,000.00 | MOH/DACF | Jan-23 | Dec-23 | 0 | 0 | 0% |  | Districtwide health facilities | yet to Start |
| 92 | Distribute LLINs to vulnerable groups | Social Development | 2,000.00 | MOH | May-23 | Dec-23 | 2,000.00 | 0 | 100% |  |  | Completed |
| 93 | Conduct health education on Radio | Social Development | 2,000.00 | MOH/DACF | May-23 | Dec-23 | 2,000.00 | 0 | 100% |  | Districtwide | Completed |
| 94 | Train community information centre | Social Development | 7,000 | DACF | May-23 | Dec-23 | 7,000 | 0 | 100% |  | Districtwide | Completed |
| 95 | Print Health education materials | Social Development | 2,000.00 | MOH | May-23 | Dec-23 | 2,000.00 | 0 | 100% |  | Districtwide | Completed |
| 96 | Quarterly HIV/TB Review meetings | Social Development | 12,000.00 | DACF (MSHAP) | May-23 | Dec-23 | 12,000.00 | 0 | 100% |  | Districtwide | Completed |
| 97 | Half yearly DAC meetings | Social Development | 6,000.00 | DACF (MSHAP) | May-23 | Dec-23 | 6,000.00 | 0 | 100% |  | Districtwide | Completed |
| 98 | Conduct Quarterly DRMT Meeting | Social Development | 6,000.00 | DACF (MSHAP) | Jan-23 | Dec-23 | 6,000.00 | 0 | 100% |  | Districtwide | Completed |
| 99 | Assist in mobilization for HIV Activities | Social Development | 6,000.00 | DACF (MSHAP) | Aug-23 | Dec-23 | 6,000.00 | 0 | 100% |  | Districtwide | Completed |
| 100 | Intensify comprehensive education on HIV/AIDS and STIs, including reduction of stigmatization (SDG Target 3.7) | Social Development | 5,000.00 | DACF | Jan-23 | Dec-23 | 5,000.00 | 0 | 100% |  | Districtwide | Completed |
| 101 | Expand and intensify HIV Counselling and Testing (HTC) programs in the District (SDG Targets 3.3, 3.7 | Social Development | 5,000.00 | DACF | Jan-23 | Dec-23 | 5,000.00 | 0 | 100% |  | Districtwide | Completed |
| 102 | Screening of infected HIV Persons on TB | Social Development | 10,000 | DACF/DONOR (RAAF) | Feb-23 | Dec-23 | 10,000 | 0 | 100% |  | 102 | Completed |
| 103 | Organize quarterly Monitoring exercise on activities of HIV Related NGOs in the District. | Social Development | 6,000.00 | DACF | FEB, 2023 | DEC,2023 | 6,000.00 | 0 | 100 |  | 15 | Completed |
| 104 | Organize Community sensitization on Mother to Child infection | Social Development | 12,720.00 | DONOR (RAAF) | MARCH, 2023 | MARCH, 2023 | 12,720.00 | 0 | 100 |  | 50 MOTHERS | Completed |
| 105 | Playing of jingles on community Information Centres in the District | Social Development | 2,000.00 | DACF | FEB, 2023 | DEC,2022 | 2,000.00 | 0 | 100 |  | Districtwide | Completed |
| 106 | Celebration of World AIDS Day | Social Development | 2,000.00 | RAAF | FEB, 2023 | DEC,2023 | 2,000.00 | 0 | 100 |  | Districtwide | Completed |
| 107 | Organize stakeholders Consultations on HIV | Social Development | 5,289.00 | DACF | 01/12/2023 | 01/12/2023 | 5,289.00 | 0 | 100 |  | Districtwide | Completed |
| 108 | Provide support to voluntary care supporters of PLHIV | Social Development | 7,000.00 | IGF/DACF | October, 2023 | December, 2023 | 7,000 | 0 | 100% |  | 17 | Completed |
| 109 | Conduct Assessment of People nominated by PLHIV | Social Development | 3,000.00 | RAAF | April, 2023 | June, 2023 | 3,000 | 0 | 100 |  | 29 | Completed |
| 110 | Conduct awareness on the importance of family planning and birth spacing | Social Development | 7,000 | UNICEF | April, 2023 | August, 2023 | 7,000.00 | 0 | 100 |  | 320 | Completed |
| 111 | Restructuring and re-positioning of the Birth and Death Registry | Social Development | 0 | 0 | Jan-23 | Nov,2023 | 0 | 0 | 0 |  | 0 | yet to Start |
| 112 | Sensitize youth on the use of condoms and other pregnancy preventive measures | Social Development | 10,000 | Donor | October, 2023 | December, 2023 | 8000 | 2000 | 80% |  | Selected communities | On-going |
| 113 | Organize education in schools, hospitals and communities on birth and death registration | Social Development | 5,000.00 | IGF/DACF | Jan-23 | Dec-23 | 5,000 | 0 | 100 |  | 10 Basic Schools and 1 SHS | Completed |
| 114 | Conduct annual mobile registration | Social Development | 3,000.00 | SDA/ GOG | JULY.2023 | SEPT.2023 | 5,000.00 | 4,000.00 | 90% |  | Districtwide | On-going |
| 115 | Conduct Mobile registration (child health promotion week | Social Development | 2, 000.00 | SDA/ GOG | JULY.2023 | SEPT.2023 | 2,000.00 | 0.00 | 100 |  | Districtwide | Completed |
| 116 | Desilt choked drains and gutter in the communities | Social Development | 12000 | IGF/DACF | FEB, 2023 | Nov,2023 | 12000 | 0 | 100 |  | All major drains districtwide | Completed |
| 117 | Evacuate and Push 10 refuse heaps sites | Social Development | 35,500 | IGF/DACF | FEB, 2023 | August, 2023 | - | - | 100 |  | Districtwide | Completed |
| 118 | Purchase of 15no. refuse containers | Social Development | 68,000 | DACF | Jan-23 | Dec-23 | - | - | 100 |  | Districtwide | Completed |
| 119 | Purchase and supply cleaning tool – 50 n. wheel barrows, 2 no. water storage tanks, 50 no shovels, 50 no. pick rods, 25 no spades, 100 no. wellington boots, 30 no. machetes and 20 no. rakes | Social Development | 20,000.00 | DACF | Jan-23 | Dec-23 | 7,000.00 | 13,000.00 | 70% |  | Districtwide | On-going |
| 120 | Supervise activities of waste management contractors in the District | Social Development | 1,000 | IGF | Jul-23 | Sep-23 | - | - | 100 |  | Districtwide | Completed |
| 121 | To sensitize landlords on provision of household latrines. | Social Development | 500 | IGF | Jul-23 | Sep-23 | - | - | 100 |  | District Wide | Completed |
| 122 | Fumigation and Sanitation improvement activities | Social Development | 50,312.50 | DACF | Jul-23 | Sep-23 | - | - | 100 |  | District Wide | Completed |
| 123 | Organize Community Clean-up activities across the District | Social Development | 5,000 | IGF | Jul-23 | Sep-23 | 5,000 | 0 | 100 |  | District Wide | Completed |
| 124 | Educate the public on proper waste management/CLTS | Social Development | 1,000 | IGF | Jul-23 | Sep-23 | 1000 | 0 | 100% |  | District Wide | Completed |
| 125 | Reconstitute the Community water and Sanitation Boards in the Various Communities | Social Development | 5,000 | IGF | Jan-23 | Jun-23 | 3000 | 2000 | 80% |  | District Wide | ongoing |
| 126 | Train Community Water and Sanitation Board members | Social Development | 3,000 | IGF | Jan-23 | Sep-23 | 3000 | 0 | 100 |  | Members of Water and Sanitation board | Completed |
| 127 | Public education on proper food handling & medical screening | Social Development | 500 | IGF | July | September | - | - | 100 |  | Districwide | Completed |
| 128 | To educate the public on the dangers of stray animals | Social Development | - | - | Jul-23 | Sep-23 | - | - | 100 |  | Districwide | Completed |
| 129 | Organize Public education on Proper waste management and Public cleansing | Social Development | - | - | Jul-23 | Sep-23 | - | - | 100 |  | Districwide | Completed |
| 130 | Scale-up sensitization campaigns to promote proper handwashing and hygiene practices particularly among children (SDGs Target 6.2) and Train caterers of SFP on hygienic and nutritious preparation of food | Social Development | - | - | Jul-23 | Sep-23 | - | - | 100% |  | Districwide | Completed |
| 131 | Organize community engagements and behavioural change campaigns to promote positive parenting attitudes and practices among parents and caregivers | Social Development | 2500 | UNICEF/SDA | Jan-22 | DEC.2022 | 2500 | 0 | 100 |  | 368 | Completed |
| 132 | Sensitize communities/schools in the District on Gender Based Violence etc. (child Protection Toolkit) and Child Protection issues such as drug abuse, child abuse, child trafficking, etc. | Social Development | 1800 | DACF | Jan-22 | DEC.2022 | 1800 | 0 | 100 |  | 306 | Completed |
| 133 | Collaborate with the relevant state institutions i.e. Police, Courts etc. on child related issues | Social Development | 0 | DACF | Jan-23 | Dec-23 | 0 | 0 | 100% |  | 0 | Completed |
| 134 | Train caregivers on the Standards Operating Procedures of the Department. | Social Development | 5,000 | DACF | Nov-23 | Nov-23 | 5000 | 0 | 100 |  | 7 caregivers | Completed |
| 135 | Organize Homes, Schools, Markets and Lorry Parks visits to identify Children of school drop outs who loiter and reinstate them in school. | Social Development | 4,000.00 | DACF | JULY.2023 | SEPT.2023 | 4,000 | 0.00 | 100% |  | Districtwide | Completed |
| 136 | Organize Public sensitization on child labour issues (Celebration of World Day Against Child Labour) | Social Development | 2500.00 | DACF | AUGUST.2023 | SEPT.2023 | 2,500.00 | 1,000.00 | 100% |  | Districtwide | Completed |
| 137 | Create Data on children in child labour, teenage mothers and school drop outs | Social Development | 4,000.00 | DACF | JULY.2023 | SEPT.2023 | 4,000 | 0 | 100% |  | Districtwide | Completed |
| 138 | Create awareness on teenage Pregnancy in schools | Social Development | 2,000.00 | DACF | JULY.2023 | SEPT.2023 | 2,000.00 | 0 | 100% |  | Districtwide | Completed |
| 139 | Increase awareness on the effects of child labour | Social Development | 5,000 | DACF | AUGUST.2023 | SEPT.2023 | 4,000 | 1,000 | 90% |  | Districtwide | On-going |
| 140 | Institute child protection committees in all communities | Social Development | 3,000 | DACF | JULY.2023 | SEPT.2023 | 3,000 | 0 | 100% |  | Districtwide | Completed |
| 141 | Increase education and advocacy on Sexual and Gender-Based Violence and other Harmful Cultural Practices | Social Development | 7,000 | UNICEF/SDA | Jan-23 | DEC,2023 | 7000 | 0 | 100% |  | 167 | Completed |
| 142 | Increase the advocacy of women in political participation | Social Development | 5,000 | UNICEF/SDA | Jan-23 | DEC,2023 | 5000 | 0 | 100% |  | Districtwide | Completed |
| 143 | sensitize, empower and build capacities of women to participate in leadership and decision making at all levels (SDG 5.5) | Social Development | 10000 | UNICEF/SDA | Jan-23 | DEC,2023 | 10000 | 0 | 100% |  | 100 | Completed |
| 144 | Organize programs to mentor girls and create a pool of potential female leaders (SDG Targets 5.1, 5.c) | Social Development | 5,000 | UNICEF/SDA | Jan-23 | DEC,2023 | 5,000 | 0 | 100% |  | 60 | Completed |
| 145 | Organise skills training in income-generating activities for vulnerable women (SDG Targets 3.8, 4.5) | Social Development | 4000 | UNICEF/SDA | Jan-23 | DEC,2023 | 4000 | 0 | 100% |  | Districtwide | Completed |
| 146 | Encourage women artisans and other tradespeople, including farmers, to form associations to facilitate their access to information and other support (SDG Targets 1.4, 5.c) | Social Development | 8,325 | DACF | Jan-23 | DEC,2023 | 8,325 | 0 | 100% |  | Districtwide | Completed |
| 147 | Build the Capacity of DPCU on gender-responsive budgeting and financing (SDG Target 5.c) | Social Development | 4,200.00 | Donor(Hurds Foundation) | 27/07/2023 | 27/07/2023 | 4,200.00 | 0 | 100% |  | DPCU Members | Completed |
| 148 | Support Inter Schools Sporting Activities in the District | Social Development | 5,000 | MOE/IGF | JAN.2023 | Dec-23 | 5,000 | 0 | 100% |  | Didtrictwide | Completed |
| 149 | Organize District Sports Committee Meetings | Social Development | 5,000 | MOE/IGF | JAN.2023 | Dec-23 | 5,000 | 0 | 100% |  | Sport Committee Members | Completed |
| 150 | Participate in Regional Sports activities | Social Development | 6,000.00 | MOE/IGF | JAN.2023 | Dec-23 | 6,000.00 | 0 | 100% |  | District Sport Team | Completed |
| 151 | Provide Skills and Entrepreneurship training for the youth | Social Development | 6,000.00 | MOE/IGF | JAN.2023 | Dec-23 | 6,000.00 | 0 | 100% |  | Districtwide | Completed |
| 152 | Develop and implement apprenticeship and employable skill training for out-of-school youth and graduates (SDG Targets 4.4, 8.6) | Social Development | 6,000.00 | DACF | July,2023 | Sept,2023 | 6,000.00 | 5,000.00 | 90% |  | Districtwidw | On-going |
| 153 | Support the youth to participate in modern and climate-smart agriculture (SDG Target 8.6) | Social Development | 2,000.00 | Donor (MAG) | Mar-23 | Aug-23 | 2,000.00 | 0 | 100 |  | 7 | Completed |
| 154 | Strengthen and expand the coverage of existing social protection programmes to include all vulnerable people (SDG Target 1.3, 5.4, 10.4) | Social Development | 1000 | SDA | JAN.2023 | DEC.2023 | 1000 | 0 | 100 |  | 231 | Completed |
| 155 | Organise public /Radio sensitisation against stigma, abuse, discrimination, and harassment of vulnerable people (SDG Targets 16.2, 16.3, 16.b | Social Development | 162,936.00 | DACF | JAN.2023 | DEC.2023 | 113,000.00 | 8936 | 100 |  | 62 | Completed |
| 156 | Support People with Disabilities (PWDs) with items/cash, school fees and medical bills | Social Development | 28,000.00 | DACF | AUG.2023 | DEC.2023 | 28,000.00 | 0 | 78% |  | 74 PWDs | On-going |
| 157 | Organized Durbars to support PWDs | Social Development | 7500 | DACF | JUN.2023 | DEC.2023 | 7,500.00 | 0 | 100 |  | 62 | Completed |
| 158 | Monitor the activities of PWDs supported | Social Development | 0 | DACF | Jan-23 | DEC.2023 | 0 | 0 | 100 |  | 62 | Completed |
| 159 | Identify and register PWDs in the District. | Social Development | 12,000 | SDA | Jan-23 | Dec-23 | 12,000 | 0 | 100 |  | 26 | Completed |
| 160 | Organize Social Services Sub Committee Meeting | Social Development | 5,000 | DACF | Jan-23 | Dec-23 | 5,000 | 0 | 100% |  | Social Service Subcommittee members | Completed |
| 161 | Sensitize citizens and organisations on eradication of disability-related discrimination | Social Development |  | Unicef | JAN.2023 | Dec-23 | 7,432.00 | 0 | 100 |  | Districtwide | Completed |
| 162 | Sensitize and educate populace on land Degradation | Environment, Infrastructure And Human Settlement | 2,500.00 | Donor (FoN) | 16/03/2023 | 08/10/2023 | 2,500.00 | 0 | 100% |  | District wide | Completed |
| 163 | Encourage all schools in the District to plant trees | Environment, Infrastructure And Human Settlement | 4,500.00 | DACF, DONOR(FoN) | May-23 | Jul-23 | 4,500.00 | 0 | 100% |  | District wide | Completed |
| 164 | Reforest degraded lands | Environment, Infrastructure And Human Settlement | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  | 0.00 | Yet to start |
| 165 | Strengthen involvement of local communities in the management of forests and wetlands (SDG Targets 6.a, 6b) | Environment, Infrastructure And Human Settlement | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |  | 0.00 | Yet to start |
| 166 | Ensure mining activities are undertaken in an environmentally sustainable manner (SDG Targets 6.5, 8.4, 12.2,) | Environment, Infrastructure And Human Settlement | 2,000 | IGF | Jul-23 | Sep-23 | 1500 | 500 | 80 |  | Selected communities | On-going |
| 167 | Ensure land reclamation after mining operations (SDG Targets 15.1, 15.3) | Environment, Infrastructure And Human Settlement | 5000 | IGF | Jul-23 | Sep-23 | 4000 | 1000 | 80 |  | Selected communities | On-going |
| 168 | Monitor the activities of quarry and sand wining industries | Environment, Infrastructure And Human Settlement | - | IGF | Jul-23 | Sep-23 | - | - | 76% |  | Selected communities | On-going |
| 169 | Establish Quarry Development Fund | Environment, Infrastructure And Human Settlement | 2,000.00 | DACF | 08/10/2023 | 11/01/2023 | 2,000.00 | 0 | 100% |  | District wide | Completed |
| 170 | Establish District Community Mining Scheme | Environment, Infrastructure And Human Settlement | 1,500.00 | Donor (FoN) | 29/03/2023 | 19/05/2023 | 1,500.00 | 0 | 100% |  | District wide | Completed |
| 171 | Organize Community Clean Up exercises within the Coastal areas | Environment, Infrastructure And Human Settlement | 1,000 | IGF | Jul-23 | Sep-23 | 1,000 | 8,00 | 80 |  | 5 Coastal Communities | On-going |
| 172 | Undertake tree planting along banks of all major water bodies and tributaries to reduce silting and pollution from human activities (SDG Targets 6.5, 6.6) | Environment, Infrastructure And Human Settlement | 5000 | IGF | Jul-23 | Sep-23 | 5000 | 3000 | 70 |  | Selected communities | On-going |
| 173 | Intensify public education on indiscriminate disposal of waste (SDG Target 11.6) | Environment, Infrastructure And Human Settlement | 1000 | IGF | Jul-23 | Sep-23 | 1000 | 1000 | 100% |  | Distrwide | Completed |
| 174 | Implement SHEP (Sanitation, Env. & Safety Systems) in Schools (SDG Targets 1.4, 7.1) | Environment, Infrastructure And Human Settlement | 6,000.00 | IGF,DONOR(FON) | Jan-23 | Dec-23 | 6,000.00 | 0 | 100% |  | District wide | Completed |
| 175 | Public sensitization on climate change, SDGs & COVID – 19 | Environment, Infrastructure And Human Settlement | 5,000.00 | IGF,DONOR(FON) | Jan-23 | Dec-23 | 5,000.00 | 0 | 100% |  | District wide | Completed |
| 176 | Build the capacity of farmers on climate smart agricultural practices in collaboration with B-BOVID | Environment, Infrastructure And Human Settlement | 5,000 | IGF,DONOR(FON) | 23/02/2023 | 24/11/2023 | 5,000 | 0 | 100% |  | 120 | Completed |
| 177 | Enhanced knowledge of farmers on mitigation and adaptation measures on climate change | Environment, Infrastructure And Human Settlement | 1,500.00 | IGF,DONOR(FON) | 23/02/2023 | 23/02/2023 | 1,500.00 | 0 | 100% |  | 15 | Completed |
| 178 | Promote climate-resilience policies for women and other vulnerable groups in agriculture (SDG Targets 1.5, 13.1, 13.2, 13.b, 16.6) | Environment, Infrastructure And Human Settlement | - | IGF | 23/02/2023 | 23/02/2023 | - | 0 | 0 |  | 0 | Yet to Start |
| 179 | Develop climate-responsive infrastructure (SDG Target 9.1) | Environment, Infrastructure And Human Settlement | 6,500.00 | IGF,DONOR(FON) | 14/03/2023 | 22/11/2023 | 4,500.00 | 2000 | 75% |  | 10 | Completed |
| 180 | Organize Radio Sensitization on climate change to minimize its impacts | Environment, Infrastructure And Human Settlement | 1,500.00 | IGF,DONOR(FON) | Jan-23 | Dec-23 | 1,500.00 | 0 | 100% |  | District wide | Completed |
| 181 | Initiate Green District campaign with traditional authorities, civil society, religious bodies and other recognized groups (SDG Target 13.3) | Environment, Infrastructure And Human Settlement | - | IGF,DONOR(FON) | Jan-23 | Dec-23 | - | 0 | 100 |  | District wide | Completed |
| 182 | Organise Radio Sensitization on Disaster Risk Reduction Measures | Environment, Infrastructure And Human Settlement | 2,000.00 | Donor(FoN)/VRA | 21/03/2023 | 21/09/2023 | 1,000.00 | 1000 | 50% |  | District wide | Completed |
| 183 | Conduct Community Engagements on Disaster Risk Reduction Measures | Environment, Infrastructure And Human Settlement | 2,000.00 | Donor(FoN)/VRA | 21/02/2023 | 17/11/2023 | 1,500.00 | 500 | 75% |  | District wide | Ongoing |
| 184 | Form Disaster Volunteer’s Groups(DVGs) across the District | Environment, Infrastructure And Human Settlement | - | 0 | 28/03/2023 | 21/09/2023 | - | 0 | 100% |  | District wide | Completed |
| 185 | Build the Capacity of NADMO Staff , DVGs And Organized Groups on Disaster Management | Environment, Infrastructure And Human Settlement | 3,500.00 | IGF,DONOR(FON) | 13/04/2023 | 18/10/2023 | 3,500.00 | 0 | 100% |  | 7 | Completed |
| 186 | Organise Weekly Zonal Field Trips on Disaster Assessment | Environment, Infrastructure And Human Settlement | 5,000.00 | IGF,DONOR(FON) | 16/03/2023 | 23/12/2023 | 2,000.00 | 3000 | 45% |  | District wide | completed |
| 187 | Organise District Disaster Management Committee Meetings | Environment, Infrastructure And Human Settlement | 1,500.00 | IGF,DONOR(FON) | 23/02/2023 | 23/02/2023 | 1,500.00 | 0 | 100% |  | 15 | completed |
| 188 | Observe International Day For Disaster Risk Reduction (IDDRR) | Environment, Infrastructure And Human Settlement | - | 0 | 23/02/2023 | 23/02/2023 | - | 0 | 0% |  | 0 | Yet-to-start |
| 189 | Provide Relief Support to Disaster Victims And reconstruction | Environment, Infrastructure And Human Settlement | 18,000.00 | DACF | 23-Jul | 23-Sep | 80,000.00 | 5,000.00 | 80% |  | Anglo Beach Community | ongoing |
| 190 | Organize Road safety Campaigns | Environment, Infrastructure And Human Settlement | - | IGF,DONOR(FON) | 02/08/2023 | 21/10/2023 | - | 0 |  |  | 0 | Yet-to-start |
| 191 | Intensify the use of Geographic Information System (GIS) in spatial/land use planning at all levels | Environment, Infrastructure And Human Settlement | 4,000.00 | DACF | 23-Jul | 23-Sep | 4,000.00 | 3,000.00 | 85% |  | Districtwide | On-going |
| 192 | Undertake regular monitoring and sensitisation on spatial planning and management | Environment, Infrastructure And Human Settlement | 3,000.00 | IGF | 23-Jul | 23-Sep | 2,500.00 | 2,500.00 | 100% |  | Districtwide | Completed |
| 193 | Undertake field trips to disaster prone areas | Environment, Infrastructure And Human Settlement | 5,000.00 | DACF | 23-Jul | 23-Sep | 5,000.00 | 1,000.00 | 100% |  | Districtwide | Completed |
| 194 | Develop asset register on infrastructure conditions | Environment, Infrastructure And Human Settlement | - | GOG, DACF | jan | Dec | - | - | 90 |  |  | On-going |
| 195 | Preparation of new planning schemes | Environment, Infrastructure And Human Settlement | - | GOG, DACF | Jan-23 | Dec-23 | - | 0 | 46% |  | Ohiamadwen,Assorko | On-going |
| 196 | Sensitization of Chiefs and Families on the need to sell lands in conformity with the planning schemes | Environment, Infrastructure And Human Settlement | - | IGF | Jan-23 | Dec-23 | - | 0 | 100% |  | Districtwide | On-going |
| 197 | Extension of Street Naming and Property addressing to selected communities (Ituma, Dwomo, Beposo,Anto,Komfueku, Asemasa No.1) | Environment, Infrastructure And Human Settlement | 10000 | GOG | Jan-23 | Dec-23 | 6000 | 4000 | 90% |  | Selected communities | On-going |
| 198 | Organize Monthly Tech-Sub Comm and Spatial Planning Committee meeting | Environment, Infrastructure And Human Settlement | 3000 | GOG, DACF | Jan-23 | December, 2023 | 2000 | 1000 | 100 |  | - | On-going |
| 199 | Document all Assembly Landed properties. | Environment, Infrastructure And Human Settlement | - | GOG, DACF | Jan-00 | 0 | - | - | 0% |  | - | Yet-to-start |
| 200 | Develop District Geo Spatial | Environment, Infrastructure And Human Settlement | 5000 | GOG, DACF | Jan-23 | Dec-23 | 5000 | 0 | 100 |  | - | Completed |
| 201 | Ensure the production of base, topographic and orthophoto maps to cover the entire country (SDG Target 12.2) | Environment, Infrastructure And Human Settlement | - | DACF | Jan-23 | Dec-23 | - | - | 0 |  | - | Yet-to-start |
| 202 | Promote the production of reliable maps and site plans to ensure security of land tenure | Environment, Infrastructure And Human Settlement | - | DACF | Jan-23 | Dec-23 | - | - | 78% |  | - | Ongoing |
| 203 | Intensify education on rights and responsibilities of electorates | Governance, Corruption And Public Accountability | 3,986.00 | Donor (SCMMP) | May-23 | Jun-23 | 3,986.00 |  | 100% |  | Districtwide | Completed |
| 204 | Intensify public awareness on the need for equal gender at the Assembly | Governance, Corruption And Public Accountability | 3,986.00 | Donor (SCMMP) | May-23 | Jun-23 | 3,986.00 |  | 100% |  | Districtwide | Completed |
| 205 | Provide logistics/Office facilities for the Area councils- - computers and accessories | Governance, Corruption And Public Accountability | 5,832.00 | DACF | Jan-23 | Dec-23 | 3,784.00 | 2,048.00 | 67% |  | 4 Area Councils | On-going |
| 206 | Reconstitution of the Area Councils | Governance, Corruption And Public Accountability | 4,612.00 | Donor (CDD) | May-23 | May-23 | 4,612.00 |  | 100% |  | Area Council Members | Completed |
| 207 | Train Area Council members on Participatory Planning, Budgeting , M&E | Governance, Corruption And Public Accountability | 4,612.00 | Donor (CDD) | May-23 | May-23 | 4,612.00 |  | 100% |  | Area Council Members | Completed |
| 208 | Allocate District officers to manage the Area Councils | Governance, Corruption And Public Accountability | 0 | 0 | Jan-23 | Dec-23 | 0 | 0 | 100 |  | 4 Area Councils | Completed |
| 209 | Organize stakeholders forum on development planning process and Budgeting | Governance, Corruption And Public Accountability | 7,436.00 | FoN | Mar-23 | Jun-23 | 7,436.00 | 0 | 100% |  | 272 | Completed |
| 210 | Conduct Monthly Radio Sensitization on Assembly program Implementation and Achievements | Governance, Corruption And Public Accountability | 3,000.00 | FoN | Jan-23 | Dec-23 | 3,000.00 | 0 | 100% |  | Districtwide | Completed |
| 211 | Organise quarterly DCEs engagement with the Public on Radio | Governance, Corruption And Public Accountability | 10,247.90 | FoN | Jan-23 | Dec-23 | 10,247.90 | 0 | 100% |  | Districtwide | Completed |
| 212 | Organize quarterly DPCU Meetings. | Governance, Corruption And Public Accountability | 12,845.00 | FoN | Jan-23 | Dec-23 | 12,845.00 | 0 | 100% |  | DPCU Members | Completed |
| 213 | Prepare Annual Action Plan | Governance, Corruption And Public Accountability | 6,794.00 | FoN | May-23 | Sep-23 | 6,794.00 | 0 | 100% |  | 0 | Completed |
| 214 | Prepare Annual Budgets | Governance, Corruption And Public Accountability | 14,893.00 | IGF/FoN | Jun-23 | Oct-23 | 14,893.00 | 0 | 100% |  | 0 | Completed |
| 215 | Conduct Review of Annual Action Plans | Governance, Corruption And Public Accountability | 6,794.00 | FoN | Jun-23 | Jun-23 | 6,794.00 | 0 | 100% |  | 0 | Completed |
| 216 | Conduct Review of Annual Budgets | Governance, Corruption And Public Accountability | 6,794.00 | FoN | Jun-23 | Jun-23 | 6,794.00 | 0 | 100% |  | 0 | Completed |
| 217 | Preparation of Procurement Plan | Governance, Corruption And Public Accountability | 4,986.00 | IGF | Nov-23 | Nov-23 | 4,986.00 | 0 | 100% |  | 0 | Completed |
| 218 | Organize Town Hall Meetings and Organise DCEs Community Engagements | Governance, Corruption And Public Accountability | 30,467.90 | FoN | Mar-23 | Dec-23 | 30,467.90 | 0 | 100% |  | Districtwide | Completed |
| 219 | Mount Accountability bill boards at the various Area Councils | Governance, Corruption And Public Accountability | 99,673.00 | FoN | Jan-23 | Dec-23 | 99,673.00 | 0 | 100% |  | Districtwide | Completed |
| 220 | Conduct quarterly audit committee meeting | Governance, Corruption And Public Accountability | 8,465 | IGF | Jan-23 | Dec-23 | 8,465 | 0 | 100% |  | Audit Committee Members | Completed |
| 221 | Organize Social Audit Committee project monitoring (engagements to include marginalized groups) | Governance, Corruption And Public Accountability |  |  |  |  |  |  |  |  |  |  |
| 222 | Encourage and Support Communities to undertake self-help projects | Governance, Corruption And Public Accountability | 0 | 0 | Jan-23 | Dec-23 | 0 | 0 | 56% |  | Districtwide | Ongoing |
| 223 | Rent accommodation for officers who are entitled to official accommodation | Governance, Corruption And Public Accountability | 5,600 | IGF | Jan-23 | Dec-23 | 5,600 | 0 | 100 |  | 1 | Completed |
| 224 | Procure office equipment for offices (computers, printers, stationary ,Anti-virus, value book etc | Governance, Corruption And Public Accountability | 56,468.00 | DACF/IGF | Jan-23 | Dec-23 | 26,189.00 | 30,279.00 | 45% |  | District Assembly | On-going |
| 225 | Maintenance of furniture and fixtures | Governance, Corruption And Public Accountability | 14,594.00 | IGF | Jan-23 | Dec-23 | 5,378.00 | 9,216 | 36% |  |  | On-going |
| 226 | Intensify the use of Strategic Environmental Assessment (SEA) in the Assembly’s policy processes, plans and programs (SDG Targets 11.6, 16.6) | Governance, Corruption And Public Accountability | 0 | 0 | Jan-23 | Dec-23 | 0 | 0 | 100% |  |  | Completed |
| 227 | Organise capacity building training/workshops for Management & Assembly Members | Governance, Corruption And Public Accountability | 17,934.00 | IGF/Donor | Jan-23 | Dec-23 | 17,934.00 | 0 | 100% |  | Management and Assembly Members | Completed |
| 228 | Train Agric Officers on yield estimation | Governance, Corruption And Public Accountability | 3,848.00 | Donor (MAG) | Jan-23 | Dec-23 | 3,848.00 | 0 | 100% |  | All Agric Officers | Completed |
| 229 | Train on Assets, Inventory and Procurement Management for HODs and selected staff | Governance, Corruption And Public Accountability | 8,984.00 | IGF | Jan-23 | Dec-23 | 8,984.00 |  | 100 |  | HoDs and Selected Staff | Completed |
| 230 | Ensure effective implementation of the National Anti-Corruption Action Plan (NACAP) (SDG Targets 16.5, 16.b) | Governance, Corruption And Public Accountability | 6,478.00 | Donor (Gender in Focus) | Jan-23 | Dec-23 | 6,478.00 | 0 | 100% |  |  | Completed |
| 231 | Pursue an effective campaign for attitudinal change (SDG Targets 16.5, 16.7) | Governance, Corruption And Public Accountability | 2,934.00 | IGF | Jan-23 | Dec-23 | 2,934.00 | 0 | 100% |  |  | Completed |
| 232 | Engage CSOs and other stakeholders in the District in the Fight against Corruption. | Governance, Corruption And Public Accountability | 4,823.00 | GACC | Jan-23 | Dec-23 | 4,823.00 | 0 | 100% |  | 120 | Completed |
| 233 | Introduce the Clocking System to control absenteeism, lateness and moonlighting. | Governance, Corruption And Public Accountability | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Yet to start |
| 234 | Organize monthly Radio education and sensitization on Corruption related issues. | Governance, Corruption And Public Accountability | 3,840 | FoN | Jan-23 | Dec-23 | 3,840 | 0 | 100 |  | districtwide | Completed |
| 235 | Provide office for city guards at Beposo Market | Governance, Corruption And Public Accountability | 0 | 0 | Jan-23 | Dec-23 | 0 | 0 | 0 |  | 0 | Yet to start |
| 236 | Provide support to the District Police Service | Governance, Corruption And Public Accountability | 4,984.00 | IGF | Jan-23 | Dec-23 | 4,984.00 | 0 | 100% |  |  | Completed |
| 237 | DISEC Activity | Governance, Corruption And Public Accountability | 48,394.00 | DACF/IGF | Jan-23 | Dec-23 | 48,394.00 | 0 | 100% |  |  | Completed |
| 238 | Strengthen the Shama Traditional Council to promote development (SDG Targets 16.6, 16.a | Governance, Corruption And Public Accountability | 5,038.00 | IGF | Jan-23 | Dec-23 | 5,038.00 | 0 | 100% |  |  | Completed |
| 239 | Enhance private sector participation in culture promotion (SDG Target 17.17) | Governance, Corruption And Public Accountability | 90,034.00 | IGF/PRIVATE SECTOR | Jan-23 | Dec-23 | 32,644.00 | 57,390.00 | 28% |  |  | On-going |
| 240 | Identify and initiate actions with relevant cities in Africa, USA, UK, Australia | Governance, Corruption And Public Accountability | 2,067,124,00 | PRIVATE SECTOR (TICO) | Jan-23 | Dec-23 | 203,876.00 | 1,863,248 | 34% |  |  | On-going |
| 241 | Support/Implement Open Governance Partnership(OGP) activities | Governance, Corruption And Public Accountability | 34,458.00 | Donor (CDD/FoN) | Jan-23 | Dec-23 | 13,475.00 | 20,983.00 | 76% |  |  | On-going |
| 242 | Strengthen early warning and response mechanisms for disasters | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 20,000 | DACF | Jan. | Dec. | 20,000 | 20,000 | 100% |  | Districtwide | Completed |
| 243 | Support data gathering, preparation of hazards/ risk maps and sensitization on natural hazards and human induced disasters | Emergency Planning And Response (Including Covid-19 Reacovery Plan) | 15,000 | DACF | Jan. | March. | 15000 | 15000 | 100% |  | Districtwide | Completed |
| 244 | Develop monitoring mechanism for disaster prevention and mitigation plan | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 10,000 | DACF | Jan. | march | 9850 | 9850 | 100% |  | Districtwide | Completed |
| 245 | Build the Capacity of National Disaster Management Organization (NADMO) on Disaster Control and Management | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 12,000 | DACF | Jan. | march | 11,500 | 11,500 | 100% |  | All staff | Completed |
| 246 | Strengthen the participation of civil society in disaster risk management | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 30,000 | DACF | Jan. | June. | 30,000 | 30,000 | 100% |  | Districtwide | Completed |
| 247 | Sensitize stakeholders on disaster risk reduction legislation | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 30,000 | DACF | Jan. | Sept. | 30,000 | 30,000 | 100% |  | Districtwide | Completed |
| 248 | Improve surveillance, monitoring and evaluation of Health threats and epidemics and pandemics | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 15,000 | DACF | Feb | Sept. | 15,000 | 15,000 | 100% |  | Districtwide | Completed |
| 249 | Establish Covid-19 testing centres in the district | Emergency Planning And Response (Including Covid-19 Recovery Plan) | 25,000 | DACF | Mar | Sept. | 5,000 | 5,000 | 25% |  | Shama | Ongoing |
| 250 | Ensure that planning activities of Departments are in line with the Coordinated Programme in DMTDP | Implementation, Coordination, Monitoring And Evaluation |  |  | Apr | Sept. |  |  | 100% |  | Districtwide | Completed |
| 251 | Strengthen coordination between CSOs, NGOs, DPS and local authorities | Implementation, Coordination, Monitoring And Evaluation | 5,000 | DACF | May | Sept. | 5,000 | 5,000 | 100% |  | Districtwide | Completed |
| 252 | Implement the District Development Data Platform (DDDP) | Implementation, Coordination, Monitoring And Evaluation | 1,000 | DACF | Jun | Sept. | 1,000 | 1,000 | 100% |  | Districtwide | Completed |
| 253 | Strengthen and improve resource mobilization for plan implementation | Implementation, Coordination, Monitoring And Evaluation | 15,000 | DACF | Jul | Sept. | 15,000 | 15,000 | 100% |  | Districtwide | Completed |
| 254 | Design uniform Reporting Format for all Departments | Implementation, Coordination, Monitoring And Evaluation |  |  | Jan. | Dec. |  |  | 100% |  | Districtwide | Successfully Completed |
| 255 | Develop effective participation and communication arrangements for M&E results | Implementation, Coordination, Monitoring And Evaluation | 10,000 | DACF | Jan. | Nov. | 10,000 | 10,000 | 100% |  | Districtwide | Monitoring Activities successfully conducted |
| 256 | Increase investments in the development and use of M&E results | Implementation, Coordination, Monitoring And Evaluation | 20,000 | DACF | Jan. | Oct. | 20,000 | 20,000 | 100% |  | Districtwide | Completed |
| 257 | Strengthen M&E technical and logistical capacities at all levels | Implementation, Coordination, Monitoring And Evaluation | 5,000 | DACF | Jan. | Nov. | 5,000 | 5,000 | 100% |  | Districtwide | Completed |
| 258 | Conduct Periodic Project Monitoring | Implementation, Coordination, Monitoring And Evaluation | 20,000 | DACF | Jan. | Nov. | 20,000 | 20,000 | 100% |  | Districtwide | 2 Project Monitoring Completed |
| 259 | Build the capacity of DPCU on data Management | Implementation, Coordination, Monitoring And Evaluation | 10,000 | DACF | Jan. | Nov. | 10,000 | 10,000 | 100% |  | DPCU Members | Completed |
| 260 | Organize exchange visits and peer leaning among other MMDAs | Implementation, Coordination, Monitoring And Evaluation | 35,000 | DACF | Jan. | Nov. | 10,000 | 35,000 | 45% |  | Districtwide | Ongoing |
| 261 | Digitize District records and retrieval processes | Implementation, Coordination, Monitoring And Evaluation | 10,000 | DACF | Jan. | Nov. | 2,000 | 10,000 | 20% |  | Districtwide | Ongoing |

Appendix 4: PERFORMANCE INDICATORS (CORE AND DISTRICT SPECIFIC) AT THE DISTRICT LEVEL

|  | Indicator (Categorized by Development Dimension | Baseline (2021) | Target 2022 | Actual 2022 | Target 2023 | Actual 2023 | Key programmes Undertaken during the year | Challenges encountered in the year | Policy recommendations |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CORE INDICATORS |  |  |  |  |  |  |  |  |  |  |
| ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| 1 | Total output in agricultural production |  |  |  |  |  |  |  |  |  |
| i | Maize | 9200 | 162000 | 25000 | 2350 | 2112 | 1. Yield studies on selected crops (rice, maize, cassava, and plantain). 2.Demonstration and field days on improved technologies. 3. Regular farm and home visits to operational areas. 4. Build capacity of livestock farmers on livestock management and IMO 5. Technology and facilitate activities on PJF, RFJ, PERD | Inadequate of machinery such as tractors, planters, harvesters, dryers, etc to help improve and reduce cost of rice production in the district. | The government or an NGO to set up a mechanization center in the district. |
| ii | Rice (milled), | 3012 | 231000 | 18109 | 815 | 635 |  |  |  |
| iii | Cassava | 2,700,018 | 74210 | 67120 | 13215 | 12515 |  |  |  |
| iv | Oil palm | 279,300 | 15200 | 15000 | 48,323 | 211,647 |  |  |  |
| v | Goat | 7216 | 8200 | 8532 | 14700 | 13350 |  |  |  |
| vi | Pig | 3030 | 2500 | 2000 | 1556 | 2000 |  |  |  |
| vii | Poultry | 279,300 | 15200 | 15000 | 42,144 | 43,000 |  |  |  |
| viii | Sheep | 600 | 10000 | 8520 |  |  |  |  |  |
| 2 | Average productivity of selected crop (mt/ha): |  |  |  |  |  |  |  |  |
| i | Maize | 5.6 | 5.2 | 4.5 | 5.2 | 4.5 |  | Sale of cropping lands to clay miners and sand winners. Also, more food crop lands are being sold out for rubber plantation and infrastructure development. | The district should map out areas for crop production Refresher trainings should be provided at time interval |
| ii | Cassava | 23.5 | 25.5 | 20.5 | 25.5 | 23.76 |  |  |  |
| 3 | Percentage of arable land under cultivation | 88% |  | 65% | 75% | 60% |  |  |  |
| 4 | Number of AEAs Trained on Agric Technologies | 11 | 10 | 17 | 17 | 17 |  |  |  |
| 5 | Total Number farmers with access to agriculture technologies | 123 | 150 | 167 | 160 | 185 |  |  |  |
| 6 | Number of Farmers engaged in livestock production | 265 | 270 | 393 | 400 | 434 |  |  |  |
| 7 | Number of Farmers trained of Climate Smart Agriculture | 210 | 400 | 329 | 400 | 350 |  |  |  |
| 8 | Number of new industries established. |  |  |  |  |  |  |  |  |  |
| i | Agriculture, | 17 | 7 | 5 | 20 | 5 | Capacity Building for SMEs, Support to SMEs, Collaboration with Private Sectors for the development of Tourist sites, Formation of LED platforms | Inadequate funds to carry out capacity building across the district | Government should massively support industrial development |
| ii | Industry, | 15 | 9 | 4 | 20 | 10 |  |  |  |
| iii | Service | 23 | 5 | 3 | 20 | 10 |  |  |  |
| 9 | Number of new jobs created. |  |  |  |  |  |  |  |  |
| i | Agriculture | 10,863 | 11,009 | 5,894 | 6,023 | 6,140 |  |  |  |
| ii | Industry | 662 | 123 | 96 | 130 | 108 |  |  |  |
| iii | Service | 846 | 57 | 64 | 131 | 129 |  |  |  |
| 10 | Number of Tourism site developed | 1 | 1 | 1 | 1 | 1 |  |  |  |
| 11 | Number of SMEs trained on Business Development | 12 | 25 | 23 | 30 | 25 |  |  |  |
| 12 | Number of Market facilities in the District | 4 | 5 | 4 | 5 | 4 |  |  |  |
| 13 | Percentage change in IGF | 16.40% | 17% | 15.50% | 18% | 68.04% | Formation of Revenue Mobilization task force, sensitization of chiefs and landlords on development issues, distribution of bills | Inadequate logistics, citizens unwillingness to pay bills, GRA take over of property rates | The Assembly should provide the Revenue unit with the necessary logistics, regular stakeholders engagement on the need for taxation |
| 14 | Number of Development Permit Issued | 109 | 100 | 186 | 120 | 178 |  |  |  |
| 15 | Number of Development Application Received | 199 | 150 | 197 | 150 | 190 |  |  |  |
| 16 | Number of Bills Distributed |  |  |  |  |  |  |  |  |
| i | BOP | 1970 | 2,561 | 2,561 | 2771 | 2771 |  |  |  |
| ii | Property Rate | 6,331 | 6,845 | 6,845 | 12,834 | 561 |  |  |  |
| SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |
| 17 | Net enrolment ratio |  |  |  |  |  |  |  |  |  |
| i | Kindergarten | 88.50% | 90% | 89.50% | 94% | 84.24% | Regular monitoring and inspection of schools, Feeding programme, presentation SMART School Tools to two schools in the District, Mock Examination for final year JHS students | Inadequate funds to run programmes of the Directorate, Inadequate funds for Coordinators and School Improvement Support Officers for monitoring, | Timely release of funds to support educational activities |
| ii | Primary | 93.60% | 95% | 94% | 100% | 101.17% |  |  |  |
| iii | JHS | 47.80% | 70% | 49.80% | 75% | 64.55% |  |  |  |
| iv | SHS |  |  |  | 55% | 30.10% |  |  |  |
| 18 | Gender Parity Index |  |  |  |  |  |  |  |  |
| i | Kindergarten | 0.97 | 1.1 | 0.97 | 01:01 | 01:01 |  |  |  |
| ii | Primary | 0.98 | 1.1 | 0.98 | 01:01 | 01:08 |  |  |  |
| iii | JHS | 1.03 | 1.1 | 1.03 | 01:01 | 01:01 |  |  |  |
| iv | SHS | 1.06 | 1.1 | 1.06 | 01:01 | 01:07 |  |  |  |
| 19 | Completion rate |  |  |  |  |  |  |  |  |  |
| i | Kindergarten | 112.2% | 100% | 97.2% | 100% | 100% | Regular monitoring and inspection of schools, School Feeding programme, presentation SMART School Tools to two schools in the District, Mock Examination for final year JHS students | Inadequate funds to run programmes of the Directorate, Inadequate funds for Coordinators and School Improvement Support Officers for monitoring, | Timely release of funds to support educational activities |
| ii | Primary | 100.1% | 100% | 99.1% | 100% | 99.7% |  |  |  |
| iii | JHS | 85.9% | 100% | 84.9% | 100% | 100% |  |  |  |
|  | SHS | 88.2% | 100% | Girls:75.2% | Girls:100% | 89.0% |  |  |  |
| 20 | PASS RATE |  |  |  |  |  |  |  |  |  |
|  | • JHS | 59.48% | 59.48% | 55% | 61.58% | 55% | Provision of mono and dual desks for schools, Mock Examination for final year students | Inadequate funds to run programmes of the Directorate, Inadequate funds for Coordinators and School Improvement Support Officers for monitoring, | Timely release of funds to support educational activities |
|  | • SHS | 71.21% | 100% | 75.3% | 100% | 79.8% |  |  |  |
| 21 | Number of school furniture | 620 | 415 | 390 | 400 | 340 |  |  |  |
| 22 | Proportion of health facilities that are functional |  |  |  |  |  |  |  |  |  |
|  | i. CHPS Compound | 81.80% | 100% | 81.80% | 100% | 81.80% | Continuation and Completion of CHPs compound | Unpaid Contractors | Contractors should be paid Government should fast tract the completion of the hospital under construction under Agenda 111 in the district |
|  | iii. Health Center | 18.20% | 100% | 18.20% | 100% | 18.20% |  |  |  |
|  | v. Hospital | 0 | 1 | 0 | 1 | 0 |  |  |  |
| 23 | Proportion of population with valid NHIS card |  |  |  |  |  |  |  |  |  |
| i | Total | 99.99% | 40.3% | 99.99% | 100% | 46.56% | Registration school children on NHIS scheme, Radio Education on NHIS, Community Sensitization/Registration on NHIS | Inadequate logistics, delay in the release of funds for mass registration | Provision of adequate logistics and timely release of funds |
| ii | Indigents | 3.36% | 3% | 3.36% | 100% | 7.57% |  |  |  |
| iii | Informal | 35.27% | 20% | 35.27% | 100% | 16.12% |  |  |  |
| iv | Aged | 3.30% | 3% | 3.3%s | 100% | 1.59% |  |  |  |
| v | Under 18years | 49.60% | 25% | 49.60% | 100% | 19.81% |  |  |  |
| vi | Pregnant Women | 3.46% | 100% | 3.46% | 100% | 1.47% |  |  |  |
| 24 | Number of births and deaths registered |  |  |  |  |  |  |  |  |  |
| i | i. Birth (sex) | Male: 439 | Male: 400 | Male:522 | Male:651 | Male:772 | Conduct annual mobile registration | Lack of office space, inadequate logistics for mass registration |  |
|  |  | Female:621 | Female:650 | Female:571 | Female: 699 | Female: 711 |  |  |  |
| ii | ii. Death (sex, age group) | Male:24 | Male:0 | Male:30 | Male:0 | Male:42 |  |  |  |
|  |  | Female:30 | Female:0 | Female:25 | Female:0 | Female:26 |  |  |  |
| 25 | Percent of population with sustainable access of safe drinking water sources |  |  |  |  |  |  |  |  |  |
| i | District | 92.00% | 100% | 82% | 100% | 92% | Construction of Boreholes, Collaboration with Ghana Water Company and Community Water and Sanitation | Broken pipes, late payment of water bills, low coverage of GWCL pipes, salinity of water from boreholes | Extension of GWCL pipelines, Filtration of saline water, repair of broken pipes |
| ii | Urban | 89.50% | 100% | 58.90% | 100% | 61.33 |  |  |  |
| iii | Rural | 72.40% | 100% | 23.70% | 100% | 30.67 |  |  |  |
| 26 | Proportion of population with access to improved sanitation services |  |  |  |  |  |  |  |  |  |
| i | District | 89.00% | 100% | 52.60% | 100% | 58.60% | Desilting of choked drains. Monitoring and Supervision of Service Provider. Evacuate and Push 10 refuse heaps sites | Lack of vehicle for regular visit to the communities, Inadequate equipment and unskilled laborers to improve on Sanitation in the district, Indiscriminate and open defecation in the communities and Beaches, Lack of cooperation and compliance by some of the community members. | The Regional Environment dpt should train staff on sanitation improvement activities, sensitization of indigenes to keep their homes neat. |
| ii | Urban | 98.50% | 100% | 34.90% | 100% | 39.06% |  |  |  |
| iii | Rural | 79.50% | 100% | 17.70% | 100% | 19.54% |  |  |  |
| 27 | Number of functional Sanitation Facilities |  |  |  |  |  |  |  |  |
| i | Public Toilet | 35 | 35 | 35 | 35 | 35 |  |  |  |
| 28 | Dumping Site | 25 | 25 | 25 | 25 | 25 |  |  |  |
| 29 | Number of Sanitation cases prosecuted | 45 | 37 | 44 | 45 | 42 |  |  |  |
| 30 | Maternal mortality ratio (Institutional) | 39.6/100,000 | 0 | 39.6/100,000 | 40/100,00 | 0/100,000 | Training of health staff, Quarterly DRMT meeting, Fumigation exercise (Anti-mosquito spraying).Health Sensitization on Radio. Community Sensitization on health issues | Insufficient fumigation materials, Inadequate funds for health monitoring | More fumigation materials should be provided to the health units, funds should be released on time to carry out monitoring activities |
| 31 | Malaria case fatality (Institutional) |  |  |  |  |  |  |  |  |
|  | i. District | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | ii. Under five | 5 | 0 | 3 | 0 | 0 |  |  |  |
|  | iii. Women between 15-49 | 0 | 0 | 0 | 0 | 0 |  |  |  |
| 32 | Number functional adolescent health club | 7 | 10 | 7 | 10 | 8 |  |  |  |
| 33 | Recorded cases of child abuse |  |  |  |  |  | Radio Sensitization on Child and GBV | Inadequate funds to abuse related issues | Timely release of funds to support activities |
|  | i. Child trafficking, | 2 | 0 | 0 | 0 | 0 |  |  |  |
|  | ii. child labour, | 32 | 0 | 0 | 0 | 0 |  |  |  |
|  | iii. sexual abuse, | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | iv. emotional abuse | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | v. neglect. | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | vi. early marriage | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | vii. female genital mutilation | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | viii. family-child separation | 0 |  | 0 | 0 | 4 |  |  |  |
| 34 | Percentage of road network in good condition |  |  |  |  |  |  |  |  |  |
|  | Total | 64% | 100% | 64% | 100% | 0% | Reshaping of feeder roads | Inadequate funds to reshape roads across the district | The ministry of roads should collaborate with MMDAs to reshape roads in the district |
|  | Urban | NA | NA | NA | NA | NA |  |  |  |
|  | Feeder | 64% | 100% | 64% | 100% | 0% |  |  |  |
| 35 | Percentage of communities covered by electricity |  |  |  |  |  |  |  |  |  |
| i | · District | 96.70% | 100% | 96.70% | 90% | 100% | Extension of Electricity to Community. Collaboration meeting between the Assembly and ECG | Faulty Meters, late payment of Electricity bills | Replacement of Faulty Meters. |
| ii | · Rural | 93.50% | 100% | 93.50% | 90% | 100% |  |  |  |
| iii | · Urban | 98.70% | 99.50% | 98.70% | 90% | 100% |  |  |  |
| 36 | Prevalence of malnutrition (institutional) |  |  |  |  |  |  |  |  |  |
|  | • Wasting | N/A | 0% | 0% | 0% | 0% | Child health promotion activities, distribution of vitamins to enfants | Inadequate funds to organize child promotion activities | Timely release of funds to support activities |
|  | • Underweight | N/A | 0% | 4.30% | 0% | 0% |  |  |  |
|  | • Stunting | N/A | 0% | 4.70% | 0% | 0% |  |  |  |
|  | • Overweight | N/A | 0% | 0% | 0% | 0% |  |  |  |
| 37 | Reported cases of crime |  |  |  |  |  |  |  |  |  |
|  | i. Rape | 0 | 0 | 0 | 0 | 4 | Radio Sensitization on the effects and consequences associated with crime and the need to thrive in peaceful society | Inadequate funds and logistics to cramp down criminals | Provision of logistics to facilitate the work of the security services in cramping down criminals |
|  | ii. Armed robbery | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | iii. Defilement | 0 | 0 | 0 | 0 | 14 |  |  |  |
|  | iv. Murder | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | v. Drug trafficking | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | vi. Peddling | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | vii. Drug abuse | 0 | 0 | 0 | 0 | 0 |  |  |  |
|  | viii. Domestic violence | 0 | 0 | 0 | 0 | 0 |  |  |  |
| EMERGENCY PLANNING AND PREPAREDNESS DIMENSION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 38 | Number of communities affected by disaster |  |  |  |  |  |  |  |  |  |
| i | Bushfire | 2 | 0 | 0 | 0 | 4 | Education and sensitization programmes on disaster prevention. Monitoring and Evaluation exercise to assess the impact of the education and sensitization programs being carried out. | Inadequate relief items, safety gears for staff, absence of official vehicle for operations and emergency duties and lack of communal spirit that is necessary for effective disaster management in the district | Relief items must be priotized to support victims of disasters, logistics should be provided to staff for emergency duties |
| ii | Floods | 4 | 0 | 4 | 0 | 2 |  |  |  |
| iii | Wind/Rainstorm | 0 | 0 | 0 | 0 | 2 |  |  |  |
| 39 | Number of Public Education Campaigns on Climate and Disaster carried out | 6 | 10 | 8 | 10 | 12 |  |  |  |
| 40 | Number of Field Trip & Assessment undertaken on disaster prone areas | 4 | 5 | 4 | 5 | 4 |  |  |  |
| 41 | Number of major drains/other waterways dredged | 10 | 10 | 12 | 15 | 25 |  |  |  |
| 42 | Number of District Disaster Management Committee meetings held | 1 | 3 | 2 | 3 | 1 |  |  |  |
| 43 | Proportion of population who have tested positive for covid-19 | 0.68% | 0 | 0 | 0 | 0 | Regular Sensitization on Covid Preventive measures | NRD | NRD |
| IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION DIMENSION |  |  |  |  |  |  |  |  |  |  |
| 44 | Percentage of annual action plan implemented | 91.60% | 100% | 92.96% | 100% | 92.98% | Monitoring and Evaluation of most projects and programmes in the AAP | Late submission of quarterly reports, noncollaboration of some decentralized agencies within the District | Workshop should be organized for decentralized agencies to cooperate with the Assembly |
| DISTRICT SPECIFIC INDICATORS |  |  |  |  |  |  |  |  |  |  |
| Start with the underlisted Integrated Social Services (ISS) indicators |  |  |  |  |  |  |  |  |  |  |
| 1 | Number of trainings conducted on ISSOPs | 1 | 10 | 5 | 4 | 4 | Training on how to use the CP toolkit App - 8th Dec. 2023 | Financial and logistical constraints | Training on the effective use of the toolkits |
| 2 | Proportion of case workers trained in child protection and family welfare | 7 | 15 | 4 | 9 | 9 | In - House training for officers on Child Protection and Case management issues | Financial and logistical | More training should be organized for officers |
| 3 | Number of child violence cases benefitting from social welfare/social services | 45 | 50 | 16 | 50 | 54 | In partnership with other NGOs, training was organized for selected community members on relevant topics such as Child labour and Gender Based Violence | Lack of resources: funds and logistics | More sensitization programme should be organized on child violence to educate them on their rights and responsibilities as children |
| 4 | Number of children reached by social work/social services | 36 | 50 | 62 | 65 | 58 | Specific officers are assigned to follow-up on affected children | Transportation problems | Adequate financial and logistical resources is needed to reach out to more children. |
| 5 | Number of people reached with child protection and SGBV information | 3,604 | 1279 | 1279 | 850 | 1,088 | Community training and sensitization on Child Protection and SGBV issues. This was championed by the Gender Desk | Delay in funds disbursement | funds should be disbursed in time to meet deadlines |
| 6 | Number of LEAP household members on NHIS | 1,097 | 817 | 817 | 1,297 | 1,297 | Community engagement with Leap beneficiaries to educate them on the importance of the LEAP programme and to address their concerns | Transportation challenges | funds should be made available to educate beneficiaries |
| 7 | Number of households with adolescent girls benefiting from LEAP | 1,297 | 35 | 27 | 500 | 331 | Community engagement with Leap beneficiaries to educate them on the importance of the LEAP programme and to address their concerns | Common problems reported by beneficiaries include: 1. Lost/missing cards 2. Faulty | The department needs a vehicle to embark on its outreach visits/programme |
| 8 | Number of outreach visits to communities with LEAP households | 5 | 30 | 24 | 53 | 53 | Community engagement with Leap beneficiaries to educate them on the importance of the LEAP programme and to address their concerns | The department needs a vehicle to embark on its outreach visits/programme | More training packages should be organized for officers to keep them abreast on modern trends |
| 9 | Number of referrals received from GHS | 1 | 5 | 3 | 30 | 10 | Regular meeting with health directorate | Inadequate funds to follow up of referred casses | Timely release of funds |
| 10 | Proportion of referrals receiving adequate follow-up | 100% | 100% | 100% | 10 | 7 | Specific officers were assigned to follow-up on specific | inadequate funding lack of vehicular movement | Provision of adequate funds |
| 11 | Number of DSWCD’s that have shared their MMDA’s LEAP Household data with both NHIS and GHS | Yes | 1 | 1 | 1 | 1 | NRD | NRD | NRD |
| 12 | Number of regional intersectoral monitoring visits conducted | 1 | 1 | 1 | 1 | 1 | A team from the Regional Office visited the Department in Dec. 2023 to train officers on the CP toolkit | logistical challenges | Provision of logistics |
| 13 | Number of meetings organised to discuss integrated services | 1 | 1 | 1 | 1 | 1 | A meeting was organized with key stakeholders in the area of child welfare and disability | lack of funds to organize meetings | assembly should support/a |
| 14 | Number of girls reached by prevention and care services | 3,604 | 10 | 5 | 300 | 292 | The gender desk reached out girls in selected communities to educate them on relevant topics | most of the girls in schools are not met | The department should be well resourced for it to be able to organize more programmes for girls |
| 15 | Number of CP/SGBV cases referred to other services and followed up | 1 | 15 | 9 | 10 | 7 | In partnership with UNICEF. Community engagement was organized to educate community members on relevant topics | inadequate funding | The Gender Desk should be well resourced |
| 16 | Number of NGOs, including RHCs, trained | 2 | 3 | 2 | 3 | 2 | NRD | inadequate funds | Training should be organized for NGOs |
| 17 | Number of children in RHCs profiled and reunified | 7 | 7 | 7 | 12 | 1 | NRD | source of funding | Training should be organized for RHCs |
| 18 | Proportion of sub-standard RHCs closed | 0 | 0 | 0 |  | 1 | NRD | NRD | NRD |
| 19 | Number of children placed in foster care | 0 | 5 | 0 | 5 | 0 | No training was done. However, workshop on fostering was organized in 2022 | the number of persons picking up forms to register as foster parents is not encouraging | Workshop should be organized for interested persons on fostering |
| 20 | Proportion of population with access to basic drinking water sources | 92.00% | 100% | 82.60% | 100% | 92% | Construction of Boreholes, Collaboration with Ghana Water Company and Community Water and Sanitation | Broken pipes, late payment of water bills, low coverage of GWCL pipes, salinity of water from boreholes | Extension of GWCL pipelines, Filtration of saline water, repair of broken pipes |
| 21 | Proportion of population with access to improved sanitation services | 89.00% | 100% | 52.60% | 100% | 58.60% | Desilting of choked drains. Monitoring and Supervision of Service Provider. Evacuate and Push 10 refuse heaps sites | Lack of vehicle for regular visit to the communities, Inadequate equipment and unskilled laborers to improve on Sanitation in the district, Indiscriminate and open defecation in the communities and Beaches, Lack of cooperation and compliance by some of the community members. | The Regional Environment dpt should train staff on sanitation improvement activities, sensitization of indigenes to keep their homes neat. |
| 22 | Number of people in ODF communities | 40665 | 39383 | 40665 | 41,000 | 39894 | Sensitization on radio and community engagement | Attitudinal change | Continuous sensitization and engagement |
| 23 | Number of staff trained | 106 | 160 | 167 | 170 | 167 | Training on Local government Safety protocol Defensive driving, etc | Inadequate funds and logistics | Release of funds and logistical support |
| 24 | Number of Assembly Members and Unit Committee trained | 110 | 110 | 105 | 110 | 110 |  |  |  |
| 25 | Police Citizen Ratio | 1:1450 | 1:1450 | 1:1532 | 1:1550 | 1:1620 | Training on Safety and Security | Inadequate Personnel | Government should recruit more personnel |
| 26 | Number of Public engagements organized | 32 | 50 | 47 | 60 | 72 | Assembly on Radio and community engagement | Funds and logistics | Timely release of funds and logistics |
| 27 | Number of Spatial Plans Prepared | 8 | 10 | 12 | 15 | 18 | Preparation of Local Plans | Inadequate logistics | Provision of adequate logistics to support the Department |
| 28 | Number of Radio Sensitization organized | 23 | 48 | 36 | 48 | 44 | Assembly on radio programmes | Inadequate funds | Timely release of funds |

NRD-No Reliable Data